## Sheet1
Work Order | Priority | Status | Type | Equipment | Equipment Description | Description | Assigned To | Date Created | Sched. Start Date | Department | Safety | Persons Required | Estimated Hs | Trade | Class
1353549 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0600-EAST PLINT CONTAINMENT | East PLINT Containment | North west outer wall leaking between CL601 floc skid and East PLINT | COSERMO | 2024-12-02 15:50 | 2024-12-02 | 600 | No | 1 | 1 | NC-CONT-MECH
1388587 |  | Scoping Required | Corrective | 0700-FF-725-BIN | FF-725 -SODIUM SULFIDE CONVEYOR | FF-725 Need a new motor mount plate made and installed | COSERMO | 2025-05-23 11:58 | 2025-05-23 | 700 | No | 2 | 4 | NC-CONT-MECH
1396126 | 2-Urgent/Scheduled | Scoping Required | Corrective | 1500-800-001 | 1500-800-001-FIRE WATER PUMP HOUSE | (OUTAGE)Water Seeping from Key on East Side of Pump House. |  | 2025-06-30 14:08 | 2025-06-30 | 800 | No | 1 | 1 | NC-CONT-MECH
1400352 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0900-BA-901-FURNACE | BA-901 -ROTARY/RECYCLE FURNACE | Move hydraulic unit outside of building | COSERMO | 2025-07-14 13:06 | 2025-07-14 | 900 | No | 2 | 10 | NC-CONT-MECH
1400276 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0300-GYPSUM PRECIP CONTAINMENT | Gypsum Precip Containment | Gypsum south wall behind the GA-301 pumps has a slow leak on a crack in the wall | LOBO | 2025-07-12 22:04 | 2025-07-12 | 300 | No | 1 | 1 | NC-LCS CONTRACT
1366445 | 3-First Opportunity | Scoping Required | Corrective | 1500-ENV-90 DAY STORAGE | ENVIRONMENTAL 90 DAY STORAGE - ORIGINAL WHITE TENT | Water Intrusion - 90-day tent and roll off pad. | LOBO | 2025-02-12 13:00 | 2025-02-12 | 200 | No | 1 | 1 | NC-LCS CONTRACT
1390076 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | Hydrulic tubing supports for both CSM Machines (11-14) | COSERMO | 2025-06-03 09:02 | 2025-06-03 | 400 | No | 2 | 4 | NC-CONT-MECH
1424526 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0100-CL-151-A | 0100-CL-151-A NEUTRAL LEACHING THICKENER | We need to verify filter differential switches on CL-151A & CL-151B work | AALEXEYEV | 2025-11-11 13:09 | 2025-11-11 | 100 | No | 1 | 1 | NC-E/I
1365369 |  | Scoping Required | Corrective | 0400-CB-6D-MCC03 | UPS-400-01 PLC Uninterruptable Power Supply | UPS needs service |  | 2025-02-04 13:57 | 2025-02-04 | 400 | No | 2 | 4 | NC-CONT-ELEC
1359175 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 1500-1100-005 | 1500-1100-005-LIGHT MAINTENANCE SHOP | Safety shower east side at ACT fan level needs insulated | LOBO | 2025-01-02 11:32 | 2025-01-02 | 200 | Yes | 1 | 3 | NC-LCS CONTRACT
1378069 | 2-Urgent/Scheduled | Awaiting Parts | Corrective | 0300-PX-301-A | PX-301A GYPSUM BELT FILTER PACKAGE | Install rigging points in PX-301 basement | COSERMO | 2025-04-03 10:12 | 2025-04-03 | 300 | No | 1 | 2 | NC-CONT-MECH
1426323 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 1400-ME-0139 | 1400-ME-0139 2018 Kawaski Mule SX Green - Maintenance | Buggey #4 needs wheel bearings and brake switch | EQUIPMENT CREW | 2025-11-19 15:52 | 2026-02-13 | 1400 | No | 1 | 1 | NC-MECHANIC
1367173 | 2-Urgent/Scheduled | Scoping Required | Corrective | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | heat trace not working Zone#8 cic#6 GFEP | LOBO | 2025-02-14 21:14 | 2025-02-14 | 300 | No | 2 | 2 | NC-LCS CONTRACT
1445065 | 2-Urgent/Scheduled | Parts Required | Corrective | 0400-CA-402-STRIPPING | CA-402 Stripping Machine Stripping Conveyor | modify anti sway bay prox mounts | BBROUSE | 2026-02-25 08:32 | 2026-02-25 | 400 | No | 1 | 1 | NC-E/I
1445056 |  | Scoping Required | Corrective | 0800-EER-AREA 800 | Electrical Room Area 800 | SENS unit in 800MCC faulted | BBROUSE | 2026-02-25 06:06 | 2026-02-25 | 800 | No | 1 | 1 | NC-E/I
1445080 |  | Scoping Required | Corrective | 0400-CA-401-STACKER | CA-401 Stripping Machine Stacker | Replace limit switch box on the stacker hydraulic outlet manual valve on CSM 1 | AALEXEYEV | 2026-02-25 11:27 | 2026-02-25 | 400 | No | 1 | 1 | NC-E/I
1445081 |  | Scoping Required | Corrective | 0400-CA-402-STACKER | CA-402 Stripping Machine Stacker | Repair/replace limit switch box on stacker hyd. inlet manual valve on CSM 2 | AALEXEYEV | 2026-02-25 11:34 | 2026-02-25 | 400 | No | 1 | 1 | NC-E/I
1445021 | 2-Urgent/Scheduled | Scoping Required | Corrective | 100 | Leaching | PX-101 East walk-in door upstairs needs to be replaced. |  | 2026-02-24 10:48 | 2026-02-24 | 100 | No | 1 | 1 | NC-CONT-MECH
1430677 |  | Awaiting Parts | Corrective | 0500-PX-501 | PX-501 HERZOG METALS ANALYZER | Herzog machine power supply is burnt up |  | 2025-12-11 15:01 | 2025-12-11 | 500 | No | 1 | 1 | NC-E/I
1436256 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-FB-709-0-TANK | FB-709 SODIUM SULFIDE DAY TANK - METALS POLISHING | Add level transmitter to the tank | AALEXEYEV | 2026-01-09 14:24 | 2026-01-09 | 300 | No | 2 | 3 | NC-E/I
1437590 | 1-Emergency/Break-in | Scoping Required | Corrective | 0300-GA-321-B-PUMP | GA-321-B-GYPSUM PRECIPITATION CYCLONE UNDERFLOW SEED RECYCLE PUMP | GA-321 A and B Seal water line needs insulated | TMILLS2 | 2026-01-18 16:04 | 2026-01-18 | 300 | No | 1 | 1 | NC-CONT-MECH
1437644 | 1-Emergency/Break-in | Scoping Required | Corrective | 0700-FB-709-0-TANK | FB-709 SODIUM SULFIDE DAY TANK - METALS POLISHING | Repair Insulation on Sodium Sulfide line near FB-709 | TMILLS2 | 2026-01-20 05:45 | 2026-01-20 | 300 | No | 1 | 1 | NC-CONT-MECH
1440337 | 2-Urgent/Scheduled | Scoping Required | Corrective | 400 | ELECTROWINNING AREA 400 | support steps going to second level of cell house |  | 2026-01-29 07:19 | 2026-01-29 | 400 | No | 1 | 1 | NC-CONT-MECH
1445069 | 1-Emergency/Break-in | Scoping Required | Corrective | 0300-GA-321-A-PUMP | GA-321-A GYPSUM PRECIPITATION CYCLONE UNDERFLOW SEED RECYCLE PUMP | Process Water line feeding GA-321 A/B Seal Water needs replaced | TMILLS2 | 2026-02-25 09:14 | 2026-02-25 | 300 | No | 1 | 1 | NC-CONT-MECH
1445020 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0900-BA-902 | MZR ROTARY FURNACE | Install heat sheild btw control box & MZR furnace (do WO 1445018 first) | AALEXEYEV | 2026-02-24 10:39 | 2026-02-24 | 900 | No | 1 | 2 | NC-E/I
1444991 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0800-PX-808-B-COMPR | 0800-PX-808-B-AIR COMPRESSOR | PX-808-B- needs scoping, burnt T lead control panel | SALLEN2 | 2026-02-23 13:52 | 2026-02-23 | 800 | No | 1 | 1 | NC-CONT-ELEC
1444969 |  | Parts Required | Corrective | 0800-PX-808-A-COMPR | 0800-PX-808-A-AIR COMPRESSOR | PX-808-A- Needs scoping, oil is leaking from the back of the compressor | SALLEN2 | 2026-02-23 08:33 | 2026-02-23 | 800 | No | 1 | 1 | NC-CONT-MECH
1445031 | 2-Urgent/Scheduled | Parts Required | Corrective | 0400-LCV-4040 | FA-408 SRCO3 MIXING TANK LCV-4040 | Order and Install new 1" ball valve body for 400-32070 and re-stock |  | 2026-02-24 12:50 | 2026-02-24 | 400 | No | 1 | 1 | NC-MECHANIC
1445050 | 1-Emergency/Break-in | Awaiting Parts | Corrective | 900 | METAL RECYCLING, AREA 900 | Replace pin right front bucket of skid steer 900 area (Hicham) | EQUIPMENT CREW | 2026-02-24 16:04 | 2026-02-24 | 900 | No | 1 | 1 | NC-EQUIPMENT
1377486 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0100-GA-110-A-PUMP | GA-110A WOX FEED PREPARATION SUMP PUMP (650 GPM @ 61' TDH, 20 HP) | Modify I beams/utilities overhead to improve safety during pump swaps | COSERMO | 2025-04-03 08:04 | 2025-04-03 | 100 | Yes | 2 | 4 | NC-CONT-MECH
1445116 |  | Scoping Required | Corrective | 0400-CA-401-CATHBRUSH | CA-401 Stripping machine Cathode Brush System | Light needs replaced on CSM 1 facing cathode brushes | BBROUSE | 2026-02-26 05:08 | 2026-02-26 | 400 | No | 1 | 1 | NC-E/I
1377487 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-GA-700-E-DAMPNER | GA-700E WOX SLURRY PREPARATION DAMPNER | Design a trolley system to move dampeners through the 700 building | COSERMO | 2025-04-03 08:06 | 2025-04-03 | 700 | No | 2 | 3 | NC-CONT-MECH
1399453 | 3-First Opportunity | Open - Ready to Schedule | Corrective | 0200-GA-204-B-PUMP | GA-204B FILTERED RAFFINATE PUMP (2500 GPM AT 180' TDH, 4160 VAC, 200 HP) | GA-204 B Need to install new check valve And spool | TMILLS2 | 2025-07-08 14:23 | 2025-07-08 | 200 | No | 2 | 6 | NC-CONT-MECH
1440304 | 2-Urgent/Scheduled | Scoping Required | Corrective | 500 | MELTING / CASTING, AREA 500 | Run hard line from cabinet to bolt resetters on slab lines | COSERMO | 2026-01-28 13:08 | 2026-01-28 | 500 | No | 1 | 1 | NC-CONT-MECH
1444961 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0200-FD-203-C-FILTER | FD-203C DEPLETED SOLUTION FILTER (NORMAL 506.8 / MAX 1258.4 GPM, 40 C, 0) | FD-203C Piping needs repaired, see Teams | COSERMO | 2026-02-23 07:40 | 2026-03-09 | 200 | No | 1 | 1 | NC-CONT-MECH
1444936 | 1-Emergency/Break-in | Open - Ready to Schedule | Corrective | 0200-DC-201-B | 0200-DC-201-B HCL RECOVERY REACTOR | DC-201B leaking on top 10" EJ | TMILLS2 | 2026-02-22 06:56 | 2026-02-22 | 200 | No | 1 | 1 | NC-CONT-MECH
1444935 | 2-Urgent/Scheduled | Parts Required | Corrective | 0300-PX-323-A | PX-323-A GYPSUM OSCILLATING SPRAY BAR MOTOR [FOR PX-301A] | replace motor on gear box (Rebuild shed) | REBUILD CREW | 2026-02-21 23:31 | 2026-02-21 | 300 | No | 1 | 1 | NC-REBUILD
1383202 |  | Scoping Required | Corrective | 0200-FA-208-A-TANK | FA-208A 2ND STAGE STRIPPING MIXER 1 (886.4 FT3, 0) | FA-208-A- has a steam leak at the T that needs to be welded. | COSERMO | 2025-05-01 11:12 | 2025-05-01 | 200 | No | 1 | 1 | NC-CONT-MECH
1437495 | 1-Emergency/Break-in | Scoping Required | Corrective | 0300-GA-320-B-PUMP | GA-320-B GYPSUM PRECIPITATION CYCLONE UNDERFLOW ADVANCE PUMP | GA-320 B Need seal water lines insulated | TMILLS2 | 2026-01-16 14:59 | 2026-01-16 | 300 | No | 1 | 1 | NC-CONT-MECH
1437444 | 3-First Opportunity | Open - Ready to Schedule | Corrective | 0500-CA-505 | CGG / SHG JUMBO INGOT MOLDS | Jumbos-change cylinders on 6,7,8,9,10,& 12 |  | 2026-01-15 14:23 | 2026-01-15 | 500 | No | 2 | 1 | NC-MECHANIC
1444880 |  | Open - Ready to Schedule | Corrective | 0400-CCTV-DUKE-SUBSTATION | DUKE SUBSTATION CAMERA | Replace lens on Duke Substation (Harmonic filter) camera with replacement lens |  | 2026-02-20 09:14 | 2026-02-20 | 400 | No | 1 | 1 | NC-E/I
1448637 |  | Open - Ready to Schedule | Corrective | 0300-PX-303-A | 0300-PX-303-A LIQUID EFFLUENT PRESS FILTER PACKAGE | REPLACE DCV FOR THE DRIP TRAY | TMILLS2 | 2026-03-18 08:39 | 2026-03-18 | 300 | No | 1 | 1 | NC-MECHANIC EXE
1448652 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 1000 | RAILYARD, CO-PRODUCT/RAW MATERIAL/REAGENT HANDLING AND STORAGE | Evaporative Cooler Install (Cosermo) | COSERMO | 2026-03-18 14:28 | 2026-03-25 | 1000 | No | 1 | 1 | NC-CONT-MECH
1401276 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0200-GA-227-PUMP | GA-227 HCL DRAINING TANK PUMP FOR PX-203 | Suction spool needs replaced including sample port | COSERMO | 2025-07-22 10:42 | 2025-07-22 | 200 | No | 2 | 2 | NC-CONT-MECH
1448426 | 3-First Opportunity | Scoping Required | Corrective | 200 | SOLVENT EXTRACTION, AREA 200 | 4 Lights need to be replaced in the Site Services trailer | AALEXEYEV | 2026-03-16 10:39 | 2026-03-16 | 200 | No | 1 | 1 | NC-E/I
1418495 |  | Scoping Required | Corrective | 100 | Leaching | Repair short in heat trace junction box Heat trace zone 2 |  | 2025-10-12 16:03 | 2025-10-12 | 100 | No | 1 | 1 | NC-LCS CONTRACT
1442895 | 1-Emergency/Break-in | Scoping Required | Corrective | 0600-PX-601 | 0600-PX-601 LEAD LEACHING FILTRATION PACKAGE | PX-601 filtrate receiver pump has exposed wiring at motor junction box | BBROUSE | 2026-02-10 12:47 | 2026-02-10 | 600 | Yes | 1 | 1 | NC-E/I
1442899 | 1-Emergency/Break-in | Scoping Required | Corrective | 0600-PX-601 | 0600-PX-601 LEAD LEACHING FILTRATION PACKAGE | PX-601 louvers in the basement need to be replaced | TMILLS2 | 2026-02-10 12:53 | 2026-02-10 | 600 | No | 1 | 1 | NC-CONT-MECH
1442900 | 1-Emergency/Break-in | Scoping Required | Corrective | 0600-PX-601 | 0600-PX-601 LEAD LEACHING FILTRATION PACKAGE | South walk-in door for PX-601 basement needs to be replaced. | TMILLS2 | 2026-02-10 12:54 | 2026-02-10 | 600 | No | 1 | 1 | NC-CONT-MECH
1442910 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0700-GA-795-0-PUMP | GA-795 SULFURIC ACID STORAGE SUMP PUMP | Water Line feeding GA-795 seal water leaking under insulation | SWORLEY2 | 2026-02-10 14:07 | 2026-02-10 | 700 | No | 1 | 1 | NC-CONT-MECH
1442889 | 2-Urgent/Scheduled | Awaiting Parts | Corrective | 1000-RC-RAIL | AREA 1000 RAILYARD EQUIPMENT | (Outage) Bay door on North of track 11 is going to need repaired |  | 2026-02-10 10:54 | 2026-04-07 | 1000 | No | 1 | 1 | NC-CONT-MECH
1448403 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-OH-0100-SKID-PX-703 | CALCIUM HYDROXIDE SILO PREPARATION PACKAGE (1800 FT3) | 2ND FLOOR door latch needs repaired |  | 2026-03-15 19:39 | 2026-03-15 | 300 | No | 1 | 1 | NC-MECHANIC EXE
1448475 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-PC-701-0-CONVEYOR | WOX WEIGH FEEDER BELT CONVEYOR (28 STPH, 2 HP) | PC-701 door latches at the load cells need replaced | AALEXEYEV | 2026-03-17 08:22 | 2026-03-17 | 700 | No | 1 | 1 | NC-E/I
1448470 | 2-Urgent/Scheduled | Scoping Required | Corrective | 100 | Leaching | PLS road lights do not work or are strobing. (AC-INC-20260317-005) | BBROUSE | 2026-03-17 04:31 | 2026-03-17 | 100 | Yes | 1 | 1 | NC-E/I
1448427 |  | Open - Ready to Schedule | Corrective | 0100-PIT-1136-A | WOX FEED SLURRY TO GA-136A | FT-1136 A Needs rolled out for site services | TMILLS2 | 2026-03-16 12:02 | 2026-03-16 | 100 | No | 1 | 1 | NC-MECHANIC EXE
1448472 | 2-Urgent/Scheduled | Scoping Required | Corrective | 1400-ME-0182 | 1400-ME-0182 Ford Escape 2010 | Right rear window will not roll up | EQUIPMENT CREW | 2026-03-17 07:37 | 2026-03-23 | 1400 | No | 1 | 2 | NC-CONT-MECH
1381467 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-GA-752-A-PUMP | GA-752A LIMESTONE DISTRIBUTION PUMPS (280 GPM @ 134' TDH, 40 HP) | Replace damaged line for GA-752-A/B. Line was E-wrapped | COSERMO | 2025-04-23 12:17 | 2025-04-23 | 100 | No | 1 | 1 | NC-CONT-MECH
1364411 |  | Scoping Required | Corrective | 0200-ELECTROLYTE CONTAINMENT | Electrolyte Containment | Containment Needs an Overhaul of Concrete Repair | LOBO | 2025-01-28 14:18 | 2025-01-28 | 200 | No | 1 | 1 | NC-LCS CONTRACT
1372837 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-GA-405-0-PUMP | GA-405 SPENT ELECTROLYTE RECIRCULATION PUMP #5 (177' TDH @ 3440GPM) | Install pressure gauge on suction piping | COSERMO | 2025-03-13 13:03 | 2025-03-13 | 400 | No | 2 | 2 | NC-CONT-MECH
1381503 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0200-DC-201-A | 0200-DC-201-A HCL RECOVERY REACTOR | Steam line to the DC-201 A leak needs inspected. | COSERMO | 2025-04-24 05:14 | 2025-04-24 | 200 | No | 1 | 2 | NC-CONT-MECH
1416754 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CA-402-STACKER | CA-402 Stripping Machine Stacker | Replace hydraulic hard lines to stacker | COSERMO | 2025-09-29 13:50 | 2025-09-29 | 400 | No | 1 | 1 | NC-CONT-MECH
1416753 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CA-401-STACKER | CA-401 Stripping Machine Stacker | Replace hydraulic hard lines to stacker | COSERMO | 2025-09-29 13:49 | 2025-09-29 | 400 | No | 1 | 1 | NC-CONT-MECH
1407836 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0700-FB-700-F-BIN | WOX SILO BIN F (4975 FT3, 0) 11'X11' X 35'-3/4" SSH | Modify WOX baghouse discharge for better access to broken bag detector | COSERMO | 2025-08-08 13:17 | 2025-08-08 | 700 | No | 2 | 3 | NC-CONT-MECH
1410749 | 1-Emergency/Break-in | Scoping Required | Corrective | 0400-GA-453-PUMP | 0400-GA-453-EW SLUDGE PUMP | Modify suction piping on GA-453 to match GA-700s design | COSERMO | 2025-09-04 09:19 | 2025-09-04 | 400 | No | 1 | 1 | NC-CONT-MECH
1416866 | 2-Urgent/Scheduled | Scoping Required | Corrective | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | Replace/ repair the bent support post for the gasoline containment shipping |  | 2025-10-01 08:06 | 2025-10-01 | 1100 | No | 1 | 1 | NC-CONT-MECH
1448387 | 1-Emergency/Break-in | Scoping Required | Corrective | 0500-CA-505 | CGG / SHG JUMBO INGOT MOLDS | Mold #2 has multiple water leaks. | COSERMO | 2026-03-15 08:16 | 2026-03-15 | 500 | No | 1 | 1 | NC-CONT-MECH
1450113 | 2-Urgent/Scheduled | Parts Required | Corrective | 0900-BA-902 | MZR ROTARY FURNACE | Replace shaft in MZR furnace. |  | 2026-03-20 16:54 | 2026-03-20 | 900 | No | 1 | 1 | NC-MECHANIC EXE
1450136 | 1-Emergency/Break-in | Scoping Required | Corrective | 0200-GA-250-B-MOTOR | GA-250B RAFFINATE TO FILTER PUMP MOTOR (4160 VAC, 125 HP) | GA-250 Tripped on overtemp | BBROUSE | 2026-03-21 17:32 | 2026-03-21 | 200 | No | 1 | 1 | NC-E/I
1450206 | 1-Emergency/Break-in | Scoping Required | Corrective | 0400-GB-401-0-FILTER | STAINLESS STEEL FINE FILTER | GB-401 air leak Alpha tank | COSERMO | 2026-03-23 10:14 | 2026-03-23 | 400 | No | 1 | 1 | NC-CONT-MECH
1444537 | 3-First Opportunity | Scoping Required | Corrective | 0500-CA-501-HPU | CA-501 Slab Casting Hydraulic Power Unit | Replace hyd line with butt weld fittings | COSERMO | 2026-02-20 07:44 | 2026-02-20 | 500 | No | 1 | 1 | NC-CONT-MECH
1444528 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0300-PX-301-B | PX-301B GYPSUM BELT FILTER PACKAGE | PX-301 B has a broken cable and few frayed ones on the vacuum tray. | BBROUSE | 2026-02-20 04:47 | 2026-02-20 | 300 | No | 1 | 1 | NC-E/I
1444527 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CB-01-A-3-X-MLD | MCC-400-01 | Install Camrea in Upper MCC 400 | AALEXEYEV | 2026-02-20 02:05 | 2026-02-20 | 400 | No | 1 | 1 | NC-E/I
1448317 | 2-Urgent/Scheduled | Scoping Required | Corrective | 400 | ELECTROWINNING AREA 400 | replace all step treads on stairs to csm level |  | 2026-03-13 09:11 | 2026-03-13 | 400 | Yes | 1 | 1 | NC-CONT-MECH
1448383 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0100-PX-183-PRSFLTR | PX-183 PRESS FILTER PACKAGE | PX-183 hopper brace is not attached on the left side | COSERMO | 2026-03-15 05:12 | 2026-03-15 | 100 | No | 1 | 1 | NC-CONT-MECH
1450151 |  | Scoping Required | Corrective | 0700-OH-0100-REACTOR-DC-703 | CALCIUM HYDROXIDE MIXING TANK | Replace load cell 4 under PX-703 mix tank | AALEXEYEV | 2026-03-22 05:59 | 2026-03-22 | 700 | No | 1 | 6 | NC-E/I
1450219 | 1-Emergency/Break-in | Open - Ready to Schedule | Corrective | 400 | ELECTROWINNING AREA 400 | Bay1 cell33 overflow box sleeve is leaking |  | 2026-03-23 12:40 | 2026-03-23 | 400 | No | 1 | 1 | NC-MECHANIC EXE
1450222 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-GA-700-E-PUMP | GA-700E WOX SLURRY PREPARATION TANK PUMP | GA-700E discharge Clarkson needs to be replaced | TMILLS2 | 2026-03-23 14:38 | 2026-03-23 | 700 | No | 1 | 1 | NC-MECHANIC EXE
1450212 | 3-First Opportunity | Scoping Required | Corrective | 1500 | 1500-BUILDING AND GROUNDS | Women's locker room- the sink on the red side is spraying water in the floor |  | 2026-03-23 11:17 | 2026-03-23 | 1500 | No | 1 | 1 | NC-CONT-MECH
1450116 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0700-GA-721-B-PUMP | GA-721 SODA ASH SOLUTION PUMP (170 GPM @ 97' TDH, 30 HP) | GA-721B seal leak, Pull, Rebuild, & Reinstall (D8M) | REBUILD CREW | 2026-03-21 03:40 | 2026-04-02 | 600 | No | 2 | 8 | NC-REBUILD
1450239 |  | Scoping Required | Corrective | 0700-DC-703-0-REACTOR | DC-703 CALCIUM HYDROXIDE MIXING TANK TO AREA 0300 | Replace LT-7655 on 703 Mix tank with economical EH level transmitter | TMILLS2 | 2026-03-24 05:25 | 2026-03-24 | 300 | No | 2 | 1 | NC-E/I
1450207 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0100-PX-101-B | 0100-PX-101-B FILTER PRESS | Operator side shifter pin keeps popping out. Spring may need replaced | TMILLS2 | 2026-03-23 10:26 | 2026-03-30 | 100 | No | 1 | 1 | NC-MECHANIC EXE
1450200 | 1-Emergency/Break-in | Scoping Required | Corrective | 100 | Leaching | Repair BOBCAT 12-19-23 | EQUIPMENT CREW | 2026-03-23 08:55 | 2026-03-23 | 100 | No | 1 | 1 | NC-EQUIPMENT
1450087 | 3-First Opportunity | Scoping Required | Corrective | 1000-RC-RAIL | AREA 1000 RAILYARD EQUIPMENT | Swamp cooler electrical cord needs replaced | AALEXEYEV | 2026-03-20 10:43 | 2026-03-20 | 1000 | No | 1 | 1 | NC-E/I
1410705 | 2-Urgent/Scheduled | Parts Required | Corrective | 0400-CA-401-VKNIFE | CA-401 Stripping machine Vertical Knife | Hard pipe counter balance valve | COSERMO | 2025-09-03 13:55 | 2025-09-03 | 400 | No | 1 | 3 | NC-CONT-MECH
1450146 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0400-GA-406-B-PUMP | GA-406B PUMP (1375 GPM @ 66' TDH) | Ga-406 B pull, rebuild, and reinstall. | REBUILD CREW | 2026-03-21 21:16 | 2026-04-02 | 400 | No | 1 | 1 | NC-REBUILD
1450120 |  | Open - Ready to Schedule | Corrective | 0200-FA-209-A-TANK | FA-209A DEPLETION MIXER 1 (886.4 FT3, 0) | reattach conduit FA-209-A (Nights) | AALEXEYEV | 2026-03-21 06:08 | 2026-03-21 | 200 | No | 1 | 1 | NC-E/I
1410654 | 3-First Opportunity | Scoping Required | Corrective | 0500-PC-503 | Slab Casting Transfer Cart/Walking Beam Conveyor | PC-503 build guarding for cable tray (Cosermo) |  | 2025-09-02 12:58 | 2025-09-02 | 500 | No | 2 | 4 | NC-CONT-MECH
1364210 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0700-FB-708-0-TANK | SULFURIC ACID STORAGE TANK (NOMINAL 7238 / NET 1962 FT3, 20-60 C) | Eyewash process water line busted behind FB-708 | LOBO | 2025-01-24 11:42 | 2025-01-24 | 700 | Yes | 1 | 1 | NC-LCS CONTRACT
1379939 | 1-Emergency/Break-in | Scoping Required | Corrective | 1500-1100-OIL STORAGE / FUEL | MAINTENANCE RED BARN USED FOR OIL STORAGE / FUEL STATION | Diesel pump running slow at fueling station |  | 2025-04-11 10:40 | 2025-04-11 | 200 | No | 1 | 1 | NC-CONT-MECH
1444506 | 2-Urgent/Scheduled | Scoping Required | Corrective | 14266 | BC-301 -PX-301 BUILDING HEATER | PX-301 Basement- 2 Breaker panels need covers | AALEXEYEV | 2026-02-19 12:12 | 2026-02-19 | 800 | No | 1 | 1 | NC-E/I
1448099 | 2-Urgent/Scheduled | Awaiting Parts | Corrective | 0100-PX-183-PRSFLTR | PX-183 PRESS FILTER PACKAGE | PX-183 getting a fault for GENERAL FAILURE SEQUENCE: HIGH PRESSURE CLOTHES WASHI | AALEXEYEV | 2026-03-13 05:14 | 2026-03-13 | 100 | No | 1 | 1 | NC-E/I
1450089 | 3-First Opportunity | Scoping Required | Corrective | 0200-LT-2110-0-CTRL | FE-201 1ST EXTRACTION SETTLER LT-2110 | Seal gaps around level transmitters on SX settler train | AALEXEYEV | 2026-03-20 10:55 | 2026-03-20 | 200 | No | 1 | 5 | NC-E/I
1446227 |  | Scoping Required | Corrective | 0300-GA-316-A-PUMP | GA-316A ZINC PRECIPITATION PUMP (1489 GPM @ 36.3 FT, 100 HP) | GA-316 Seal water lines need insulated | TMILLS2 | 2026-03-03 11:39 | 2026-03-03 | 300 | No | 1 | 1 | NC-CONT-MECH
1446278 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 400 | ELECTROWINNING AREA 400 | Replace # 12 EQ bar | MECH EXE CREW | 2026-03-04 10:14 | 2026-04-07 | 400 | No | 3 | 3 | NC-MECHANIC EXE
1446253 |  | Open - Ready to Schedule | Corrective | 0300-CL-302 | CL-302 METALS POLISHING THICKENER | Upside existing E3 in GX-302 from a 2A max to a 5A max (FLA on motor is 2.6A) | AALEXEYEV | 2026-03-03 18:17 | 2026-03-03 | 300 | No | 1 | 1 | NC-E/I
1446290 | 3-First Opportunity | Scoping Required | Corrective | 0400-NCW-1065-CONT-FA-419 | FA-419 NON-CONTACT COOLING WATER TOWER COLD WELL, 12,000 GALLONS | Replace cooling water supply valve to EW |  | 2026-03-04 11:32 | 2026-04-07 | 400 | No | 1 | 1 | NC-MECHANIC EXE
1366131 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0300-CB-01-C-X-MLD | MCC-300-01 D-300-E-0101 | Need to address issues with ER300 480V LVSG | TMILLS2 | 2025-02-06 09:57 | 2025-02-06 | 300 | No | 1 | 1 | NC-CONT-ELEC
1446191 | 3-First Opportunity | Scoping Required | Corrective | 0300-GA-362-A-PUMP | GA-362A GYPSUM PRECIPITATION CYCLONE FEED PUMP | Process/Seal Water lines in Gypsum area need replaced | TMILLS2 | 2026-03-02 12:55 | 2026-03-02 | 300 | No | 1 | 1 | NC-CONT-MECH
1439633 |  | Open - Ready to Schedule | Corrective | 0100-DC-101-F-PAD | DC-101F NEUTRALIZATION REACTOR 4' CONCRETE PAD | Replace heat trace at safety shower | LOBO | 2026-01-28 10:28 | 2026-01-28 | 100 | Yes | 1 | 1 | NC-CONT-ELEC
1384000 | 1-Emergency/Break-in | Scoping Required | Corrective | 0200-DC-201-A | 0200-DC-201-A HCL RECOVERY REACTOR | Steam valve 2124 has a steam leak | COSERMO | 2025-05-06 13:41 | 2025-05-06 | 200 | No | 1 | 1 | NC-CONT-MECH
1385263 | 3-First Opportunity | Scoping Required | Corrective | 0200-GA-290-A-PUMP | GA-290-A DEPLETION SETTLER CONTAINMENT PUMP (FE-209) | AOD 1" drain ports to each AOD in the settler train. | COSERMO | 2025-05-14 08:42 | 2025-05-14 | 200 | No | 1 | 1 | NC-CONT-MECH
1410460 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0900-BA-901-FURNACE | BA-901 -ROTARY/RECYCLE FURNACE | Weld channel iron on back side of door support | COSERMO | 2025-08-28 09:49 | 2025-08-28 | 900 | No | 2 | 2 | NC-CONT-MECH
1419422 | 1-Emergency/Break-in | Scoping Required | Corrective | 0400-FB-450-0-TANK | FB-450 ELECTROLYTE STORAGE TANK (364200 GAL) | Tank itself leaking around decant outlet valve on top |  | 2025-10-18 15:34 | 2025-10-18 | 400 | No | 1 | 1 | NC-CONT-MECH
1423680 | 1-Emergency/Break-in | Scoping Required | Corrective | 0400-PA-401-CRANE | KUNZ CRANE #1 | PA-401 Install Temporary Spray Bar. | COSERMO | 2025-11-05 07:28 | 2025-11-05 | 400 | No | 1 | 1 | NC-CONT-MECH
1436791 |  | Awaiting Parts | Corrective | 0600-PX-613 | 0600-PX-613 LEAD PRECIPITATION PRESS FILTER PACKAGE | Modify PX-613 piping to accept Clarkson valve | COSERMO | 2026-01-14 09:40 | 2026-03-23 | 600 | No | 1 | 1 | NC-CONT-MECH
1440972 | 1-Emergency/Break-in | Awaiting Parts | Corrective | 400 | ELECTROWINNING AREA 400 | vac port has hole in line | COSERMO | 2026-02-05 08:29 | 2026-02-05 | 400 | No | 1 | 1 | NC-CONT-MECH
1446072 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-PA-402-CRANE | KUNZ CRANE #2 | Need a tie off on 2nd level of Kunz crane |  | 2026-02-27 08:37 | 2026-02-27 | 400 | No | 1 | 1 | NC-CONT-MECH
1446187 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | Repair electrical cords in the shop (AC-AUD-20260219-003) | AALEXEYEV | 2026-03-02 12:20 | 2026-03-02 | 1100 | Yes | 1 | 3 | NC-E/I
1446188 |  | Scoping Required | Corrective | 0300-GA-362-A-PUMP | GA-362A GYPSUM PRECIPITATION CYCLONE FEED PUMP | GA-362 Seal Water Lines needs heat trace attached and insulated | AALEXEYEV | 2026-03-02 12:24 | 2026-03-02 | 300 | No | 1 | 1 | NC-E/I
1448081 | 1-Emergency/Break-in | Parts Required | Corrective | 200 | SOLVENT EXTRACTION, AREA 200 | SX sampler golf cart wheel bearing and control arm | EQUIPMENT CREW | 2026-03-12 14:45 | 2026-03-12 | 200 | No | 1 | 1 | NC-EQUIPMENT
1446161 | 3-First Opportunity | Open - Ready to Schedule | Corrective | 0300-CL-301 | CL-301 SILICA PRECIPITATION THICKENER | Clarkson valve to GA302B needs replaced (CL-301 Drained) | MECH EXE CREW | 2026-03-02 07:46 | 2026-04-07 | 300 | No | 2 | 2 | NC-MECHANIC EXE
1449857 | 1-Emergency/Break-in | Scoping Required | Corrective | 0600-PX-613-B | 0600-PX-613-B LEAD PRECIPITATION PRESS FILTER PACKAGE | PIT-6263-B recalibration/ possible cleanout | BBROUSE | 2026-03-19 22:27 | 2026-03-19 | 600 | No | 1 | 1 | NC-E/I
1449843 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-EF-404-0-HANDRAIL | EF-404 PERIMETER HANDRAIL | ACT #4 fan level stairs is missing a handrail |  | 2026-03-19 12:56 | 2026-03-19 | 400 | Yes | 1 | 1 | NC-CONT-MECH
1439520 |  | Scoping Required | Corrective | 0100-PX-101-A | 0100-PX-101-A FILTER PRESS | PX-101A Drip tray skins and top of press peeling | TMILLS2 | 2026-01-26 17:53 | 2026-01-26 | 100 | No | 1 | 1 | NC-CONT-MECH
1408794 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-FF-725-BIN | FF-725 -SODIUM SULFIDE CONVEYOR | door latches need to be replaced |  | 2025-08-19 11:30 | 2025-08-19 | 700 | No | 2 | 2 | NC-CONT-MECH
1428323 | 3-First Opportunity | Scoping Required | Corrective | 0300-PX-303-A | 0300-PX-303-A LIQUID EFFLUENT PRESS FILTER PACKAGE | Feed lines for the PX-303 A/B a few welds have slow leaks. |  | 2025-11-30 00:41 | 2025-11-30 | 300 | No | 1 | 1 | NC-CONT-MECH
1428245 | 1-Emergency/Break-in | Awaiting Parts | Corrective | 900 | METAL RECYCLING, AREA 900 | 900 building north side access roll up door is damaged |  | 2025-11-27 17:39 | 2025-11-27 | 900 | Yes | 1 | 1 | NC-CONT-MECH
1428388 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CA-401-INLET | CA-401 Stripping machine Inlet Conveyor | weld coupling on pipe for csm1 inlet hose | COSERMO | 2025-12-02 06:12 | 2025-12-02 | 400 | No | 1 | 1 | NC-CONT-MECH
1428242 | 1-Emergency/Break-in | Scoping Required | Corrective | 0300-PX-303-A | 0300-PX-303-A LIQUID EFFLUENT PRESS FILTER PACKAGE | Roll up door is off the track and won't close | COSERMO | 2025-11-27 15:36 | 2025-11-27 | 300 | No | 1 | 1 | NC-CONT-MECH
1406988 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-GA-422-A-PUMP | ANODE CLEANING HIGH PRESSURE WATER PUMPS (85 GPM @ 2610 PSI) | Relocate recirc valve further upstream | COSERMO | 2025-08-05 08:27 | 2025-08-05 | 400 | No | 2 | 3 | NC-CONT-MECH
1439480 |  | Scoping Required | Corrective | 0300-PX-302-A | PX-302A CEMENTATION SOLUTION PRESS FILTER PACKAGE | Skins are peeling on PX-302A | TMILLS2 | 2026-01-25 16:31 | 2026-01-25 | 300 | No | 1 | 1 | NC-CONT-MECH
1420688 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-PA-401-CRANE | KUNZ CRANE #1 | Rebuild old tow arm bracket the wheels/linear bearings (see attached picture) | BBROUSE | 2025-10-27 11:57 | 2025-10-27 | 400 | No | 1 | 1 | NC-E/I
1423560 |  | Open - Ready to Schedule | Corrective | 0200-EA-208-A | Organic heating system Hot water to organic heat exchanger | Replace threaded pipe on EA-208/209 | COSERMO | 2025-11-03 14:54 | 2025-11-03 | 200 | No | 1 | 1 | NC-CONT-MECH
1423446 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0100-GA-154-A2-0-PUMP | GA-154A2 L/N PRESS FILTER FEED PUMP | Lower seal water lines for GA-154s for easier access to regulators and indicator | COSERMO | 2025-10-31 13:45 | 2025-10-31 | 100 | No | 1 | 1 | NC-CONT-MECH
1433835 | 2-Urgent/Scheduled | Scoping Required | Corrective | 100 | Leaching | Spool fabricated to replace piping that has holes on 700E to FA-700E | COSERMO | 2025-12-29 09:27 | 2025-12-29 | 100 | No | 1 | 1 | NC-CONT-MECH
1433860 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0500-PC-501-0-CONVEYOR | CATHODE BUNDLE CONVEYOR SYSTEM #1 | repair transfer plate pedastool ( twisted ) | COSERMO | 2025-12-29 13:37 | 2025-12-29 | 500 | No | 1 | 1 | NC-CONT-MECH
1435231 | 1-Emergency/Break-in | Scoping Required | Corrective | 0700-PX-721 | 0700-PX-721 ROCKWOOD WAELZ OXIDE Preparation Package | GA-721 A/B seal water piping is leaking | COSERMO | 2026-01-07 11:36 | 2026-01-07 | 600 | No | 1 | 1 | NC-CONT-MECH
1439515 |  | Scoping Required | Corrective | 0200-HEATTRACE-Z1 | AREA 200 HEAT TRACE CONTROL PANEL ZONE 1 | Heat trace on HCL not working | TMILLS2 | 2026-01-26 15:29 | 2026-01-26 | 200 | No | 1 | 1 | NC-CONT-ELEC
1440867 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0400-GB-401-0-PUMP | VACUUM PUMP | GB-401 one of the vacuuming suction line have a hole and we are losing suction | COSERMO | 2026-02-03 13:05 | 2026-02-03 | 400 | No | 1 | 1 | NC-CONT-MECH
1440821 | 1-Emergency/Break-in | Scoping Required | Corrective | 100 | Leaching | Water leak on piping at wox decon building. Needs traced and insulati |  | 2026-02-02 13:40 | 2026-02-02 | 100 | No | 1 | 1 | NC-CONT-MECH
1440798 | 1-Emergency/Break-in | Scoping Required | Corrective | 0500-PX-503-A | CATHODE CHARGING LANE #1 | charging lane 1 conveyor 2 keeps tripping out | AALEXEYEV | 2026-02-02 10:36 | 2026-02-02 | 500 | No | 1 | 1 | NC-CONT-ELEC
1420687 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-FF-721-BIN | FF-721 -ROCKWOOD WAELZ OXIDE STORAGE BIN | ROX silo PLC120 volt to DCS 24 volt | A W | 2025-10-27 11:57 | 2025-10-27 | 700 | No | 1 | 10 | NC-CONT-ELEC
1440792 | 2-Urgent/Scheduled | Scoping Required | Corrective | 100 | Leaching | GA-154's seal water lines and seal pot need insulated and working heat trace. | AALEXEYEV | 2026-02-02 09:44 | 2026-02-02 | 100 | No | 1 | 1 | NC-E/I
1440787 |  | Scoping Required | Corrective | 0200-EW-201-EYEWASH | EW-201 -AREA 200 SAFETY EYEWASH | DC-201 Eye wash at top of tower leaking | TMILLS2 | 2026-02-02 08:16 | 2026-02-02 | 200 | No | 1 | 1 | NC-CONT-MECH
1439396 | 2-Urgent/Scheduled | Parts Required | Corrective | 0900-DP-8 | Dock Plate-8-900 Warehouse Loading Dock South Side | 900 area loading ramp will not raise. |  | 2026-01-23 10:54 | 2026-01-23 | 900 | No | 1 | 1 | NC-CONT-MECH
1420675 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0300-GA-324-B-PUMP | GA-324B METALS POLISHING CLARIFIER MICROSAND RECIRCULATION PUMP [CL-304] | GA-324 B Seal water lines need insulated | TMILLS2 | 2025-10-27 07:52 | 2025-10-27 | 300 | No | 1 | 1 | NC-CONT-MECH
1445001 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CA-402-STACKER | CA-402 Stripping Machine Stacker | eye bolt need install on ceiling on left side | COSERMO | 2026-02-23 15:27 | 2026-02-23 | 400 | No | 1 | 1 | NC-CONT-MECH
1440717 |  | Scoping Required | Corrective | 0700-GA-721-A-PUMP | GA-721A SODA ASH SOLUTION PUMP (170 GPM @ 97' TDH, 30 HP) | GA-721 A & B Need seal water lines insulated. | TMILLS2 | 2026-01-30 10:18 | 2026-01-30 | 600 | No | 1 | 1 | NC-CONT-MECH
1444046 | 1-Emergency/Break-in | Awaiting Parts | Corrective | 900 | METAL RECYCLING, AREA 900 | Replace 900 sifter boot |  | 2026-02-19 09:20 | 2026-02-19 | 900 | No | 1 | 1 | NC-MECHANIC EXE
1408577 | 3-First Opportunity | Scoping Required | Corrective | 0400-GA-409-0-PUMP | GA-409 PUMP (44 GPM @ 85' TDH, 5 HP) | GA-409 Base needs the tiles replaced | LOBO | 2025-08-14 11:47 | 2025-08-14 | 400 | No | 2 | 4 | NC-LCS CONTRACT
1408612 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0200-DC-201-B | 0200-DC-201-B HCL RECOVERY REACTOR | Main steam inlet - Bypass valve broken | COSERMO | 2025-08-15 05:46 | 2025-08-15 | 200 | No | 2 | 2 | NC-CONT-MECH
1408574 | 3-First Opportunity | Scoping Required | Corrective | 0400-GA-405-0-PUMP | GA-405 SPENT ELECTROLYTE RECIRCULATION PUMP #5 (177' TDH @ 3440GPM) | GA-405 Need floor repaired just outside the containment | LOBO | 2025-08-14 11:36 | 2025-08-14 | 400 | No | 2 | 5 | NC-LCS CONTRACT
1417680 | 3-First Opportunity | Scoping Required | Corrective | PE-4101603-PE1 | PE TO CELL FEED TANK NO.2 | (Outage) Launder pipe to cell feed tank on the east side leaking |  | 2025-10-07 15:59 | 2025-10-07 | 400 | No | 1 | 1 | NC-CONT-MECH
1420616 |  | Scoping Required | Corrective | 0700-PX-721 | 0700-PX-721 ROCKWOOD WAELZ OXIDE Preparation Package | Install stilling well in px-721 tank for level xmtr. (See Art for details) | AALEXEYEV | 2025-10-24 13:55 | 2025-10-24 | 600 | No | 1 | 1 | NC-E/I
1435205 |  | Parts Required | Corrective | 0100-GA-110-A-MOTOR | GA-110A WOX FEED PREPARATION SUMP PUMP MOTOR (650 GPM @ 61' TDH, 20 HP) | Run dedicated circuit for vibration sensor AP at GA-110s | MECH EXE CREW | 2026-01-06 16:59 | 2026-01-06 | 100 | No | 2 | 3 | NC-E/I
1439373 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0300-DC-308-D-REACTOR | DC-308D GYPSUM PRECIPITATION REACTORS | DC-308D to GA-362 suction Y pipe needs replaced see comments | COSERMO | 2026-01-22 18:26 | 2026-01-22 | 300 | No | 1 | 1 | NC-CONT-MECH
1443933 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0800-PX-806-D | 0800-PX-806-D COMPRESSOR NO. 4 | PX-806D tripping breaker | BBROUSE | 2026-02-17 13:49 | 2026-02-17 | 800 | No | 1 | 1 | NC-E/I
1435176 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0900-PX-902 | PX-902 -CHARGER TILTING FOR RECYCLE FURNACE | INSTALL BALLARDS AROUND BURNER |  | 2026-01-06 10:34 | 2026-01-06 | 900 | No | 1 | 1 | NC-CONT-MECH
1435162 | 2-Urgent/Scheduled | Parts Required | Corrective | 0900-BA-901-FURNACE | BA-901 -ROTARY/RECYCLE FURNACE | Replacehydraulic heat exchanger |  | 2026-01-06 08:20 | 2026-01-06 | 900 | No | 1 | 1 | NC-MECHANIC
1443947 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-GK-700-0-CTRL | GK-700 WOX SILO BUILDING DUST COLLECTOR DISCHARGE ROTARY VALVE (1 HP) | the handles on the load cell covers off the PC-701 are broke | AALEXEYEV | 2026-02-17 22:33 | 2026-02-17 | 700 | No | 1 | 1 | NC-E/I
1442061 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 1000-RC-RAIL | AREA 1000 RAILYARD EQUIPMENT | Rail Yard electrical conduit AC-AUD-20260206-005 | AALEXEYEV | 2026-02-09 08:50 | 2026-04-08 | 1000 | Yes | 1 | 1 | NC-E/I
1443929 | 2-Urgent/Scheduled | Awaiting Parts | Corrective | 2100 | Maintenance shop Tools and Equipment | Yellow cabinet in lower shop needs replaced. | LOWER PM CREW | 2026-02-17 11:09 | 2026-02-17 | 2100 | No | 1 | 2 | NC-PM DAY
1444004 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0700-PX-703 | 0700-PX-703 MILK OF LIME PREPARATION PACKAGE | Process Water Line Feeding PX-703 Boot Wash Leaking Under Insulation | TMILLS2 | 2026-02-18 12:50 | 2026-02-18 | 300 | No | 1 | 1 | NC-CONT-MECH
1434956 | 3-First Opportunity | Scoping Required | Corrective | 700 | WOX UNLOADING, SLURRYING AREA 700 | GA-721A piping needs modified to allow a pressure gauge to be installed | COSERMO | 2026-01-03 10:04 | 2026-01-03 | 700 | No | 1 | 1 | NC-CONT-MECH
1434957 | 3-First Opportunity | Scoping Required | Corrective | 700 | WOX UNLOADING, SLURRYING AREA 700 | GA-721B discharge piping needs modfied so a pressure gauge can be installed. | COSERMO | 2026-01-03 10:05 | 2026-01-03 | 700 | No | 1 | 1 | NC-CONT-MECH
1443901 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | Machine on indicator light missing on top of brush elev | BBROUSE | 2026-02-17 10:15 | 2026-02-17 | 400 | No | 1 | 1 | NC-E/I
1443902 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | machine on indicator light missing on top of brush elev | BBROUSE | 2026-02-17 10:16 | 2026-02-17 | 400 | No | 1 | 1 | NC-E/I
1430745 |  | Scoping Required | Corrective | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | install automatic door openers on maintenance shop bay doors |  | 2025-12-12 07:21 | 2025-12-12 | 1100 | No | 1 | 1 | NC-CONT-MECH
1435026 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 200 | SOLVENT EXTRACTION, AREA 200 | Install seal water orifice to 200/300 goulds pumps (On Going) |  | 2026-01-05 12:37 | 2026-01-05 | 200 | No | 1 | 1 | NC-MECHANIC
1417495 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0200-DC-201-B | 0200-DC-201-B HCL RECOVERY REACTOR | TV-2125 steam supply valve needs replaced, leaking by | COSERMO | 2025-10-04 15:01 | 2025-10-04 | 200 | No | 1 | 1 | NC-CONT-MECH
1443772 |  | Scoping Required | Corrective | 0200-TV-2814-B | EA-209B TEMPERATURE STEAM VALVE | EA-209 Need tream lines insulated |  | 2026-02-13 13:31 | 2026-02-13 | 200 | No | 1 | 1 | NC-CONT-MECH
1443771 |  | Scoping Required | Corrective | 0200-TV-2814-A | EA-209A TEMPERATURE STEAM VALVE | EA-208 Need sraem lines insulated |  | 2026-02-13 13:30 | 2026-02-13 | 200 | No | 1 | 1 | NC-CONT-MECH
1443775 |  | Scoping Required | Corrective | 0300-EA-301 | EA-301 FILTERED CEMENTED SOLUTION HEAT EXCHANGER | EA-301 Need steam lines insulated |  | 2026-02-13 13:35 | 2026-02-13 | 300 | No | 1 | 1 | NC-CONT-MECH
1424642 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0400-PA-402-CRANE | KUNZ CRANE #2 | A&W to install new energy chain on Kunz crane 2 | AALEXEYEV | 2025-11-13 08:44 | 2026-04-07 | 400 | No | 1 | 1 | NC-CONT-ELEC
1429495 | 1-Emergency/Break-in | Awaiting Parts | Corrective | 0300-PX-301-A | PX-301A GYPSUM BELT FILTER PACKAGE | The PX301A feed line is leaking and needs spool replaced | COSERMO | 2025-12-05 09:46 | 2025-12-05 | 300 | No | 1 | 1 | NC-CONT-MECH
1436411 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0400-GA-422-A-PUMP | ANODE CLEANING HIGH PRESSURE WATER PUMPS (85 GPM @ 2610 PSI) | GA-422 replace bad oiler on spare assembly |  | 2026-01-13 06:26 | 2026-03-24 | 400 | No | 1 | 1 | NC-REBUILD
1441973 | 3-First Opportunity | Open - Ready to Schedule | Corrective | 0300-GA-323-MOTOR | GA-323 METAL POLISHING PRESS FILTER CORE BLOW COLLECTION TANK PUMP MOTOR PX-303 | Change GA-323 over to AOD | TMILLS2 | 2026-02-06 15:30 | 2026-04-03 | 300 | No | 1 | 1 | NC-E/I
1441994 |  | Scoping Required | Corrective | 0300-PC-311 | 0300-PC-311 SCREENED OXIDIC FINES FEED CONVEYOR | Add e-stop and jog switch to PC-311 | AALEXEYEV | 2026-02-07 09:24 | 2026-02-07 | 300 | No | 1 | 1 | NC-E/I
1441993 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0100-PX-101-B | 0100-PX-101-B FILTER PRESS | Conduit needs repaired and secured this is where the drops come out on the pad | BBROUSE | 2026-02-07 09:15 | 2026-02-07 | 100 | No | 1 | 1 | NC-E/I
1447565 | 2-Urgent/Scheduled | Scoping Required | Corrective | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | Repair power cord for swamp cooler | AALEXEYEV | 2026-03-11 14:23 | 2026-03-11 | 1100 | No | 1 | 1 | NC-E/I
1447577 | 2-Urgent/Scheduled | Scoping Required | Corrective | 0500-PB-502-ELEVATOR | PB-502 -CATHODE BUNDLE FEEDING SYSTEM #2 ELEVATOR | lane 2 elevator motor needs brake with handle swapped | BBROUSE | 2026-03-11 16:49 | 2026-03-11 | 500 | Yes | 1 | 1 | NC-E/I
1447545 | 3-First Opportunity | Scoping Required | Corrective | 0100-UV-1804-0-CTRL | SLURRY FEED FROM FB-111 TO PX-101-A/B | U-1804 is leaking by | AALEXEYEV | 2026-03-11 09:38 | 2026-03-11 | 100 | No | 1 | 1 | NC-E/I
1447546 | 3-First Opportunity | Scoping Required | Corrective | 0100-UV-1811-B-CTRL | PX-101B L/N PRESS FILTER FEED VALVE UV-1811B | U-1811-B is leaking by / came off closed limit with pressure built up | AALEXEYEV | 2026-03-11 09:41 | 2026-03-11 | 100 | No | 1 | 1 | NC-E/I
1447543 | 2-Urgent/Scheduled | Open - Ready to Schedule | Corrective | 0200-FD-202-F-FILTER | FD-202F LOADED ELECTROLYTE FILTER (NORMAL 463.9 / MAX 1553.6 GPM, 39 C, 0) | Repair FD-202 F coating (Blastco) | TMILLS2 | 2026-03-11 09:35 | 2026-03-23 | 200 | No | 1 | 1 | NC-CONT-MECH
1447374 | 1-Emergency/Break-in | Open - Ready to Schedule | Corrective | 0200-EA-203-A | 0200-EA-203-A HCL HEATER | EA-203A valve replacement | BPETERS2 | 2026-03-08 17:21 | 2026-03-08 | 200 | No | 1 | 1 | NC-MECHANIC EXE
1447297 | 2-Urgent/Scheduled | Scoping Required | Corrective | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | Repair gutters on the South side of the boiler room (HA-20260306-002) |  | 2026-03-06 13:18 | 2026-03-06 | 1100 | Yes | 1 | 1 | NC-CONT-MECH
1447506 | 2-Urgent/Scheduled | Awaiting Parts | Corrective | 500 | MELTING / CASTING, AREA 500 | Move camera in lower parts cage | AALEXEYEV | 2026-03-10 14:11 | 2026-03-10 | 500 | No | 1 | 4 | NC-E/I
1447507 | 2-Urgent/Scheduled | Parts Required | Corrective | 0400-CA-401-ROLLTABLE | CA-401 Stripping Machine Roller Table | build drive roller |  | 2026-03-10 14:15 | 2026-03-10 | 400 | No | 1 | 1 | NC-MECHANIC EXE
1447453 | 3-First Opportunity | Awaiting Parts | Corrective | 0400-PA-401-0-MCS | KUNZ CRANE #1 MAIN CONTROL STATION | Kunz 1&2 prevent from traveling over CSM while CSM is locked | BBROUSE | 2026-03-09 15:36 | 2026-03-09 | 400 | No | 1 | 1 | NC-E/I
1449374 | 1-Emergency/Break-in | Open - Ready to Schedule | Corrective | 0500-CA-505 | CGG / SHG JUMBO INGOT MOLDS | Mold #5 has a water leak coming from around the pin. | COSERMO | 2026-03-18 17:54 | 2026-03-18 | 500 | No | 1 | 1 | NC-CONT-MECH
1447309 |  | Scoping Required | Corrective | 0300-GA-341-0-PUMP | GA-341 METALS POLISHING COLLECTION TANK PUMP | GA-341- HEAT TRACE NEEDS SCOPING | AALEXEYEV | 2026-03-06 15:00 | 2026-03-06 | 300 | No | 1 | 1 | NC-E/I
1444992 | 3-First Opportunity | Scoping Required | Follow-up | 0600-PX-613-B | 0600-PX-613-B LEAD PRECIPITATION PRESS FILTER PACKAGE | Drip tray skins are peeling on PX-613B | TMILLS2 | 2026-02-23 14:05 | 2026-02-23 | 600 | No | 1 | 1 | NC-CONT-MECH
1448462 |  | Scoping Required | Follow-up | 0700-PX-703 | 0700-PX-703 MILK OF LIME PREPARATION PACKAGE | PX-703 repair/ re-route wires in control panel | AALEXEYEV | 2026-03-16 18:30 | 2026-03-16 | 300 | No | 1 | 1 | NC-E/I
1450128 |  | Scoping Required | Follow-up | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | Install quick connect plugs on all 4 rotary valves | BBROUSE | 2026-03-21 09:07 | 2026-03-21 | 500 | No | 1 | 1 | NC-E/I
1450235 | 3-First Opportunity | Scoping Required | Follow-up | 0100-PC-101-A-CONVEYOR | PC-101A L/N RESIDUE BELT CONVEYOR TO DIKE (15 HP) | PC101A tail pulley cage is deteriorating | TMILLS2 | 2026-03-24 00:56 | 2026-03-24 | 100 | No | 1 | 1 | NC-MECHANIC EXE
1450236 | 2-Urgent/Scheduled | Scoping Required | Follow-up | 0100-PC-101-A-CONVEYOR | PC-101A L/N RESIDUE BELT CONVEYOR TO DIKE (15 HP) | PC101A 13th v-roller from the south needs replaced | TMILLS2 | 2026-03-24 00:58 | 2026-03-24 | 100 | No | 1 | 1 | NC-MECHANIC EXE
1450231 |  | Scoping Required | Follow-up | 0300-PX-303-B | 0300-PX-303-B LIQUID EFFLUENT PRESS FILTER PACKAGE | PX-303B drip trays wont close at 500 PSI needs inspected | TMILLS2 | 2026-03-23 18:10 | 2026-03-23 | 300 | No | 1 | 1 | NC-EQUIPMENT
1445038 |  | Scoping Required | Follow-up | 0400-CA-401-0-HPU | ROW#1 MACHINE HYDRAULIC UNIT | Need a platform made for V knife and elevator work on CSM machines | COSERMO | 2026-02-24 14:03 | 2026-02-24 | 400 | Yes | 1 | 1 | NC-CONT-MECH
1389990 | 2-Urgent/Scheduled | Scoping Required | Follow-up | 0300-GA-398-0-PUMP | GA-398 GYPSUM PAD TRUCK TIRE WASH SUMP PUMP | Seal water supply line come apart at pro press in pipe rack. | COSERMO | 2025-05-31 22:25 | 2025-05-31 | 300 | No | 1 | 1 | NC-CONT-MECH
1450198 |  | Scoping Required | Follow-up | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | Small gearbox has seal leak CA-501 |  | 2026-03-23 08:25 | 2026-03-23 | 500 | No | 1 | 1 | NC-MECHANIC EXE
1450232 |  | Scoping Required | Follow-up | 0300-PX-303-B | 0300-PX-303-B LIQUID EFFLUENT PRESS FILTER PACKAGE | Hydraulic cooling fan needs changed PX-303B (see comments) | TMILLS2 | 2026-03-23 18:11 | 2026-03-23 | 300 | No | 1 | 1 | NC-MECHANIC EXE
1387835 |  | Scoping Required | Follow-up | 0300-PX-303-A | 0300-PX-303-A LIQUID EFFLUENT PRESS FILTER PACKAGE | Coating is coming off of outer edge of drip tray doors | TMILLS2 | 2025-05-21 07:54 | 2025-05-21 | 300 | No | 1 | 1 | NC-CONT-MECH
1426213 | 2-Urgent/Scheduled | Awaiting Parts | Follow-up | 0300-GD-306-A-GEARBOX | GD-306A CEMENTATION AGITATOR GEARBOX (10 HP) | Rebuild GD-306 | TMILLS2 | 2025-11-18 09:39 | 2025-11-18 | 300 | No | 1 | 1 | NC-REBUILD
1444921 | 2-Urgent/Scheduled | Parts Required | Follow-up | 0700-GA-700-F-PUMP | WOX SLURRY PREPARATION TANK PUMP GA-700F | Rebuild 700 pump gearbox | REBUILD CREW | 2026-02-21 06:47 | 2026-02-21 | 700 | No | 1 | 1 | NC-MECHANIC
1428378 |  | Scoping Required | Follow-up | 0300-PX-302-B | PX-302B CEMENTATION SOLUTION PRESS FILTER PACKAGE | PX-302B drip tray skins are peeling |  | 2025-12-01 17:50 | 2025-12-01 | 300 | No | 1 | 1 | NC-LCS CONTRACT
1443755 | 2-Urgent/Scheduled | Scoping Required | Follow-up | 0100-GA-120-A-PUMP | GA-120-A EAST STORM POND PUMP | GA-120A Needs Insulation Replaced on Seal Water Line at Pump | MECH EXE CREW | 2026-02-13 10:59 | 2026-02-13 | 100 | No | 1 | 1 | NC-CONT-MECH
1443757 | 2-Urgent/Scheduled | Scoping Required | Follow-up | 0300-GA-315-A-PUMP | GA-315A ZINC PRECIPITATION THICKENER OVERFLOW PUMP FOR CL-303 | Process Water Drop Outside Containment Near GA-315's is Broken | TMILLS2 | 2026-02-13 11:01 | 2026-02-13 | 300 | No | 1 | 1 | NC-CONT-MECH
1443763 | 2-Urgent/Scheduled | Scoping Required | Follow-up | 1000 | RAILYARD, CO-PRODUCT/RAW MATERIAL/REAGENT HANDLING AND STORAGE | Safety Shower Piping in Acid Unloading needs Insulation Repaired |  | 2026-02-13 11:11 | 2026-02-13 | 1000 | No | 1 | 1 | NC-CONT-MECH
1449856 | 2-Urgent/Scheduled | Scoping Required | Follow-up | 0700-PA-3000 | WOX RAILCAR UNLOADING | Stop needs fabricated for track 11 door |  | 2026-03-19 16:23 | 2026-03-19 | 700 | No | 1 | 1 | NC-MECHANIC EXE
1419362 |  | Scoping Required | Follow-up | 0100-GA-154 P-PUMP | GA-154 P -GA-154 SEAL WATER PUMP | Insulation on GA-154 booster pump needs replaced | MECH EXE CREW | 2025-10-17 09:29 | 2025-10-17 | 100 | No | 1 | 1 | NC-CONT-MECH
1433815 |  | Scoping Required | Follow-up | 0200-PX-201 | 0200-PX-201 CRUD TREATMENT PRESS FILTER PACKAGE | Skins peeling in multiple spots on PX-201 drip trays | TMILLS2 | 2025-12-28 16:51 | 2025-12-28 | 200 | No | 1 | 1 | NC-CONT-MECH
1436435 |  | Scoping Required | Follow-up | 0300-PX-303-B | 0300-PX-303-B LIQUID EFFLUENT PRESS FILTER PACKAGE | PX-303B drip tray door skins peeling | TMILLS2 | 2026-01-13 14:11 | 2026-01-13 | 300 | No | 1 | 1 | NC-CONT-MECH
1430923 |  | Scoping Required | Follow-up | 0300-GA-321-B-PUMP | GA-321-B-GYPSUM PRECIPITATION CYCLONE UNDERFLOW SEED RECYCLE PUMP | insulation needs installed on GA-321B seal water lines | LOBO | 2025-12-16 13:50 | 2025-12-16 | 300 | No | 1 | 1 | NC-CONT-MECH
1448423 | 2-Urgent/Scheduled | Scoping Required | Process Improvement | 0900-PX-931 | 900-00230 | Install Broken Bag Detector on PX-931 | A W | 2026-03-16 09:10 | 2026-03-16 | 900 | No | 1 | 1 | NC-CONT-ELEC
1448424 | 2-Urgent/Scheduled | Scoping Required | Process Improvement | 0700-BH-730 | BH-730 WOX UNLOADING BAGHOUSE | Complete wiring of BH-730 Baghouse Instrumentation | A W | 2026-03-16 09:12 | 2026-03-16 | 700 | No | 1 | 1 | NC-CONT-ELEC
1407000 | 2-Urgent/Scheduled | Scoping Required | Follow-up | 0300-GA-322-A-PUMP | GA-322-A DILUTE SULFURIC ACID MAKEUP DAY TANK PUMP | Pump base is destroyed, pump needs replaced | LOBO | 2025-08-05 12:11 | 2025-08-05 | 300 | No | 1 | 2 | NC-LCS CONTRACT
1447455 |  | Scoping Required | Follow-up | 0200-FT-2065B | Cooling Water To HCl Subcooler EA-202.1B | Need to replace electronics on FT-2065B | AALEXEYEV | 2026-03-09 17:29 | 2026-03-09 | 200 | No | 1 | 1 | NC-E/I
1386329 | 3-First Opportunity | Scoping Required | Process Improvement | 0400-PA-403-CRANE | PA-403 -AUXILIARY CRANE #1 | bring comms to mnt crane PA-403 (see Tremayne) | AALEXEYEV | 2025-05-16 15:51 | 2025-05-16 | 400 | No | 1 | 1 | NC-E/I
1386330 | 3-First Opportunity | Scoping Required | Process Improvement | 0400-PA-404-CRANE | PA-404 -AUXILIARY CRANE #2 | bring comms to mnt crane PA-404 (See Tremayne) | AALEXEYEV | 2025-05-16 15:52 | 2025-05-16 | 400 | No | 1 | 1 | NC-E/I
1329745 | 3-First Opportunity | Scoping Required | Process Improvement | 0400-GA-414-0-PUMP | PUMP (66 GPM @ 70' TDH) | hang spools 2x1-10 | COSERMO | 2024-07-24 14:53 | 2024-07-24 | 400 | No | 2 | 2 | NC-CONT-MECH
1356883 | 2-Urgent/Scheduled | Scoping Required | Process Improvement | 0400-GV-402-FAN | GV-402 -ACT-2 FAN | fabricate and install vent for motor and gear reducer | COSERMO | 2024-12-19 12:46 | 2024-12-19 | 400 | No | 2 | 10 | NC-CONT-MECH
1436842 | 3-First Opportunity | Scoping Required | Process Improvement | 0400-CA-401-0-HPU | ROW#1 MACHINE HYDRAULIC UNIT | install pressure transduce CSM 1 hydraulic pumps | AALEXEYEV | 2026-01-15 09:44 | 2026-01-15 | 400 | No | 1 | 1 | NC-E/I
1436843 | 3-First Opportunity | Scoping Required | Process Improvement | 0400-CA-402-0-HPU | ROW#2 MACHINE HYDRAULIC UNIT | install pressure transduce CSM 2 hydraulic pumps | AALEXEYEV | 2026-01-15 09:45 | 2026-01-15 | 400 | No | 1 | 1 | NC-E/I
1397270 | 2-Urgent/Scheduled | Scoping Required | Process Improvement | 500 | MELTING / CASTING, AREA 500 | build platform to set on stacker outlet conveyor | COSERMO | 2025-07-01 14:46 | 2025-07-01 | 500 | No | 2 | 2 | NC-CONT-MECH
1408050 | 3-First Opportunity | Scoping Required | Process Improvement | 0400-EJ-403-0-EXCHANGER | RECTIFIER 1 HEAT EXCHANGER | Move hx to outside of cubical east side | COSERMO | 2025-08-13 13:29 | 2025-08-13 | 400 | No | 2 | 8 | NC-CONT-MECH
1408051 | 3-First Opportunity | Scoping Required | Process Improvement | 0400-EJ-404-0-EXCHANGER | RECTIFIER 2 HEAT EXCHANGER | Move hx to outside of cubical east side | COSERMO | 2025-08-13 13:31 | 2025-08-13 | 400 | No | 2 | 8 | NC-CONT-MECH
1442969 | 3-First Opportunity | Awaiting Parts | Process Improvement | 1300 | ANALYTICAL SERVICES, LABORITORY | Attach UPS outlet panel to wall | AALEXEYEV | 2026-02-11 12:03 | 2026-02-11 | 800 | No | 1 | 1 | NC-E/I
1329751 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0300-GA-313-A-PUMP | GA-313A GYPSUM BELT FILTER WASH NO. 2 PUMP FOR PX-301A | hang spools 1x1.5-8 GA-313-A and B | COSERMO | 2024-07-24 15:02 | 2024-07-24 | 300 | No | 2 | 3 | NC-CONT-MECH
1388696 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0500-CA-505 | CGG / SHG JUMBO INGOT MOLDS | Add Limits Switches to Jumbo's (D3E) | AALEXEYEV | 2025-05-27 06:41 | 2026-03-27 | 500 | No | 2 | 3 | NC-E/I
1329753 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0200-GA-207-0-PUMP | GA-207 BACKWASHING TO DEPLETION AFTER SETTLER PUMP (35 GPM @ 33' TDH, 1 HP) | hang spools 1.5x3-6 GA-207 | COSERMO | 2024-07-24 15:04 | 2024-07-24 | 200 | No | 2 | 2 | NC-CONT-MECH
1365508 |  | Open - Ready to Schedule | Planned Work | 0300-GA-362-B-PUMP | 0300-GA-362-B-GYPSUM PRECIPITATION CYCLONE FEED PUMP | GA-362 B Need a regulator installed | COSERMO | 2025-02-05 13:03 | 2025-02-05 | 300 | No | 2 | 2 | NC-CONT-MECH
1365505 |  | Open - Ready to Schedule | Planned Work | 0300-GA-325-A-PUMP | GA-325A ZINC PRECIPITATION UNDERFLOW & SEED RECYCLE PUMP | GA-325 A/B Need a regulator installed | COSERMO | 2025-02-05 13:00 | 2025-02-05 | 300 | No | 2 | 2 | NC-CONT-MECH
1203931 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 400 | ELECTROWINNING AREA 400 | Fabricate Support beams under both CSMs grating | COSERMO | 2023-05-05 17:56 | 2023-05-05 | 400 | No | 1 | 1 | NC-CONT-MECH
1339793 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0500-BA-501-0-SHELL | BA-501 STEEL FURNACE SHELL | Repair flared chute on charging lane 2 | COSERMO | 2024-09-18 08:58 | 2025-12-31 | 500 | No | 2 | 4 | NC-CONT-MECH
1365504 |  | Open - Ready to Schedule | Planned Work | 0300-GA-320-A-PUMP | GA-320-A GYPSUM PRECIPITATION CYCLONE UNDERFLOW ADVANCE PUMP | GA-320 A/B Need regulator installed | COSERMO | 2025-02-05 12:59 | 2025-02-05 | 300 | No | 2 | 2 | NC-CONT-MECH
1365510 |  | Open - Ready to Schedule | Planned Work | 0300-GA-341-0-PUMP | GA-341 METALS POLISHING COLLECTION TANK PUMP | GA-341 Need a regulator installed | COSERMO | 2025-02-05 13:06 | 2025-02-05 | 300 | No | 2 | 2 | NC-CONT-MECH
1365511 |  | Open - Ready to Schedule | Planned Work | 0300-GA-324-A-PUMP | GA-324A METALS POLISHING CLARIFIER MICROSAND RECIRCULATION PUMP [CL-304] | GA-324 A/B Need regulator installed | COSERMO | 2025-02-05 13:07 | 2025-02-05 | 300 | No | 2 | 2 | NC-CONT-MECH
1400337 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-402-VKNIFE | CA-402 Stripping Machine Vertical Knife | Hard pipe counter balance vale in on second level | COSERMO | 2025-07-14 11:08 | 2025-07-14 | 400 | No | 2 | 6 | NC-CONT-MECH
1387434 |  | Open - Ready to Schedule | Planned Work | 0700-BH-701-D | WOX SILO BIN D VENT (1039 FT2 FILTER AREA, 0) | (HOLD) Install WH PN 700-26440 on WOX silo D | AALEXEYEV | 2025-05-20 13:25 | 2025-05-20 | 700 | No | 1 | 1 | NC-E/I
1349536 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0700-PX-781 C | PX-781 C -SILICA PRECIPITATION THICKENER FLOCCULANT PREP PACKAGE | Discharge to CL-301 needs heat trace repaired | LOBO | 2024-11-12 13:15 | 2024-11-12 | 300 | No | 1 | 2 | NC-LCS CONTRACT
1346932 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0400-GA-431-PUMP | KUNZ CRANE #1 WATER SYSTEM PUMP | KUNZ WATER PUMP REBUILD | REBUILD CREW | 2024-10-24 13:42 | 2024-10-24 | 400 | No | 2 | 10 | NC-REBUILD
1400450 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0500-PX-503-A | CATHODE CHARGING LANE #1 | Add load monitors for elevator and conveyors Charging Lane 1 | AALEXEYEV | 2025-07-16 13:54 | 2026-04-07 | 500 | No | 1 | 3 | NC-E/I
1400449 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0300-GA-308-A-PUMP | GA-308A METALS POLISHING FILTER FEED PUMP (75 HP) FOR PX-303 | Replace discharge valve for GA-308-A to PX-303-A | COSERMO | 2025-07-16 13:54 | 2025-07-16 | 300 | No | 2 | 2 | NC-CONT-MECH
1400451 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0300-GA-308-B-PUMP | GA-308B METALS POLISHING FILTER FEED PUMP (75 HP) FOR PX-303 | Replace discharge valve for GA-308-B to PX-303-B | COSERMO | 2025-07-16 13:55 | 2025-07-16 | 300 | No | 2 | 2 | NC-CONT-MECH
1400453 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0300-GA-308-A-PUMP | GA-308A METALS POLISHING FILTER FEED PUMP (75 HP) FOR PX-303 | Replace Discharge valve for GA-308-C to PX-303-A | COSERMO | 2025-07-16 13:56 | 2025-07-16 | 300 | No | 2 | 2 | NC-CONT-MECH
1400454 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0300-GA-308-C-PUMP | GA-308C METALS POLISHING FILTER FEED PUMP (75 HP) FOR PX-303 | Replace Discharge valve for GA-308-C to PX-303-B | COSERMO | 2025-07-16 13:56 | 2025-07-16 | 300 | No | 2 | 2 | NC-CONT-MECH
1426326 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 200 | SOLVENT EXTRACTION, AREA 200 | Green buggy #1 wont start see comments (Hicham) | EQUIPMENT CREW | 2025-11-19 15:55 | 2026-02-12 | 200 | No | 2 | 3 | NC-MECHANIC
1367315 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 0700-PX-703 | 0700-PX-703 MILK OF LIME PREPARATION PACKAGE | PX-703 mix tank process water line needs the insulation repaired | LOBO | 2025-02-19 04:36 | 2025-02-19 | 300 | No | 1 | 2 | NC-LCS CONTRACT
1426292 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0700-GA-795-0-PUMP | GA-795 SULFURIC ACID STORAGE SUMP PUMP | Use standard sump level transmitter mount to remount LT on GA-795 | AALEXEYEV | 2025-11-19 10:15 | 2026-04-03 | 700 | No | 1 | 1 | NC-E/I
1372034 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 400 | ELECTROWINNING AREA 400 | Water lines to Safety showers in middle of EW basement is leaking. | COSERMO | 2025-03-12 12:15 | 2026-01-26 | 400 | Yes | 2 | 3 | NC-CONT-MECH
1352570 | 3-First Opportunity | Scoping Required | Planned Work | 0200-PL-0202-ASSM-FE-202 | FE-202 2ND EXTRACTION SETTLER | INSPECTION COVER organic weir is broken, restricting flow, see comments | COSERMO | 2024-11-25 12:30 | 2024-11-25 | 200 | No | 2 | 3 | NC-CONT-MECH
1356147 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0400-GA-450-A-PUMP | GA-450 LOADED ELECTROLYTE PUMP (1560 GPM @ 80' TDH, 60 HP) | Run fresh water to GA-450 for seal flush | COSERMO | 2024-12-16 13:20 | 2024-12-16 | 400 | No | 1 | 1 | NC-CONT-MECH
1386394 |  | Open - Ready to Schedule | Planned Work | 0400-GA-401-0-PUMP | GA-401 SPENT ELECTROLYTE RECIRCULATION PUMP #1 (177' TDH @ 3440GPM) | Pull GA-401 for new base installation | COSERMO | 2025-05-18 12:24 | 2025-05-18 | 400 | No | 1 | 1 | NC-CONT-MECH
1386396 |  | Open - Ready to Schedule | Planned Work | 0400-GA-401-0-PUMP | GA-401 SPENT ELECTROLYTE RECIRCULATION PUMP #1 (177' TDH @ 3440GPM) | Demo GA-401 pump base and remove grout | COSERMO | 2025-05-18 12:26 | 2025-05-18 | 400 | No | 1 | 1 | NC-CONT-MECH
1386398 |  | Open - Ready to Schedule | Planned Work | 0400-GA-401-0-PUMP | GA-401 SPENT ELECTROLYTE RECIRCULATION PUMP #1 (177' TDH @ 3440GPM) | Install and level new pump base | COSERMO | 2025-05-18 12:28 | 2025-05-18 | 400 | No | 1 | 1 | NC-CONT-MECH
1386399 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-401-0-PUMP | GA-401 SPENT ELECTROLYTE RECIRCULATION PUMP #1 (177' TDH @ 3440GPM) | Install new GA-401 on new pump base | COSERMO | 2025-05-18 12:31 | 2025-05-18 | 400 | No | 2 | 4 | NC-CONT-MECH
1361610 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FE-209-0-SETTLER | FE-209 DEPLETION SETTLER | Crossover between mixer and settler leaking | COSERMO | 2025-01-09 12:56 | 2025-01-09 | 200 | No | 1 | 1 | NC-CONT-MECH
1367316 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 0700-GA-733-0-PUMP | GA-733 CALCIUM HYDROXIDE TRANSFER PUMP (150 GPM @ 133' TDH, 30 HP) | GA-733 process water flush line needs to be insulated | LOBO | 2025-02-19 04:39 | 2025-02-19 | 300 | No | 1 | 2 | NC-LCS CONTRACT
1386401 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-401-0-PUMP | GA-401 SPENT ELECTROLYTE RECIRCULATION PUMP #1 (177' TDH @ 3440GPM) | (HOLD) Align GA-401 after installation on new pump base | MECH EXE CREW | 2025-05-18 12:32 | 2025-05-18 | 400 | No | 2 | 3 | NC-MECHANIC
1424525 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-PA-402-CRANE | KUNZ CRANE #2 | Repair new energy chain for Kunz 2 in north white tent. (Terry/A&W) |  | 2025-11-11 12:48 | 2026-03-19 | 400 | No | 2 | 5 | NC-E/I
1386408 | 3-First Opportunity | Scoping Required | Planned Work | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | Install gauge bank for slab line cylinders | MECH EXE CREW | 2025-05-18 17:25 | 2025-05-18 | 500 | No | 2 | 3 | NC-MECHANIC
1437521 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | Install jbox and conduit for CSM 2 laser test project | AALEXEYEV | 2026-01-17 12:36 | 2026-03-16 | 400 | No | 2 | 2 | NC-E/I
1445040 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | Repair the 6 slab line heater hoods use job plan (Terry/A&W) | AALEXEYEV | 2026-02-24 14:18 | 2026-02-24 | 500 | No | 1 | 10 | NC-E/I
1445064 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0400-CA-402-BELTCONV | CA-402 Stripping Machine Belt Conveyor | install bearing grease sheilds (Nights) | LOWER PM CREW | 2026-02-25 08:31 | 2026-03-03 | 400 | No | 2 | 2 | NC-PM DAY
1444984 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0100-GA-136-A-PUMP | GA-136-A WASHED WOX SLURRY PREPARATION SUMP PUMP | address quick connect conduit issues both GA-136 pumps | MECH EXE CREW | 2026-02-23 12:50 | 2026-03-18 | 100 | No | 2 | 2 | NC-E/I
1437615 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-PA-401-0-HOIST | KUNZ CRANE #1 HOIST (14 T) | ribs missing on cable tray causing cables to dangle (Night)s | BBROUSE | 2026-01-19 13:03 | 2026-03-25 | 400 | No | 2 | 4 | NC-E/I
1363330 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | Remove Unistrut and install clamp rails for all hydraulic tubing CSM1&2 | COSERMO | 2025-01-20 12:58 | 2025-01-20 | 400 | No | 2 | 8 | NC-CONT-MECH
1359066 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 1000 | RAILYARD, CO-PRODUCT/RAW MATERIAL/REAGENT HANDLING AND STORAGE | Sulfuric Acid Containment in the Railyard Needs Repair | LOBO | 2024-12-31 12:53 | 2024-12-31 | 1000 | No | 1 | 1 | NC-LCS CONTRACT
1386258 |  | Open - Ready to Schedule | Planned Work | 0300-GA-314-A-PUMP | GA-314A ZINC PRECIPITATION THICKENER UNDERFLOW TANK PUMP FOR CL-303 | Repair concrete around pump base | LOBO | 2025-05-15 14:49 | 2025-05-15 | 300 | No | 1 | 1 | NC-LCS CONTRACT
1434868 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-GA-102-B-PUMP | GA-102B L/N THICKENER UNDERFLOW PUMP (780 GPM @ 64' TDH, 50 HP) | Motor needs peckerhead installed and returned to stock. | REBUILD CREW | 2025-12-31 14:07 | 2026-03-19 | 100 | No | 1 | 1 | NC-REBUILD
1444989 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0600-PC-601 | 0600-PC-601 PLINT RESIDUE CONVEYOR | PC-601 rollers seem to be seized. | MECH EXE CREW | 2026-02-23 13:42 | 2026-03-12 | 600 | No | 2 | 10 | NC-MECHANIC EXE
1377485 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | Install rigging points for CSM 1&2 belt conveyors. | COSERMO | 2025-04-03 07:56 | 2025-04-03 | 400 | Yes | 1 | 3 | NC-CONT-MECH
1445092 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 400 | ELECTROWINNING AREA 400 | Install safety gate on both transformers |  | 2026-02-25 14:01 | 2026-04-07 | 400 | Yes | 1 | 1 | NC-MECHANIC EXE
1394805 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 0300-GA-301-A-PUMP | GA-301A SILICA PRECIPITATION OVERFLOW PUMP (1151 GP @ 50.1 FT, 75 HP) | Run seal water line to GA-301s | COSERMO | 2025-06-24 12:45 | 2025-06-24 | 300 | No | 1 | 1 | NC-CONT-MECH
1409698 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0300-LT-3530 | ZINC PPT U/F TANK LEVEL | Install duct seal in all level transmitters. See list attached to documents | AALEXEYEV | 2025-08-26 13:51 | 2025-08-26 | 300 | No | 1 | 8 | NC-E/I
1434890 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 100 | Leaching | Safety shower #113 needs insulation/plastic around eyewash area |  | 2026-01-01 12:05 | 2026-01-01 | 100 | Yes | 1 | 1 | NC-CONT-MECH
1434891 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 100 | Leaching | Safety shower #118 needs insulation/plastic around eyewash area |  | 2026-01-01 12:06 | 2026-01-01 | 100 | Yes | 1 | 1 | NC-CONT-MECH
1434821 | 1-Emergency/Break-in | Awaiting Parts | Planned Work | 0100-TV-1021 | 0100-TV-1021 CONTROL VALVE | TV-1021 is leaking by when closed and needs to be replaced. | TMILLS2 | 2025-12-30 13:53 | 2025-12-30 | 300 | No | 1 | 1 | NC-MECHANIC
1441822 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0800-GA-810-C-PUMP | GA-810C BOILER DEAERATOR PUMP (114 GPM @ 340' TDH, 15 HP) | GA-810C Seal replacement in the field (D4M) | REBUILD CREW | 2026-02-06 08:46 | 2026-02-26 | 800 | No | 2 | 3 | NC-REBUILD
1445117 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-ZT-0701-A | CL-151B RAKE POSITION | replace missing zerk fitting hinges | COSERMO | 2026-02-26 05:11 | 2026-03-07 | 100 | No | 1 | 1 | NC-CONT-MECH
1445136 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-CONTACTBRUSH | CA-401 Stripping machine Contact Brush System | replace hold downs |  | 2026-02-26 09:36 | 2026-03-24 | 400 | No | 1 | 1 | NC-MECHANIC EXE
1437473 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0400-GA-422-A-PUMP | ANODE CLEANING HIGH PRESSURE WATER PUMPS (85 GPM @ 2610 PSI) | GA-422 Rebuild | REBUILD CREW | 2026-01-16 09:23 | 2026-01-26 | 400 | No | 2 | 16 | NC-MECHANIC
1444885 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0600-GA-650-B-PUMP | GA-650B LEAD PRECIPITATION PRESS FILTER FEED PUMPS | GA-650B Seal Leak | REBUILD CREW | 2026-02-20 09:47 | 2026-02-20 | 600 | No | 2 | 6 | NC-REBUILD
1444962 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FD-203-C-FILTER | FD-203C DEPLETED SOLUTION FILTER (NORMAL 506.8 / MAX 1258.4 GPM, 40 C, 0) | FT-2122C needs wired after mechanics install. | BBROUSE | 2026-02-23 07:41 | 2026-03-26 | 200 | No | 1 | 2 | NC-E/I
1444964 | 3-First Opportunity | Parts Required | Planned Work | 0500-PX-501 | PX-501 HERZOG METALS ANALYZER | herzog key to safety door broke inside the lock |  | 2026-02-23 08:04 | 2026-03-02 | 500 | No | 1 | 2 | NC-MECHANIC
1444898 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-INLET | CA-401 Stripping machine Inlet Conveyor | Put guards back in place on CSM 1 north side inlet conveyor. | COSERMO | 2026-02-20 13:37 | 2026-02-20 | 400 | No | 2 | 2 | NC-CONT-MECH
1448643 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0400-CA-401-ROLLTABLE | CA-401 Stripping Machine Roller Table | dissmantale roller for marcus 400-34620 and assemble after complete | REBUILD CREW | 2026-03-18 10:51 | 2026-03-23 | 400 | No | 2 | 2 | NC-REBUILD
1442948 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 0900-BA-901-FURNACE | BA-901 -ROTARY/RECYCLE FURNACE | Rotary Dumper leaking hydraulic oil (Hicham) | EQUIPMENT CREW | 2026-02-11 09:09 | 2026-03-17 | 900 | No | 1 | 1 | NC-EQUIPMENT
1371347 |  | Open - Ready to Schedule | Planned Work | 0400-GA-410-A-PUMP | GA-410-A PUMP (128 GPM @ 75' TDH) | replace insulation on GA-410A | LOBO | 2025-03-07 00:26 | 2025-03-07 | 400 | No | 1 | 2 | NC-LCS CONTRACT
1442950 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | Outside Lights on Metals & Reagent Warehouse are staying on all the time | AALEXEYEV | 2026-02-11 09:16 | 2026-02-16 | 1100 | No | 1 | 1 | NC-E/I
1443004 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | Swap inlet S to N and outlet S to N walking beam | COSERMO | 2026-02-12 03:06 | 2026-02-24 | 400 | No | 2 | 3 | NC-MECHANIC
1443005 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | Swap inlet S to N and outlet S to N walking beam | COSERMO | 2026-02-12 03:09 | 2026-03-06 | 400 | No | 2 | 3 | NC-MECHANIC EXE
1444954 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0400-PA-401-CRANE | KUNZ CRANE #1 | Kunz 1 south cathode hooks are losing hydraulic pressure when not active (Hicham | EQUIPMENT CREW | 2026-02-22 23:07 | 2026-04-07 | 400 | No | 2 | 3 | NC-EQUIPMENT
1448622 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FD-202-B-FILTER | FD-202B LOADED ELECTROLYTE FILTER (NORMAL 463.9 / MAX 1553.6 GPM, 39 C, 0) | FD-202B Media refill | MECH EXE CREW | 2026-03-17 15:54 | 2026-03-27 | 200 | No | 3 | 6 | NC-MECHANIC EXE
1409501 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0500-BA-501-0-FURNACE | CATHODE MELTING FURNACE | NEED RIGGING POINTS INSTALLED OVER ALL INDUCTER BLOWERS | COSERMO | 2025-08-22 10:49 | 2026-03-03 | 500 | No | 1 | 1 | NC-CONT-MECH
1429139 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-PA-401-CRANE | KUNZ CRANE #1 | PA-401 Travel position prox flickering (Nights) | AALEXEYEV | 2025-12-04 20:10 | 2026-04-07 | 400 | No | 1 | 3 | NC-E/I
1448611 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-DC-305-B-REACTOR | DC-305B CEMENTATION REACTOR (NOMINAL 2000 / NET 1545 FT3, 37-70 C) | Install manway on DC-305 B | MECH EXE CREW | 2026-03-17 13:34 | 2026-03-25 | 300 | No | 2 | 2 | NC-MECHANIC EXE
1448642 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-DC-201-B | 0200-DC-201-B HCL RECOVERY REACTOR | Remove 10" spool for nozzle inspection/repair | TMILLS2 | 2026-03-18 10:16 | 2026-03-24 | 200 | No | 2 | 3 | NC-MECHANIC EXE
1418492 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-GA-250-A-PUMP | GA-250A RAFFINATE TO FILTER PUMP | GA-250 Spare pump needs rebuilt | REBUILD CREW | 2025-10-12 12:07 | 2026-03-18 | 200 | No | 2 | 8 | NC-REBUILD
1418457 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0300-GD-340-0-AGITATOR | GD-340 GYPSUM COLLECTION TANK AGITATOR | GD-340 Install blades (D4M) | MECH EXE CREW | 2025-10-11 05:30 | 2026-03-27 | 300 | No | 3 | 4 | NC-MECHANIC EXE
1442898 | 3-First Opportunity | Parts Required | Planned Work | 0600-PX-613 | 0600-PX-613 LEAD PRECIPITATION PRESS FILTER PACKAGE | Install limit switches and solenoid on on/off knife gate | AALEXEYEV | 2026-02-10 12:53 | 2026-03-13 | 600 | No | 2 | 2 | NC-E/I
1419930 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0400-CA-401-VKNIFE | CA-401 Stripping machine Vertical Knife | Fabricate hyd manifolds blocks with NPT threads (Nigths) | LOWER PM CREW | 2025-10-23 06:53 | 2026-02-09 | 400 | No | 2 | 3 | NC-MECHANIC
1442901 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0500-PC-503 | Slab Casting Transfer Cart/Walking Beam Conveyor | (Outage) Conduit needs repaired on east side of R2D2 in front of line 2 | AALEXEYEV | 2026-02-10 13:03 | 2026-04-07 | 500 | Yes | 2 | 2 | NC-E/I
1442883 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-401-0-PUMP | GA-401 SPENT ELECTROLYTE RECIRCULATION PUMP #1 (177' TDH @ 3440GPM) | (HOLD) Seal leak on GA-401 (D8M) | REBUILD CREW | 2026-02-10 09:22 | 2026-03-16 | 400 | No | 2 | 8 | NC-REBUILD
1442882 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-404-0-PUMP | GA-404 SPENT ELECTROLYTE RECIRCULATION PUMP #4 (177' TDH @ 3440GPM) | (HOLD) Seal leak on GA-404 (D8M) | REBUILD CREW | 2026-02-10 09:21 | 2026-03-20 | 400 | No | 2 | 8 | NC-REBUILD
1435859 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-DC-201-B | 0200-DC-201-B HCL RECOVERY REACTOR | Install stainless steel tags on DC-201B using GA drawing for nozzle locations. | TMILLS2 | 2026-01-08 11:47 | 2026-03-20 | 200 | No | 2 | 3 | NC-E/I
1442842 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0100-GA-126-PUMP | 0100-GA-126-PUMP-LEACH RESIDUE PRESS FILTER CORE BLOW YCOLLECTION TANK PUMP | Convert GA-126 to AOD | MECH EXE CREW | 2026-02-09 14:42 | 2026-02-09 | 100 | No | 2 | 3 | NC-MECHANIC EXE
1442843 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0100-GA-192-0-PUMP | GA-192 LEACH RESIDUE PAD SUMP PUMP | Convert GA-192 to AOD | MECH EXE CREW | 2026-02-09 14:42 | 2026-02-09 | 100 | No | 2 | 3 | NC-MECHANIC EXE
1442845 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0300-GA-395-0-PUMP | GA-395 METALS POLISHING AREA SUMP PUMP | Convert GA-395 to AOD | MECH EXE CREW | 2026-02-09 14:44 | 2026-02-09 | 300 | No | 2 | 3 | NC-MECHANIC EXE
1442846 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0300-GA-396-1-PUMP | GA-396.1 FINAL RESIDUE PAD SUMP PUMP | Convert GA-396 to AOD | MECH EXE CREW | 2026-02-09 14:45 | 2026-02-09 | 300 | No | 2 | 3 | NC-MECHANIC EXE
1442847 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0200-GA-226-0-PUMP | GA-226 CRUD TREATMENT PRESS FILTER CORE BLOW COLLECTION TANK PUMP | Convert GA-226 to AOD | MECH EXE CREW | 2026-02-09 14:46 | 2026-02-09 | 200 | No | 2 | 3 | NC-MECHANIC EXE
1448469 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 100 | Leaching | (Outage) replace raff addition valve on GA-204B\C line to lower sumps | MECH EXE CREW | 2026-03-17 04:26 | 2026-04-08 | 100 | Yes | 2 | 3 | NC-MECHANIC EXE
1444534 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0500-GA-504-0-PUMP | GA-504 MELTING FURNACE TO PW ALLOY FURNACE FEED PUMP | (HOLD) install pump stand on furnace | LOWER PM CREW | 2026-02-20 07:32 | 2026-02-20 | 500 | No | 2 | 3 | NC-PM DAY
1450159 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-443-C-PUMP | GA-443C PUMP (1700 GPM @ 95' TDH) | GA-443 C Water Leak | REBUILD CREW | 2026-03-22 10:49 | 2026-04-07 | 400 | No | 2 | 3 | NC-REBUILD
1450210 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-341-0-PUMP | GA-341 METALS POLISHING COLLECTION TANK PUMP | GA-341 Seal leak, Pull, rebuild, & reinstall. | REBUILD CREW | 2026-03-23 10:32 | 2026-04-03 | 300 | No | 2 | 8 | NC-REBUILD
1450220 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 0300-CEMENTATION CONTAINMENT | Cementation Containment | Add crimp fitting to bootwash in Cementation | TMILLS2 | 2026-03-23 12:54 | 2026-03-30 | 300 | No | 1 | 1 | NC-MECHANIC EXE
1448480 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-306-A-PUMP | GA-306A METALS POLISHING UNDERFLOW PUMP (110 GPM @ 55' TDH, 5 HP) | (HOLD) Replace GA-306-A. Not getting enough flow at 100% output. | TMILLS2 | 2026-03-17 09:34 | 2026-04-02 | 300 | No | 2 | 8 | NC-REBUILD
1441434 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-304-A-PUMP | GA-304A FILTERED CEMENTED SOLUTION PUMP (1145 GPM @ 46' TDH, 40 HP) | Run hard line for GA-304 seal water (D5M) | MECH EXE CREW | 2026-02-05 11:30 | 2026-04-07 | 300 | No | 2 | 5 | NC-MECHANIC EXE
1442871 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0700-LSLL-7034-0-CTRL | SULFURIC ACID STORAGE TANK FB-708 LOW LEVEL SWITCH LSLL-7034 | (Outage) switch keeps going active causing pump to kick off | BBROUSE | 2026-02-10 01:43 | 2026-04-07 | 700 | No | 1 | 2 | NC-E/I
1442873 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0400-CA-402-ROLLTABLE | CA-402 Stripping Machine Roller Table | rebuild drive roller | LOWER PM CREW | 2026-02-10 05:24 | 2026-02-10 | 400 | No | 2 | 4 | NC-PM DAY
1442905 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FD-202-B-FILTER | FD-202B LOADED ELECTROLYTE FILTER (NORMAL 463.9 / MAX 1553.6 GPM, 39 C, 0) | Remove piping after pressure test | UPPER PM CREW | 2026-02-10 13:27 | 2026-02-19 | 200 | No | 2 | 3 | NC-PM DAY
1448482 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FD-203-C-FILTER | FD-203C DEPLETED SOLUTION FILTER (NORMAL 506.8 / MAX 1258.4 GPM, 40 C, 0) | FT-2122C needs wired after mechanics install. (D4M) | MECH EXE CREW | 2026-03-17 10:37 | 2026-04-01 | 200 | No | 2 | 3 | NC-MECHANIC EXE
1448438 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 500 | MELTING / CASTING, AREA 500 | mount hose reel in ajax room on 3 inch water line | LOWER PM CREW | 2026-03-16 13:26 | 2026-03-26 | 500 | No | 2 | 2 | NC-PM DAY
1448408 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-PX-301-B | PX-301B GYPSUM BELT FILTER PACKAGE | South receiver tank drain valve stem broke | TMILLS2 | 2026-03-16 04:37 | 2026-03-26 | 300 | No | 2 | 1 | NC-MECHANIC EXE
1448474 |  | Awaiting Parts | Planned Work | 0400-PA-402-CRANE | KUNZ CRANE #2 | A&W to install rails & rollers for energy chain on the outside of bay 2 north | A W | 2026-03-17 08:06 | 2026-03-17 | 400 | No | 1 | 1 | NC-CONT-ELEC
1444511 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0400-CA-402-INLET | CA-402 Stripping Machine Inlet Conveyor | (HOLD) replace wear plate for up/dwn rollers 4 ea (Nights) | LOWER PM CREW | 2026-02-19 14:12 | 2026-03-04 | 400 | No | 2 | 3 | NC-PM NIGHT
1364287 |  | Open - Ready to Schedule | Planned Work | 0700-PX-781 D | PX-781 D -ZINC PRECIPITATION THICKENER FLOCCULANT PREP PACKAGE | repair insulation at FLOC skid PX-781 D | LOBO | 2025-01-26 07:19 | 2025-01-26 | 300 | No | 1 | 1 | NC-LCS CONTRACT
1364289 |  | Open - Ready to Schedule | Planned Work | 0400-FB-452-0-TANK | FB-452 ELECTROLYTE STORAGE TANK (364200 GAL) | repair insulation around isolation valve at safety showers in 450 containment | LOBO | 2025-01-26 07:21 | 2025-01-26 | 400 | Yes | 1 | 1 | NC-LCS CONTRACT
1381346 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 400 | ELECTROWINNING AREA 400 | Water leak beneath bay 2 in the basement by the back stairs | COSERMO | 2025-04-21 09:01 | 2026-01-27 | 400 | No | 1 | 1 | NC-CONT-MECH
1446276 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 400 | ELECTROWINNING AREA 400 | Drill holes for voltage wire in spare EQ bars | AALEXEYEV | 2026-03-04 10:11 | 2026-03-04 | 400 | No | 1 | 1 | NC-E/I
1446277 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 400 | ELECTROWINNING AREA 400 | Replace # 10 EQ bar | MECH EXE CREW | 2026-03-04 10:13 | 2026-04-07 | 400 | No | 3 | 3 | NC-MECHANIC EXE
1446295 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-GA-140-PUMP | GA-140 LEACH COLLECTION TANK PUMP | Rebuild GA-140 that is in shed | REBUILD CREW | 2026-03-04 13:40 | 2026-03-26 | 100 | No | 2 | 8 | NC-REBUILD
1439640 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0500-CA-501-ROBOT | CASTING MACHINE #1 ROBOT | Build Spare Slab Line Stacker Assy | LOWER PM CREW | 2026-01-28 12:13 | 2026-02-03 | 500 | No | 2 | 15 | NC-MECHANIC
1446126 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0100-GA-181-A-PUMP | GA-181-A WOX WASHING THICKENER UNDERFLOW PUMP | GA-181 A/B Need hooked up to the seal water skid | MECH EXE CREW | 2026-02-28 14:38 | 2026-03-10 | 100 | No | 2 | 2 | NC-MECHANIC EXE
1446273 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0500-BA-501-0-FURNACE | CATHODE MELTING FURNACE | Move Thermocouple from west side of furnace to east side | AALEXEYEV | 2026-03-04 09:10 | 2026-03-11 | 500 | No | 2 | 3 | NC-E/I
1419627 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-STACKER | CA-401 Stripping Machine Stacker | Level and grout base | COSERMO | 2025-10-22 14:05 | 2026-03-03 | 400 | No | 1 | 1 | NC-CONT-MECH
1438439 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 900 | METAL RECYCLING, AREA 900 | Find replacement valves for 900 sifter totes |  | 2026-01-22 10:25 | 2026-01-22 | 900 | No | 1 | 1 | NC-MECHANIC
1436796 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0200-FD-204-A-FILTER | FD-204-A HCL FILTER | Drain valve on the FD-204 A flange needs replaced and valve added. | COSERMO | 2026-01-14 11:42 | 2026-03-05 | 200 | No | 2 | 2 | NC-CONT-MECH
1446251 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-405-0-PUMP | GA-405 SPENT ELECTROLYTE RECIRCULATION PUMP #5 (177' TDH @ 3440GPM) | Replace EJ at pump discharge | COSERMO | 2026-03-03 17:04 | 2026-03-16 | 400 | No | 2 | 2 | NC-CONT-MECH
1446203 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-PX-101-A | 0100-PX-101-A FILTER PRESS | Remove unused limit switches (see comments) | AALEXEYEV | 2026-03-02 17:37 | 2026-04-07 | 100 | No | 1 | 4 | NC-E/I
1446204 |  | Open - Ready to Schedule | Planned Work | 0100-PX-101-B | 0100-PX-101-B FILTER PRESS | Removed unused limit switches (see comments) | AALEXEYEV | 2026-03-02 17:42 | 2026-04-07 | 100 | No | 2 | 4 | NC-E/I
1446160 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0300-CL-301 | CL-301 SILICA PRECIPITATION THICKENER | Clarkson valve to GA-302A needs replaced OUTAGE | MECH EXE CREW | 2026-03-02 07:46 | 2026-04-07 | 300 | No | 2 | 2 | NC-MECHANIC EXE
1446322 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 100 | Leaching | Jet Air booth at SX building runs constantly | AALEXEYEV | 2026-03-05 09:00 | 2026-03-14 | 100 | Yes | 1 | 1 | NC-E/I
1423654 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0400-CA-402-0-HPU | ROW#2 MACHINE HYDRAULIC UNIT | CA-402 hydraulic leaks on filter housings (Nights) | LOWER PM CREW | 2025-11-04 14:01 | 2026-03-13 | 400 | No | 2 | 4 | NC-MECHANIC EXE
1446090 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-CL-151-A | 0100-CL-151-A NEUTRAL LEACHING THICKENER | HPU ON CLARIFIER-HYDRAULIC LINE NEED REPLACED(SEE COMMENT) | EQUIPMENT CREW | 2026-02-27 12:43 | 2026-03-09 | 100 | No | 1 | 2 | NC-EQUIPMENT
1446182 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | BUILD 3196NM 1.5X3-6 STI | REBUILD CREW | 2026-03-02 11:08 | 2026-03-16 | 300 | No | 2 | 6 | NC-REBUILD
1448089 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0600-PC-601 | 0600-PC-601 PLINT RESIDUE CONVEYOR | PC-601 Motor and roller guard needs replaced | TMILLS2 | 2026-03-12 15:45 | 2026-03-12 | 600 | No | 1 | 1 | NC-MECHANIC EXE
1449845 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0400-CA-401-BELTCONV | CA-401 Stripping Machine Belt Conveyor | Replace belt and back roller on CSM1 conveyor | LOWER PM CREW | 2026-03-19 13:50 | 2026-04-07 | 400 | No | 1 | 1 | NC-PM DAY
1448054 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-GA-204-A-PUMP | GA-204A FILTERED RAFFINATE PUMP (2500 GPM AT 180' TDH, 4160 VAC, 200 HP) | (outage) GA-204A - Realign and mechanical inspection | REBUILD CREW | 2026-03-12 11:50 | 2026-04-07 | 200 | No | 2 | 4 | NC-REBUILD
1398845 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-EA-201 | 0200-EA-201 DEMIN WATER HEAT EXCHANGER | Modify EA-201 piping | COSERMO | 2025-07-04 09:21 | 2025-07-04 | 200 | No | 2 | 10 | NC-CONT-MECH
1432591 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0400-PA-401-CRANE | KUNZ CRANE #1 | Marcus to fab glide rail for Kunz 1 e-chain trough & install (see drawing) | AALEXEYEV | 2025-12-19 11:52 | 2025-12-19 | 400 | No | 1 | 1 | NC-E/I
1432619 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0100-GA-184-PUMP | 0100-GA-184-HP CLOTH WASHING PUMP | PX-184 Parts need ordered for the spare pump | MECH EXE CREW | 2025-12-20 18:06 | 2025-12-20 | 100 | No | 1 | 2 | NC-MECHANIC
1448039 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-CG-101-A-HPU | CG-101A L/N PRESS FILTER HPU (50 HP) | CG-101 A/B Heaters need shut off for hot weather | MECH EXE CREW | 2026-03-12 08:56 | 2026-03-31 | 100 | No | 1 | 1 | NC-MECHANIC EXE
1448046 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-0-HPU | ROW#1 MACHINE HYDRAULIC UNIT | hydraulic hose leaking through hole under steps {see comment} (Nigths) | LOWER PM CREW | 2026-03-12 10:09 | 2026-03-23 | 400 | No | 2 | 2 | NC-PM NIGHT
1423569 | 2-Urgent/Scheduled | Parts Required | Planned Work | 0200-GA-224-0-PUMP | GA-224 CRUD FILTER FEED PUMP (28 GPM @ 296' TDH, 20 HP) | Rebuild GA-224 | REBUILD CREW | 2025-11-03 17:29 | 2026-02-27 | 200 | No | 2 | 4 | NC-REBUILD
1408735 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | inspect process water flow meters | AALEXEYEV | 2025-08-18 12:44 | 2025-11-13 | 1100 | No | 2 | 6 | NC-E/I
1439539 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 100 | Leaching | Roll out for jetting then back in. FIC1022 off CL-101B underflow to FB-111 | UPPER PM CREW | 2026-01-27 09:35 | 2026-03-17 | 100 | No | 2 | 2 | NC-PM DAY
1420764 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-DC-305-B-REACTOR | DC-305B CEMENTATION REACTOR (NOMINAL 2000 / NET 1545 FT3, 37-70 C) | Install welding receptacle near DC-305 (TERRY/A&W) | TMILLS2 | 2025-10-28 15:40 | 2026-03-11 | 300 | No | 2 | 6 | NC-E/I
1432538 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 0500-PC-501-0-HPU | PC-501 CATHODE MELTING CHARGING SYSTEM HPU | (Outage) Change all hydraulic hoses on system (Hicham) | EQUIPMENT CREW | 2025-12-18 14:47 | 2026-04-07 | 500 | No | 2 | 5 | NC-EQUIPMENT
1432539 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-PX-310 | PX-310 -GYPSUM PRECIPITATION CYCLONE PACK | Cyclone #7 is leaking in multiple spots needs rebuilt | REBUILD CREW | 2025-12-18 15:07 | 2026-04-03 | 300 | No | 2 | 3 | NC-REBUILD
1432524 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-321-B-PUMP | GA-321-B-GYPSUM PRECIPITATION CYCLONE UNDERFLOW SEED RECYCLE PUMP | Rebuild GA-321 | REBUILD CREW | 2025-12-18 13:02 | 2026-03-13 | 300 | No | 2 | 10 | NC-REBUILD
1439440 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GB-401-0-FILTER | STAINLESS STEEL FINE FILTER | GB-401 bottom strainer's door seal is corroded | LOWER PM CREW | 2026-01-23 18:07 | 2026-01-23 | 400 | No | 1 | 1 | NC-MECHANIC
1439501 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0100-DC-101-E-REACTOR | DC-101E NEUTRALIZATION REACTOR (NOMINAL 15930/NET 13766 FT3, 40-60 C) | Safety Shower water line rupture on top of DC-101E | COSERMO | 2026-01-26 13:09 | 2026-02-05 | 100 | Yes | 2 | 2 | NC-CONT-MECH
1440685 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0900-BH-901 | BH-901 -BAGHOUSE | Scope/plan new air purge controls BH-901 (Terry/A&W) | AALEXEYEV | 2026-01-29 15:02 | 2026-03-17 | 900 | No | 2 | 10 | NC-E/I
1435167 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CCTV-BAY1-MIDDLE-THERMAL | BAY 1 MIDDLE THERMAL CAMERA | Run a dedicated circuit to the thermal camera network box from DP-400-02 | AALEXEYEV | 2026-01-06 08:31 | 2026-03-12 | 400 | No | 2 | 8 | NC-E/I
1439371 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-402-BELTCONV | CA-402 Stripping Machine Belt Conveyor | (Outage) Drive roller needs changed on CSM2 stacker belt | LOWER PM CREW | 2026-01-22 18:23 | 2026-03-04 | 400 | No | 3 | 6 | NC-PM DAY
1439356 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-CL-101-A | CL-101-A L/N Clarifier Thickener | (OUTAGE) GX-103 Oil Change - High water (D3M) | UPPER PM CREW | 2026-01-22 13:46 | 2026-04-07 | 100 | No | 2 | 3 | NC-PM DAY
1439358 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-GD-180-A-AGITATOR | GD-180-A WOX WASHING REACTOR AGITATOR | (OUTAGE) GD-180A Oil Change (D3M) | UPPER PM CREW | 2026-01-22 13:52 | 2026-04-07 | 100 | No | 2 | 3 | NC-PM DAY
1442079 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FD-203-C-FILTER | FD-203C DEPLETED SOLUTION FILTER (NORMAL 506.8 / MAX 1258.4 GPM, 40 C, 0) | FD-203C Reinstall top 90 and Torque (D3M) | MECH EXE CREW | 2026-02-09 13:58 | 2026-04-01 | 200 | No | 3 | 3 | NC-MECHANIC EXE
1433738 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-PX-183-PRSFLTR | PX-183 PRESS FILTER PACKAGE | Add time out alarm for PT-1947 during discharge (see comments for scheduling) | AALEXEYEV | 2025-12-24 18:05 | 2026-03-17 | 100 | No | 1 | 2 | NC-E/I
1435184 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GD-324-A-AGITATOR | GD-324A LIMESTONE PRECIPITATION REACTOR AGITATOR FOR DC-324A | (HOLD) GD-324A Retorque mounting bolts and inspect blades. | TMILLS2 | 2026-01-06 13:00 | 2026-01-06 | 300 | No | 2 | 3 | NC-MECHANIC
1435201 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FA-211-TANK | FA-211 CRUD FILTER FEED TANK (NOMINAL 3165 / NET 3796 FT3, 50-60 C, 0) | Old steam line knocking side of tank (Tank Needs Drained) | UPPER PM CREW | 2026-01-06 15:19 | 2026-03-20 | 200 | No | 2 | 3 | NC-PM DAY
1443885 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 500 | MELTING / CASTING, AREA 500 | Torch set in lower shop need spark arrestors | LOWER PM CREW | 2026-02-16 16:49 | 2026-02-23 | 500 | No | 1 | 1 | NC-PM DAY
1444005 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-323-MOTOR | GA-323 METAL POLISHING PRESS FILTER CORE BLOW COLLECTION TANK PUMP MOTOR PX-303 | Install solenoid for new AOD to replace GA-323 (completed except for automation) | TMILLS2 | 2026-02-18 12:54 | 2026-03-16 | 300 | No | 1 | 4 | NC-E/I
1444006 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-0-HPU | ROW#1 MACHINE HYDRAULIC UNIT | cap leaking (Hicham) | EQUIPMENT CREW | 2026-02-18 13:21 | 2026-03-19 | 400 | No | 1 | 2 | NC-EQUIPMENT
1444009 | 1-Emergency/Break-in | Scoping Required | Planned Work | 0800-PX-807-B | 0800-PX-807-B COMPRESSOR AIR DRYER | PX-807-B Air leaking Valve Stuck Open | BBROUSE | 2026-02-18 13:40 | 2026-02-18 | 800 | No | 1 | 1 | NC-E/I
1429636 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-422-A-PUMP | ANODE CLEANING HIGH PRESSURE WATER PUMPS (85 GPM @ 2610 PSI) | Install water service accumulator on GA-422 |  | 2025-12-10 09:33 | 2026-03-19 | 400 | No | 2 | 2 | NC-MECHANIC EXE
1444025 |  | Awaiting Parts | Planned Work | 0400-PA-401-0-MCS | KUNZ CRANE #1 MAIN CONTROL STATION | Retrofit existing level 4 push buttons (400-12050) w/ push button retrofit kit |  | 2026-02-18 15:31 | 2026-02-18 | 400 | No | 1 | 1 | NC-E/I
1443988 |  | Open - Ready to Schedule | Planned Work | 0200-FD-202-B-FILTER | FD-202B LOADED ELECTROLYTE FILTER (NORMAL 463.9 / MAX 1553.6 GPM, 39 C, 0) | Repair FD-202B coating (Blastco) | TMILLS2 | 2026-02-18 10:30 | 2026-03-23 | 200 | No | 1 | 1 | NC-CONT-MECH
1447544 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-GA-154-B1-0-PUMP | GA-154B1 L/N PRESS FILTER FEED PUMP | (HOLD) GA-154B1 internal seal leak | REBUILD CREW | 2026-03-11 09:37 | 2026-03-11 | 100 | No | 2 | 8 | NC-REBUILD
1447526 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-402-BELTCONV | CA-402 Stripping Machine Belt Conveyor | rebuild belt conveyor roller | LOWER PM CREW | 2026-03-11 05:58 | 2026-03-19 | 400 | No | 2 | 2 | NC-PM DAY
1447541 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FD-202-F-FILTER | FD-202F LOADED ELECTROLYTE FILTER (NORMAL 463.9 / MAX 1553.6 GPM, 39 C, 0) | Install distributor and 90 after coating repair | MECH EXE CREW | 2026-03-11 09:32 | 2026-03-11 | 200 | No | 1 | 1 | NC-MECHANIC EXE
1447542 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-FD-202-B-FILTER | FD-202B LOADED ELECTROLYTE FILTER (NORMAL 463.9 / MAX 1553.6 GPM, 39 C, 0) | Reinstall piping and top 90 on FD-202 B after coating repair | TMILLS2 | 2026-03-11 09:33 | 2026-03-26 | 200 | No | 1 | 1 | NC-MECHANIC EXE
1417486 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0700-GA-700-E-PUMP | GA-700E WOX SLURRY PREPARATION TANK PUMP | Need suction gauge installed on GA-700E | COSERMO | 2025-10-04 08:29 | 2025-10-04 | 700 | No | 1 | 2 | NC-CONT-MECH
1417483 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0700-GA-700-B-PUMP | WOX SLURRY PREPARATION TANK PUMP GA-700B | Need suction gauge installed on GA-700B | COSERMO | 2025-10-04 08:27 | 2025-10-04 | 700 | No | 1 | 1 | NC-CONT-MECH
1417484 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0700-GA-700-D-PUMP | WOX SLURRY PREPARATION TANK PUMP GA-700D | Need suction gauge installed on GA-700D | COSERMO | 2025-10-04 08:28 | 2025-10-04 | 700 | No | 1 | 2 | NC-CONT-MECH
1434969 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-STACKER | CA-401 Stripping Machine Stacker | CA-401-402 Need to relocate junction boxes at stackers | AALEXEYEV | 2026-01-03 18:27 | 2026-04-08 | 400 | No | 2 | 6 | NC-E/I
1447548 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-GA-203-PUMP | GA-203 HCL SCRUBBER RECIRCULATION PUMP FOR PX-203 | GA-203 Recirc pump leaking from casing. | MECH EXE CREW | 2026-03-11 10:05 | 2026-03-18 | 200 | No | 2 | 1 | NC-MECHANIC EXE
1435018 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 200 | SOLVENT EXTRACTION, AREA 200 | (Outage) Process water header leaking in front of site services trailer | UPPER PM CREW | 2026-01-05 11:36 | 2026-04-07 | 200 | No | 2 | 2 | NC-PM DAY
1435016 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0200-GA-253-A-PUMP | GA-253A SPENT HCL SOLUTION PUMP | GA-253 in shop needs rebuild | TMILLS2 | 2026-01-05 10:00 | 2026-06-16 | 200 | No | 1 | 2 | NC-REBUILD
1447383 | 3-First Opportunity | Open - Ready to Schedule | Planned Work | 2100 | Maintenance shop Tools and Equipment | 5S LOWER SHOP | LOWER PM CREW | 2026-03-09 05:05 | 2026-03-21 | 2100 | No | 2 | 4 | NC-PM NIGHT
1447324 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-GA-451-A-PUMP | GA-451 SPENT ELECTROLYTE PUMP (1560 GPM @ 80' TDH, 60 HP) | Twist piping and remount pipe clamp on discharge |  | 2026-03-07 11:46 | 2026-03-18 | 400 | No | 2 | 2 | NC-MECHANIC EXE
1447536 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0200-GA-252-A-PUMP | GA-252A LOADED ELECTROLYTE PUMP (1700 GPM @ 110' TDH, 100 HP) | Change discharge valve on GA-252A to lug style so spool can be removed | TMILLS2 | 2026-03-11 09:04 | 2026-04-08 | 200 | No | 2 | 3 | NC-MECHANIC EXE
1436320 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-391-0-PUMP | GA-391 SILICA THICKENER SUMP PUMP | Run wiring for solenoid at GA-391 | AALEXEYEV | 2026-01-11 16:29 | 2026-03-27 | 300 | No | 1 | 3 | NC-E/I
1441959 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0400-PC-405 | METAL SHEAR | PC-405 knife not working | LOWER PM CREW | 2026-02-06 13:32 | 2026-02-06 | 400 | No | 2 | 4 | NC-MECHANIC
1443872 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 200 | SOLVENT EXTRACTION, AREA 200 | Red buggy wont drive past 3 mph and sounds terrible. (Hicham) |  | 2026-02-16 12:49 | 2026-03-25 | 200 | No | 1 | 3 | NC-EQUIPMENT
1447373 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0700-GA-700-F-PUMP | WOX SLURRY PREPARATION TANK PUMP GA-700F | GA-700F has a seal leak (D6M) | REBUILD CREW | 2026-03-08 17:07 | 2026-03-17 | 700 | No | 2 | 5 | NC-REBUILD
1447328 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-319-A-PUMP | GA-319-A SILICA PRECIPITATION THICKENER FEED PUMP | GA-319A Inspect pump and open front casing. Install Belts | MECH EXE CREW | 2026-03-07 15:03 | 2026-04-08 | 300 | No | 2 | 6 | NC-REBUILD
1447336 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-319-B-PUMP | GA-319-B SILICA PRECIPITATION THICKENER FEED PUMP | Seal water line going to the seal pot on GA-319 B is leaking. | REBUILD CREW | 2026-03-07 22:44 | 2026-04-08 | 300 | No | 2 | 2 | NC-REBUILD
1447357 | 1-Emergency/Break-in | Open - Ready to Schedule | Planned Work | 0200-GA-209-B-PUMP | GA-209B FILTERED LOADED ELECTROLYTE PUMP (1560 GPM @ 80' TDH, 60 HP) | GA-209B seal water fittings blew out (D1M) | MECH EXE CREW | 2026-03-08 09:06 | 2026-03-17 | 200 | No | 2 | 1 | NC-MECHANIC EXE
1447469 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 1400-ME-249 | Warehouse Golf Cart Club Car | Golf cart won't move (Hicham) | EQUIPMENT CREW | 2026-03-10 06:43 | 2026-03-10 | 1400 | No | 1 | 1 | NC-EQUIPMENT
1447305 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-340-A-PUMP | GA-340-A GYPSUM COLLECTION TANK PUMPS | GA-340-A/B- need filter installed near seal pot (On Going) | MECH EXE CREW | 2026-03-06 14:52 | 2026-03-18 | 300 | No | 2 | 4 | NC-MECHANIC EXE
1447308 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-GA-111-B-PUMP | GA-111B L/N FEED PUMP (OVERHEAD BELT DRIVE, 60 HP) | GA-111-B-NEEDS GAUGE REPLACED | SWORLEY2 | 2026-03-06 14:57 | 2026-03-16 | 100 | No | 1 | 1 | NC-LUBRICATOR
1447244 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0600-GA-650-B-PUMP | GA-650B LEAD PRECIPITATION PRESS FILTER FEED PUMPS | GA-650B discharge valve leaking from drains while closed (D4M) | MECH EXE CREW | 2026-03-05 17:23 | 2026-03-16 | 600 | No | 2 | 4 | NC-MECHANIC EXE
1447298 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0500-BA-501-4A | BA-501-4A Melt Furnace Induction blower motor | (outage) Replace BA-501-A4 | MECH EXE CREW | 2026-03-06 13:31 | 2026-04-08 | 500 | No | 2 | 3 | NC-MECHANIC EXE
1447300 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0500-BA-501-3A | BA-501-3A Melt Furnace Induction blower motor | (outage) Replace BA-501-A3 | MECH EXE CREW | 2026-03-06 13:32 | 2026-04-08 | 500 | No | 2 | 3 | NC-MECHANIC EXE
1447557 | 2-Urgent/Scheduled | Scoping Required | Planned Work | 0200-GA-252-A-PUMP | GA-252A LOADED ELECTROLYTE PUMP (1700 GPM @ 110' TDH, 100 HP) | Support Beams for GA-252A Needs Replaced (See Pictures) | COSERMO | 2026-03-11 11:01 | 2026-03-11 | 200 | No | 1 | 1 | NC-CONT-MECH
1447590 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-TRANSCART | CA-401 Stripping machine Transfer Cart | linear bearings are showing wear (Nights ) | LOWER PM CREW | 2026-03-12 07:37 | 2026-03-24 | 400 | No | 2 | 3 | NC-PM NIGHT
1447571 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0600-PX-601 | 0600-PX-601 LEAD LEACHING FILTRATION PACKAGE | PX-601 Slurry Ring Main (Cosermo) | COSERMO | 2026-03-11 15:21 | 2026-03-23 | 600 | No | 1 | 1 | NC-CONT-MECH
1449383 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0400-CA-401-STRIPPING | CA-401 Stripping machine Stripping Conveyor | Install modified sway bar and move prox (Nighs) | LOWER PM CREW | 2026-03-19 07:08 | 2026-04-01 | 400 | No | 2 | 2 | NC-PM NIGHT
1447329 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0300-GA-319-A-PUMP | GA-319-A SILICA PRECIPITATION THICKENER FEED PUMP | GA-319A discharge valve needs replaced. | MECH EXE CREW | 2026-03-07 15:12 | 2026-04-08 | 300 | No | 2 | 3 | NC-MECHANIC EXE
1447258 | 2-Urgent/Scheduled | Open - Ready to Schedule | Planned Work | 0100-UV-0302 | ACID LEACHING THICKNER UNDERFLOW VALVE | UV-0302 valve stem is broken from knife gate (D2M) | MECH EXE CREW | 2026-03-06 09:43 | 2026-03-19 | 100 | No | 2 | 2 | NC-MECHANIC EXE
1447239 | 2-Urgent/Scheduled | Awaiting Parts | Planned Work | 0200-GA-234-A-PUMP | GA-234A SX MAINTENANCE POND PUMP | Rebuild GA-234 | REBUILD CREW | 2026-03-05 15:02 | 2026-03-12 | 200 | No | 3 | 8 | NC-REBUILD
1447438 | 1-Emergency/Break-in | Scoping Required | Planned Work | 100 | Leaching | PX-183 building outlets have tripped | AALEXEYEV | 2026-03-09 14:48 | 2026-03-09 | 100 | No | 1 | 1 | NC-E/I
1447110 |  | Open - Ready to Schedule | Planned Work | 0400-CA-403-ANWAGON | ANODE WAGON | Anode bay cart needs furniture changed |  | 2026-03-05 11:30 | 2026-04-03 | 400 | No | 2 | 3 | NC-MECHANIC EXE
1376960 |  | Open - Ready to Schedule | Preventive maintenance | 0800-SW | UTILITIES STORM WATER SYSTEM | ANNUAL SEWER SYSTEM MANHOLE COVER PAINT INSPECTION | SALLEN2 | 2025-03-31 11:32 | 2026-03-29 | 800 | No | 2 | 2 | NC-LUBRICATOR | EHS
1341609 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-700 | BH-700 -WOX SILO DUST COLLECTOR | SEMI-ANNUAL INSPECTION AND CLEANOUT OF BH-700 [D] |  | 2024-09-26 09:07 | 2026-02-27 | 1200 | No | 2 | 2 | NC-MECHANIC
1387468 |  | Open - Ready to Schedule | Preventive maintenance | 0200-DC-201-B | 0200-DC-201-B HCL RECOVERY REACTOR | TEST TEMPERATURES AND LEVELS SIS SYSTEM DC-201 | TMILLS2 | 2025-05-20 17:58 | 2026-04-01 | 200 | No | 2 | 2 | NC-E/I
1398429 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PSV-2165A | 0200-PSV-2165A STEAM TO HCL REBOILER EA-203A | ANNUAL CERTIFICATION OF PSVs | TMILLS2 | 2025-07-03 14:47 | 2026-01-20 | 800 | No | 2 | 2 | NC-MECHANIC
1375087 |  | Open - Ready to Schedule | Preventive maintenance | 0800-FW-1003 | FIRE WATER UNDERGROUND LOOP | MONTHLY UNDERGROUND FIRE WATER VALVE CHECK | NC-LUBRICATOR | 2025-03-23 15:06 | 2026-03-23 | 800 | No | 1 | 5 | NC-LUBRICATOR
1437534 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-C | WOX SILO BIN C VENT (1039 FT2 FILTER AREA, 0) | BAGHOUSE CLEAN AND INSPECT [D] | TMILLS2 | 2026-01-18 08:41 | 2026-04-19 | 700 | No | 2 | 2 | NC-MECHANIC EXE | EHS
1437665 |  | Open - Ready to Schedule | Preventive maintenance | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | 300 Area Grease Caddy PM - Bleed 4 |  | 2026-01-20 14:46 | 2026-04-20 | 300 | No | 2 | 4 | NC-LUBRICATOR
1437635 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-705-0-FAN | GB-705 WOX DUST COLLECTOR BLOWER (5696 CFM, 1770 RPM, 30HP) | FAN INSPECTION [D] | SWORLEY2 | 2026-01-19 18:23 | 2026-04-19 | 700 | No | 1 | 1.5 | NC-MECHANIC EXE | EHS
1448778 |  | Open - Ready to Schedule | Preventive maintenance | 0200-EER-AREA 200 | Electrical Room Area 200 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TMILLS2 | 2026-03-18 14:42 | 2026-04-27 | 200 | No | 1 | 1 | NC-E/I
1424589 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GA-700-D-PUMP | WOX SLURRY PREPARATION TANK PUMP GA-700D | 4 WEEK ALBIN PUMP HOSE REPLACEMENT [D] | TMILLS2 | 2025-11-12 16:45 | 2026-03-25 | 700 | No | 1 | 3 | NC-PM DAY
1448780 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PX-201 | 0200-PX-201 CRUD TREATMENT PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:42 | 2026-04-14 | 200 | No | 1 | 1 | NC-LUBRICATOR
1448781 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PX-201PRECOAT | 0200-Precoat System on PX-201 | Precoat System Lubrication [D] | TMILLS2 | 2026-03-18 14:42 | 2026-04-13 | 200 | No | 1 | 1 | NC-LUBRICATOR
1448847 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-302-A | PX-302A CEMENTATION SOLUTION PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:43 | 2026-04-30 | 300 | No | 1 | 1 | NC-LUBRICATOR
1448846 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-302-A | PX-302A CEMENTATION SOLUTION PRESS FILTER PACKAGE | FILTER PRESS QUARTERLY [D4] | TMILLS2 | 2026-03-18 14:43 | 2026-04-06 | 300 | No | 2 | 4 | NC-MECHANIC EXE | CRITICAL
1448853 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-302-B | PX-302B CEMENTATION SOLUTION PRESS FILTER PACKAGE | FILTER PRESS QUARTERLY [D4] | TMILLS2 | 2026-03-18 14:43 | 2026-04-20 | 300 | No | 2 | 4 | NC-MECHANIC EXE | CRITICAL
1448783 |  | Open - Ready to Schedule | Preventive maintenance | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | AREA 0300 QUARTERLY OIL SAMPLE ANALYSIS [R] |  | 2026-03-18 14:42 | 2026-04-07 | 300 | No | 1 | 5 | NC-LUBRICATOR
1448795 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3152 | AT-3152 [DC-305A/B] Ambient H2 TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:42 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448794 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AE-3155-B | DC-305B: In-situ Duct H2 SENSOR | MONTHLY HYDROGEN GAS SAMPLING SYSTEM FILTER REPLACMENT[R] | ELUSTER2 | 2026-03-18 14:42 | 2026-04-06 | 300 | No | 1 | 0.5 | NC-E/I
1448796 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3153 | AT-3153 [FA-310]: Ambient H2 TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:42 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448797 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3154 | AT-3154 [DC-305A/B] In-situ Tank H2 TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:42 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448798 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3155 | AT-3155 [DC-305A/B] In-situ Duct H2 TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448799 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3156 | AT-3156 [FA-310]: In-situ Duct H2 TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448800 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3157 | AT-3157 [PX-302A/B] Ambient Air H2 TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448801 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3158 | AT-3158 [FA-310]: In-situ Tank H2 TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448802 |  | Open - Ready to Schedule | Preventive maintenance | 0300-AT-3159 | AT-3159 [GB-302A/B] Ambient H2 Detection Motor Level TRANSMITTER | ANNUAL HYDROGEN GAS DETECTOR CALIBRATION (DOWN - COORDINATE) | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448804 |  | Open - Ready to Schedule | Preventive maintenance | 0300-CL-301 | CL-301 SILICA PRECIPITATION THICKENER | Monthly CL-301 Clarifier Lubrication | TMILLS2 | 2026-03-18 14:43 | 2026-04-02 | 300 | No | 1 | 1 | NC-LUBRICATOR
1448805 |  | Open - Ready to Schedule | Preventive maintenance | 0300-CL-301 | CL-301 SILICA PRECIPITATION THICKENER | Monthly CL-301 Clarifier Lubrication | TMILLS2 | 2026-03-18 14:43 | 2026-04-30 | 300 | No | 1 | 1 | NC-LUBRICATOR
1448806 |  | Open - Ready to Schedule | Preventive maintenance | 0300-CL-302 | CL-302 METALS POLISHING THICKENER | Monthly CL-302 Clarifier Lubrication | TMILLS2 | 2026-03-18 14:43 | 2026-04-19 | 300 | No | 1 | 1 | NC-LUBRICATOR
1448807 |  | Open - Ready to Schedule | Preventive maintenance | 0300-CL-303 | CL-303 ZINC PRECIPITATION THICKENER | CL-303 Monthly Clarifier Lubrication | TMILLS2 | 2026-03-18 14:43 | 2026-04-13 | 300 | No | 1 | 1 | NC-LUBRICATOR
1448810 |  | Open - Ready to Schedule | Preventive maintenance | 0300-EER-AREA 300 | Electrical Room Area 300 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 300 | No | 1 | 1 | NC-E/I
1448829 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PC-311 | 0300-PC-311 SCREENED OXIDIC FINES FEED CONVEYOR | SEMI-ANNUAL CAMBELT GEAR REDUCER OIL CHANGE PM | TMILLS2 | 2026-03-18 14:43 | 2026-04-16 | 300 | No | 1 | 1 | NC-MECHANIC EXE
1448835 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-301-A | PX-301A GYPSUM BELT FILTER PACKAGE | MONTHLY BELT FILTER LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:43 | 2026-04-06 | 300 | No | 1 | 1 | NC-LUBRICATOR | CRITICAL
1448840 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-301-B | PX-301B GYPSUM BELT FILTER PACKAGE | MONTHLY BELT FILTER LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:43 | 2026-04-13 | 300 | No | 1 | 1 | NC-LUBRICATOR | CRITICAL
1448845 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-302-A | PX-302A CEMENTATION SOLUTION PRESS FILTER PACKAGE | INSPECT CLASSIFIED ELECTRICAL EQUIPMENT | TMILLS2 | 2026-03-18 14:43 | 2026-04-12 | 300 | No | 1 | 2 | NC-E/I
1448706 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PX-101-A | 0100-PX-101-A FILTER PRESS | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:42 | 2026-04-09 | 100 | No | 1 | 1 | NC-LUBRICATOR
1448711 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PX-101-B | 0100-PX-101-B FILTER PRESS | FILTER PRESS QUARTERLY [D4] | TMILLS2 | 2026-03-18 14:42 | 2026-04-13 | 100 | No | 2 | 4 | NC-MECHANIC EXE | CRITICAL
1448714 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PX-101-B | 0100-PX-101-B FILTER PRESS | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:42 | 2026-04-09 | 100 | No | 1 | 1 | NC-LUBRICATOR
1448719 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PX-183-PRSFLTR | PX-183 PRESS FILTER PACKAGE | PX-183 QUARTERLY LUBRICATION CHECK [D] | TMILLS2 | 2026-03-18 14:42 | 2026-04-02 | 100 | No | 1 | 1 | NC-LUBRICATOR | MAJOR
1431871 |  | Open - Ready to Schedule | Preventive maintenance | 1500 | 1500-BUILDING AND GROUNDS | 6 Month Crane Inspections |  | 2025-12-18 10:39 | 2026-01-08 | 1500 | No | 2 | 2 | NC-CONT-MECH
1431833 |  | Open - Ready to Schedule | Preventive maintenance | 0800-NG-3011 | 0800 NATURAL GAS SERVICE | Area 500 Gas Valve Lubrication/Inspection | SALLEN2 | 2025-12-18 10:39 | 2026-01-27 | 800 | No | 2 | 5 | NC-LUBRICATOR
1448674 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-101-A | CL-101-A L/N Clarifier Thickener | CLARIFIER LUBRICATION [R] | MECH EXE CREW | 2026-03-18 14:42 | 2026-04-27 | 100 | No | 1 | 1 | NC-LUBRICATOR | CRITICAL
1448675 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-101-B | CL-101-B L/N Clarifier Thickener | CLARIFIER LUBRICATION [R] | SWORLEY2 | 2026-03-18 14:42 | 2026-04-27 | 100 | No | 1 | 1 | NC-LUBRICATOR
1448676 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-151-A | 0100-CL-151-A NEUTRAL LEACHING THICKENER | CLARIFIER LUBRICATION [R] | TMILLS2 | 2026-03-18 14:42 | 2026-04-06 | 100 | No | 1 | 1 | NC-LUBRICATOR
1440312 |  | Open - Ready to Schedule | Preventive maintenance | 200 | SOLVENT EXTRACTION, AREA 200 | MONTHLY AREA 0200 VIBRATION ROUTE PM |  | 2026-01-28 14:16 | 2026-03-23 | 200 | No | 1 | 4 | NC-LUBRICATOR
1448677 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-151-B | 0100-CL-151-B NEUTRAL LEACHING THICKENER | CLARIFIER LUBRICATION [R] | TMILLS2 | 2026-03-18 14:42 | 2026-04-06 | 100 | No | 1 | 1 | NC-LUBRICATOR
1448678 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-151-C | 0100-CL-151-C NEUTRAL LEACHING THICKENER | CL-151-C CLARIFIER LUBRICATION [R] | SWORLEY2 | 2026-03-18 14:42 | 2026-04-21 | 100 | No | 1 | 1 | NC-LUBRICATOR | CRITICAL
1448679 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-181 | 0100-CL-181 WOX WASHING THICKENER | CLARIFIER LUBRICATION [R] | TMILLS2 | 2026-03-18 14:42 | 2026-04-27 | 100 | No | 1 | 1 | NC-LUBRICATOR
1448680 |  | Open - Ready to Schedule | Preventive maintenance | 0100-DIT-1102-A | CL-101A ACID LEACH UNDERFLOW DENSITY TRANSMITTER | SEMI-ANNUAL DENSITY TRANSMITTER CALIBRATION [R] |  | 2026-03-18 14:42 | 2026-04-27 | 100 | No | 1 | 1 | NC-E/I
1448681 |  | Open - Ready to Schedule | Preventive maintenance | 0100-EER-AREA 100 | Electrical Room Area 100 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | E/I EXECUTION | 2026-03-18 14:42 | 2026-04-27 | 100 | No | 1 | 1 | NC-E/I
1448697 |  | Open - Ready to Schedule | Preventive maintenance | 0100-GE-101 | GE-101 100 EMERGENCY GENERATOR | Emergency Generator Monthly Maintenance-M/E | TPEACOCK2 | 2026-03-18 14:42 | 2026-04-05 | 100 | No | 1 | 1.5 | NC-MECHANIC EXE | EHS
1448702 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PC-183 | 0100-PC-183 WOX WASHING PRESS FILTER CAKE SCREW CONVEYOR | Screw Conveyor Quarterly PM | TMILLS2 | 2026-03-18 14:42 | 2026-04-13 | 100 | No | 1 | 4 | NC-MECHANIC EXE
1448703 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PX-101-A | 0100-PX-101-A FILTER PRESS | FILTER PRESS QUARTERLY [D4] | TMILLS2 | 2026-03-18 14:42 | 2026-04-06 | 100 | No | 2 | 4 | NC-MECHANIC EXE | CRITICAL
1448665 |  | Open - Ready to Schedule | Preventive maintenance | 100 | Leaching | Weekly Seal Pot Inspection |  | 2026-03-18 14:42 | 2026-04-06 | 100 | No | 1 | 2 | NC-LUBRICATOR
1448667 |  | Open - Ready to Schedule | Preventive maintenance | 100 | Leaching | Weekly Seal Pot Inspection |  | 2026-03-18 14:42 | 2026-04-13 | 100 | No | 1 | 2 | NC-LUBRICATOR
1448669 |  | Open - Ready to Schedule | Preventive maintenance | 100 | Leaching | Weekly Seal Pot Inspection |  | 2026-03-18 14:42 | 2026-04-20 | 100 | No | 1 | 2 | NC-LUBRICATOR
1448671 |  | Open - Ready to Schedule | Preventive maintenance | 100 | Leaching | Weekly Seal Pot Inspection |  | 2026-03-18 14:42 | 2026-04-27 | 100 | No | 1 | 2 | NC-LUBRICATOR
1418463 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GA-700-F-PUMP | WOX SLURRY PREPARATION TANK PUMP GA-700F | 4 WEEK ALBIN PUMP HOSE REPLACEMENT [D] | TMILLS2 | 2025-10-11 13:14 | 2026-04-12 | 700 | No | 2 | 3 | NC-MECHANIC EXE
1418424 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-721 | 0700-GB-721 ROCKWOOD WAELZ OXIDE WET SCRUBBER FAN | SILO MOTOR LUBRICATION [R/D] | TMILLS2 | 2025-10-10 11:31 | 2026-04-10 | 600 | No | 1 | 0.75 | NC-LUBRICATOR | EHS
1448457 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-FB-700-B-BIN | WOX SILO BIN B (4975 FT3, 0) 11'X11' X 35'-3/4" SSH | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | SWORLEY2 | 2026-03-16 17:40 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1442916 |  | Open - Ready to Schedule | Preventive maintenance | 400 | ELECTROWINNING AREA 400 | MONTHLY AREA 0400 VIBRATION ROUTE PM |  | 2026-02-10 14:54 | 2026-04-06 | 400 | No | 1 | 4 | NC-LUBRICATOR
1441447 |  | Open - Ready to Schedule | Preventive maintenance | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | MONTHLY AREA 0300 VIBRATION ROUTE PM |  | 2026-02-05 13:34 | 2026-03-30 | 300 | No | 1 | 4 | NC-LUBRICATOR
1448455 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-721 | BH-721 - ROCKWOOD WAELZ OXIDE STORAGE BIN VENT | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | TMILLS2 | 2026-03-16 17:38 | 2026-04-13 | 600 | No | 1 | 0.8 | NC-PM DAY | EHS
1448456 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-FB-700-A-BIN | WOX SILO BIN A (4975 FT3, 0) 11'X11' X 35'-3/4" SSH | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | SWORLEY2 | 2026-03-16 17:39 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1448458 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-FB-700-C-BIN | WOX SILO BIN C (4975 FT3, 0) 11'X11' X 35'-3/4" SSH | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | SWORLEY2 | 2026-03-16 17:41 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1448459 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-FB-700-D-BIN | WOX SILO BIN D (4975 FT3, 0) 11'X11' X 35'-3/4" SSH | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | SWORLEY2 | 2026-03-16 17:42 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1448451 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501-A-MODULE | MELTING FURNACE BAGHOUSE DUST COLLECTOR, MODULE #1 | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] |  | 2026-03-16 17:33 | 2026-04-14 | 500 | No | 1 | 0.8 | NC-PM DAY | EHS
1448452 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-700 | BH-700 -WOX SILO DUST COLLECTOR | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] |  | 2026-03-16 17:34 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1448453 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | SWORLEY2 | 2026-03-16 17:35 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1448454 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-703 | BH-703 -CALCIUM HYDROXIDE STORAGE BIN VENT (DUST COLLECTOR) | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | TMILLS2 | 2026-03-16 17:37 | 2026-04-15 | 300 | No | 1 | 0.8 | NC-PM DAY | EHS
1448460 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-FB-700-E-BIN | WOX SILO BIN E (4975 FT3, 0) 11'X11' X 35'-3/4" SSH | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | SWORLEY2 | 2026-03-16 17:43 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1448461 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-FB-700-F-BIN | WOX SILO BIN F (4975 FT3, 0) 11'X11' X 35'-3/4" SSH | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] | SWORLEY2 | 2026-03-16 17:44 | 2026-04-13 | 700 | No | 1 | 0.8 | NC-PM DAY | EHS
1433043 |  | Open - Ready to Schedule | Preventive maintenance | 200 | SOLVENT EXTRACTION, AREA 200 | 200 Area Grease Caddy PM - SX 3 |  | 2025-12-23 07:08 | 2026-03-23 | 200 | No | 2 | 4 | NC-LUBRICATOR
1442706 |  | Open - Ready to Schedule | Preventive maintenance | 1600-RESPIRATOR-WASHER | Respirator Washer located in the Lab sample room | Monthly Respirator Washer PM | TWOMACK | 2026-02-09 14:05 | 2026-03-05 | 800 | Yes | 1 | 2 | NC-SAFETY/EMT
1442615 |  | Open - Ready to Schedule | Preventive maintenance | 0800-EER-AREA 800 | Electrical Room Area 800 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TMILLS2 | 2026-02-09 14:05 | 2026-03-27 | 800 | No | 1 | 1 | NC-E/I
1442621 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-A-PUMP | GA-812A FIRE WATER DIESEL PUMP FP-1/FP-B (0) | DIESEL FIRE PUMP INSPECTION CHECKLIST | SALLEN2 | 2026-02-09 14:05 | 2026-03-31 | 800 | No | 2 | 1 | NC-LUBRICATOR
1442619 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-A-ENGINE | GA-812A FIRE WATER DIESEL PUMP FP-1/FP-B DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-02-09 14:05 | 2026-03-23 | 800 | No | 1 | 2 | NC-LUBRICATOR
1442620 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-A-ENGINE | GA-812A FIRE WATER DIESEL PUMP FP-1/FP-B DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-02-09 14:05 | 2026-03-30 | 800 | No | 1 | 2 | NC-LUBRICATOR
1442625 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-B-ENGINE | GA-812B FIRE WATER DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-02-09 14:05 | 2026-03-23 | 800 | No | 1 | 2 | NC-LUBRICATOR
1442626 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-B-ENGINE | GA-812B FIRE WATER DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-02-09 14:05 | 2026-03-30 | 800 | No | 1 | 2 | NC-LUBRICATOR
1442627 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-B-PUMP | GA-812B FIRE WATER DIESEL PUMP FP-1/FP-B (0) | DIESEL FIRE PUMP INSPECTION CHECKLIST | SALLEN2 | 2026-02-09 14:05 | 2026-03-31 | 800 | No | 2 | 1 | NC-LUBRICATOR
1442628 |  | Open - Ready to Schedule | Preventive maintenance | 0800-PFSS | Plant Fire Suppression System | Plant Fire Suppression System Inspection [Semi-Annual and Annual] |  | 2026-02-09 14:05 | 2026-03-31 | 800 | No | 1 | 0.6 | NC-CONT-MECH
1442668 |  | Open - Ready to Schedule | Preventive maintenance | 1400-ME-233 | 1400-ME-233 Godwin HL150m 6" 3126 sb pump at basin | LUBRICATION PM (WEEKLY) | SMCKINNEY | 2026-02-09 14:05 | 2026-03-29 | 800 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1381313 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-703 | BH-703 -CALCIUM HYDROXIDE STORAGE BIN VENT (DUST COLLECTOR) | Annual Baghouse PM [D] | TMILLS2 | 2025-04-21 07:58 | 2026-04-19 | 300 | No | 1 | 3.5 | NC-PM DAY | EHS
1384055 |  | Open - Ready to Schedule | Preventive maintenance | 400 | ELECTROWINNING AREA 400 | HARMONIC FILTER YARD CLEANING |  | 2025-05-07 09:27 | 2026-02-17 | 400 | No | 2 | 6 | NC-CONT-ELEC
1391667 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PSV-3032 | 0300-PSV-3032 FILTERED CEMENTATION SOLUTION HEAT EXCHANGER EA-301 | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2025-06-11 14:07 | 2026-01-20 | 800 | No | 2 | 2 | NC-MECHANIC
1391668 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PSV-3033 | 0300-PSV-3033 FILTERED CEMENTATION SOLUTION HEAT EXCHANGER EA-301 | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2025-06-11 14:07 | 2026-01-20 | 800 | No | 2 | 2 | NC-MECHANIC
1419614 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PX-104-A | PX-104-A -SQUEEZING AIR COMPRESSOR | Boge and Gardner-Denver compressor servicing | BPETERS2 | 2025-10-22 10:40 | 2026-04-22 | 656 | No | 2 | 1 | NC-CONT-MECH
1419615 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PX-104-B | PX-104-B -SQUEEZING AIR COMPRESSOR | Boge and Gardner-Denver compressor servicing | BPETERS2 | 2025-10-22 10:40 | 2026-04-22 | 656 | No | 2 | 1 | NC-CONT-MECH
1419588 |  | Open - Ready to Schedule | Preventive maintenance | 0400-PA-402-CRANE | KUNZ CRANE #2 | BIANNUAL KUNZ CRANE CHECKS [R&D] |  | 2025-10-22 05:38 | 2026-04-22 | 400 | No | 4 | 8 | NC-E/I
1425287 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0400-GV-403-FAN | GV-403 -ACT-3 FAN | ACT Inspection (A.15.a.ii.A) | TPEACOCK2 | 2025-11-14 13:24 | 2026-04-12 | 400 | No | 3 | 4 | NC-MECHANIC EXE | EHS
1425301 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GA-700-B-PUMP | WOX SLURRY PREPARATION TANK PUMP GA-700B | 4 WEEK ALBIN PUMP HOSE REPLACEMENT [D] | TMILLS2 | 2025-11-14 15:27 | 2026-04-17 | 700 | No | 2 | 3 | NC-MECHANIC
1442546 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-721 | BH-721 - ROCKWOOD WAELZ OXIDE STORAGE BIN VENT | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | TMILLS2 | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1442484 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | Weekly WOX (8) Blower Filter Replacements |  | 2026-02-09 14:05 | 2026-03-16 | 700 | No | 1 | 2 | NC-LUBRICATOR
1442485 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | Weekly WOX (8) Blower Filter Replacements |  | 2026-02-09 14:05 | 2026-03-23 | 700 | No | 1 | 2 | NC-LUBRICATOR
1442486 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | Weekly WOX (8) Blower Filter Replacements |  | 2026-02-09 14:05 | 2026-03-30 | 700 | No | 1 | 2 | NC-LUBRICATOR
1442491 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-D-CTRL | BH-701-D BROKEN BAG DETECTOR AT-7200D | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1442493 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-E-CTRL | FB-700E CONTROL AT-7200E | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1442495 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-F-CTRL | BH-701-F BROKEN BAG DETECTOR AT-7200F | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1442518 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-D | WOX SILO BIN D VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1442497 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-G-CTRL | BH-701-G LIMESTONE SILO BROKEN BAG DETECTOR AT-7200G | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] |  | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1442503 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-A | WOX SILO BIN A VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1442508 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-B | WOX SILO BIN B VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1442513 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-C | WOX SILO BIN C VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1442523 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-E | WOX SILO BIN E VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1444517 |  | Open - Ready to Schedule | Preventive maintenance | 500 | MELTING / CASTING, AREA 500 | MONTHLY AREA 0500 VIBRATION ROUTE PM |  | 2026-02-19 15:24 | 2026-04-13 | 500 | No | 1 | 4 | NC-LUBRICATOR
1442532 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-F | WOX SILO BIN F VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1442538 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | SWORLEY2 | 2026-02-09 14:05 | 2026-03-29 | 700 | No | 1 | 1 | NC-E/I | EHS
1442540 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-703 | BH-703 -CALCIUM HYDROXIDE STORAGE BIN VENT (DUST COLLECTOR) | Monthly Silo Filter Vent PM [D] | TMILLS2 | 2026-02-09 14:05 | 2026-03-29 | 300 | No | 1 | 1 | NC-PM DAY | EHS
1446238 |  | Open - Ready to Schedule | Preventive maintenance | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | BREAKER, TRANS., & MCC INSPECTION (OUTAGE) |  | 2026-03-03 13:28 | 2026-04-07 | 1100 | No | 1 | 10 | NC-CONT-ELEC
1391578 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PSV-2149 | 0200-PSV-2149 DEMIN WATER HEAT EXCHANGER EA-201 | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2025-06-11 14:07 | 2026-01-20 | 800 | No | 2 | 2 | NC-MECHANIC
1391579 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PSV-2163A | 0200-PSV-2163A COOLING WATER TO HCL CONDENSER EA-202A | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2025-06-11 14:07 | 2026-01-20 | 800 | No | 2 | 2 | NC-MECHANIC
1391580 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PSV-2163B | 0200-PSV-2163B COOLING WATER TO HCL CONDENSER EA-202A | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2025-06-11 14:07 | 2026-01-12 | 800 | No | 2 | 2 | NC-MECHANIC
1391581 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PSV-2164A | 0200-PSV-2164A COOLING WATER TO HCL CONDENSER EA-202B | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2025-06-11 14:07 | 2026-01-12 | 800 | No | 2 | 2 | NC-MECHANIC
1391582 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PSV-2164B | 0200-PSV-2164B COOLING WATER TO HCL CONDENSER EA-202B | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2025-06-11 14:07 | 2026-01-12 | 800 | No | 2 | 2 | NC-MECHANIC
1391478 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PSV-1026 | 0100-PSV-1026 PLS HEAT EXCHANGER EA-101B | ANNUAL CERTIFICATION OF PSVs | TMILLS2 | 2025-06-11 14:07 | 2026-01-20 | 800 | No | 2 | 2 | NC-MECHANIC
1391476 |  | Open - Ready to Schedule | Preventive maintenance | 0100-PSV-1024 | 0100-PSV-1024 PLS HEAT EXCHANGER EA-101A | ANNUAL CERTIFICATION OF PSVs | TMILLS2 | 2025-06-11 14:07 | 2026-01-20 | 800 | No | 2 | 2 | NC-MECHANIC
1378310 |  | Open - Ready to Schedule | Preventive maintenance | 0200-DC-201-A | 0200-DC-201-A HCL RECOVERY REACTOR | TEST TEMPERATURES AND LEVELS SIS SYSTEM DC-201 | TMILLS2 | 2025-04-06 16:55 | 2026-04-01 | 200 | No | 2 | 2 | NC-E/I
1423693 | 2-Urgent/Scheduled | Open - Ready to Schedule | Preventive maintenance | 400 | ELECTROWINNING AREA 400 | HARMONIC FILTER YARD WEED CONTROL |  | 2025-11-05 10:12 | 2026-04-06 | 400 | No | 2 | 3 | NC-CONT-MECH
1438230 |  | Open - Ready to Schedule | Preventive maintenance | 1100 | BUILDINGS AND WAREHOUSES, AREA 1100 | ANNUAL TRANSFORMER THERMOGRAPHY CHECK |  | 2026-01-21 20:00 | 2026-07-06 | 1100 | No | 1 | 0.5 | NC-CONT-ELEC
1442410 |  | Open - Ready to Schedule | Preventive maintenance | 0500-EER-AREA 500 | Electrical Room Area 500 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TPEACOCK2 | 2026-02-09 14:05 | 2026-03-27 | 500 | No | 1 | 1 | NC-E/I
1439560 |  | Open - Ready to Schedule | Preventive maintenance | 400 | ELECTROWINNING AREA 400 | 400/500 Area Grease Caddy PM |  | 2026-01-27 15:03 | 2026-04-27 | 400 | No | 2 | 4 | NC-LUBRICATOR
1442399 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-503 | CA-503 -SLAB CASTING MACHINE LINE #3 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-02-09 14:04 | 2026-03-30 | 500 | No | 1 | 2 | NC-MECHANIC
1442441 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-502 | Fromm Banding Machine | Weekly sealer mechanism cleaning | LOWER PM CREW | 2026-02-09 14:05 | 2026-03-25 | 500 | No | 1 | 2.5 | NC-PM NIGHT
1442460 |  | Open - Ready to Schedule | Preventive maintenance | 0600-AT-6042-A | DC-612A: Ambient Air H2S Detection | SEMI-ANNUAL HYDROGEN SULFIDE GAS DETECTOR [R/D] CALIBRATION | SWORLEY2 | 2026-02-09 14:05 | 2026-03-23 | 600 | No | 1 | 0.75 | NC-E/I
1442420 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | WEEKLY AREA 500 BAGHOUSE DUST COLLECTOR MAINTENANCE | LOWER PM CREW | 2026-02-09 14:05 | 2026-03-29 | 500 | No | 1 | 2.5 | NC-PM DAY | EHS
1442421 |  | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | DAILY BAGHOUSE INSPECTION | LOWER PM CREW | 2026-02-09 14:05 | 2026-03-29 | 500 | No | 1 | 5.25 | NC-PM DAY | EHS
1442432 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PC-503 | Slab Casting Transfer Cart/Walking Beam Conveyor | Walking Beam and Transfer cart Maintenance [D] |  | 2026-02-09 14:05 | 2026-03-30 | 500 | No | 1 | 0.5 | NC-MECHANIC
1442322 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | MONTHLY CSM BEARING GREASING [D] |  | 2026-02-09 14:04 | 2026-03-31 | 400 | No | 1 | 1 | NC-MECHANIC
1442327 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-CATHBRUSH | CA-401 Stripping machine Cathode Brush System | CSM BRUSHING ELEVATOR PM |  | 2026-02-09 14:04 | 2026-03-31 | 400 | No | 2 | 4 | NC-MECHANIC
1442317 | 2-Urgent/Scheduled | Open - Ready to Schedule | Preventive maintenance | 0400-110KVAC-XFMR-UNIT2-MCB1 | 110KVAC TRANSFORMER RECTIFIER UNIT 2 MAIN CIRCUIT BREAKER | Monthly 100KV Breakers |  | 2026-02-09 14:04 | 2026-04-07 | 400 | No | 1 | 1 | NC-E/I
1442321 | 2-Urgent/Scheduled | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-HPU | ROW#1 MACHINE HYDRAULIC UNIT | CSM 1 HYDRAULIC CLAMP CHECK |  | 2026-02-09 14:04 | 2026-03-31 | 400 | No | 1 | 3 | NC-MECHANIC
1442336 | 3-First Opportunity | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-HPU | ROW#2 MACHINE HYDRAULIC UNIT | CSM 2 HYDRAULIC CLAMP CHECK |  | 2026-02-09 14:04 | 2026-03-24 | 400 | No | 1 | 3 | NC-PM NIGHT
1442332 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-STACKER | CA-401 Stripping Machine Stacker | CSM STACKER AND ROLLER TABLE PM |  | 2026-02-09 14:04 | 2026-03-30 | 400 | No | 2 | 4 | NC-MECHANIC
1442337 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | MONTHLY CSM BEARING GREASING [D] |  | 2026-02-09 14:04 | 2026-03-31 | 400 | No | 1 | 1 | NC-PM NIGHT
1442345 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-STACKER | CA-402 Stripping Machine Stacker | CSM STACKER AND ROLLER TABLE PM |  | 2026-02-09 14:04 | 2026-03-23 | 400 | No | 2 | 4 | NC-PM NIGHT
1442339 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | BIWEEKLY CSM INLET OUTLET MECHANICAL CHECK |  | 2026-02-09 14:04 | 2026-03-26 | 400 | No | 1 | 2 | NC-PM NIGHT
1442341 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-CATHBRUSH | CA-402 Stripping Machine Cathode Brush System | CSM BRUSHING ELEVATOR PM |  | 2026-02-09 14:04 | 2026-03-25 | 400 | No | 2 | 4 | NC-PM NIGHT
1442343 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-HKNIFE | CA-402 Stripping Machine Horizontal Knife | Horizontal Knife Replacement [D] | LOWER PM CREW | 2026-02-09 14:04 | 2026-03-27 | 400 | No | 2 | 2 | NC-PM NIGHT
1442347 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-TRANSCART | CA-402 Stripping Machine Transfer Cart | CSM 2 BIWEEKLY TRANSFER CART GREASING |  | 2026-02-09 14:04 | 2026-03-26 | 400 | No | 1 | 1 | NC-PM NIGHT
1442348 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-403-ANWAGON | ANODE WAGON | ENERGY CHAIN INSPECTION |  | 2026-02-09 14:04 | 2026-03-27 | 400 | No | 1 | 1 | NC-E/I
1442367 |  | Open - Ready to Schedule | Preventive maintenance | 500 | MELTING / CASTING, AREA 500 | AREA 0500 QUARTERLY OIL SAMPLE ANALYSIS |  | 2026-02-09 14:04 | 2026-03-30 | 500 | No | 1 | 1 | NC-LUBRICATOR
1442366 |  | Open - Ready to Schedule | Preventive maintenance | 0400-PA-404-CRANE | PA-404 -AUXILIARY CRANE #2 | ENERGY CHAIN INSPECTION |  | 2026-02-09 14:04 | 2026-03-20 | 400 | No | 1 | 1 | NC-E/I
1442388 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-02-09 14:04 | 2026-03-30 | 500 | No | 1 | 2 | NC-MECHANIC
1442393 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-502 | CA-502 -SLAB CASTING MACHINE LINE #2 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-02-09 14:04 | 2026-03-30 | 500 | No | 1 | 2 | NC-MECHANIC
1442394 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-503 | CA-503 -SLAB CASTING MACHINE LINE #3 | SLAB LINE PM (D) |  | 2026-02-09 14:04 | 2026-03-31 | 500 | No | 2 | 3.5 | NC-MECHANIC
1448069 |  | Open - Ready to Schedule | Preventive maintenance | 0400-GA-453-PUMP | 0400-GA-453-EW SLUDGE PUMP | BREDEL 65 PUMP HOSE REPLACEMENT [D] | TPEACOCK2 | 2026-03-12 13:44 | 2026-05-08 | 400 | No | 2 | 2 | NC-MECHANIC EXE
1448084 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0800-VLV-ENERGYDISSIP | River Energy Dissipator Valve | River Basin Valve Checks | SALLEN2 | 2026-03-12 15:07 | 2026-04-07 | 800 | No | 1 | 0.68 | NC-LUBRICATOR | EHS
1446098 |  | Open - Ready to Schedule | Preventive maintenance | 600 | PLINT, AREA 600 | MONTHLY AREA 0600 VIBRATION ROUTE PM |  | 2026-02-27 15:31 | 2026-04-20 | 600 | No | 1 | 4 | NC-LUBRICATOR
1433859 |  | Open - Ready to Schedule | Preventive maintenance | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | 300 Area Grease Caddy PM - Bleed 1 |  | 2025-12-29 12:40 | 2026-03-30 | 300 | No | 2 | 4 | NC-LUBRICATOR
1419320 |  | Open - Ready to Schedule | Preventive maintenance | 0800-PX-806-B | 0800-PX-806-B COMPRESSOR NO. 2 | Kaeser Compressor Servicing | SALLEN2 | 2025-10-16 12:09 | 2026-04-16 | 656 | No | 2 | 0.5 | NC-CONT-MECH
1419321 |  | Open - Ready to Schedule | Preventive maintenance | 0800-PX-806-C | 0800-PX-806-C COMPRESSOR NO. 3 | Kaeser Compressor Servicing | SALLEN2 | 2025-10-16 12:09 | 2026-04-16 | 656 | No | 2 | 0.5 | NC-CONT-MECH
1419322 |  | Open - Ready to Schedule | Preventive maintenance | 0800-PX-806-D | 0800-PX-806-D COMPRESSOR NO. 4 | Kaeser Compressor Servicing | SALLEN2 | 2025-10-16 12:09 | 2026-04-16 | 656 | No | 2 | 0.5 | NC-CONT-MECH
1442252 |  | Open - Ready to Schedule | Preventive maintenance | 0300-EER-AREA 300 | Electrical Room Area 300 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TMILLS2 | 2026-02-09 14:04 | 2026-03-27 | 300 | No | 1 | 1 | NC-E/I
1442260 |  | Open - Ready to Schedule | Preventive maintenance | 0300-GA-306-A-PUMP | GA-306A METALS POLISHING UNDERFLOW PUMP (110 GPM @ 55' TDH, 5 HP) | QUARTERLY PUMP INSPECTION [R/D] | ELUSTER2 | 2026-02-09 14:04 | 2026-03-29 | 300 | No | 1 | 0.25 | NC-PM DAY
1442261 |  | Open - Ready to Schedule | Preventive maintenance | 0300-GA-306-B-PUMP | GA-306B METALS POLISHING UNDERFLOW PUMP (110 GPM @ 55' TDH, 5 HP) | QUARTERLY PUMP INSPECTION [R/D] | ELUSTER2 | 2026-02-09 14:04 | 2026-03-29 | 300 | No | 1 | 0.25 | NC-PM DAY
1442287 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-302-A | PX-302A CEMENTATION SOLUTION PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-02-09 14:04 | 2026-03-31 | 300 | No | 1 | 1 | NC-LUBRICATOR
1442292 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-302-B | PX-302B CEMENTATION SOLUTION PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-02-09 14:04 | 2026-03-31 | 300 | No | 1 | 1 | NC-LUBRICATOR
1442218 |  | Open - Ready to Schedule | Preventive maintenance | 0200-EER-AREA 200 | Electrical Room Area 200 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TMILLS2 | 2026-02-09 14:04 | 2026-03-27 | 200 | No | 1 | 1 | NC-E/I
1442221 |  | Open - Ready to Schedule | Preventive maintenance | 0200-HEATTRACE-Z2 | AREA 200 HEAT TRACE CONTROL PANEL ZONE 2 | Weekly Heat Trace Panel Inspection [R] | TMILLS2 | 2026-02-09 14:04 | 2026-03-29 | 200 | No | 1 | 0.5 | NC-E/I | CRITICAL
1442222 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PC-201 | 0200-PC-201 CRUD TREATMENT PRECOAT SCREW CONVEYOR | Screw Conveyor Quarterly PM | TMILLS2 | 2026-02-09 14:04 | 2026-03-30 | 200 | No | 1 | 4 | NC-MECHANIC
1435191 |  | Open - Ready to Schedule | Preventive maintenance | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | 300 Area Grease Caddy PM - Bleed 2 |  | 2026-01-06 13:15 | 2026-04-06 | 300 | No | 4 | 2 | NC-LUBRICATOR
1437921 |  | Open - Ready to Schedule | Preventive maintenance | 0400-110KVAC-XFMR-UNIT1 | 110KVAC TRANSFORMER RECTIFIER UNIT 1 | Yearly Rectifier Inspection |  | 2026-01-21 19:59 | 2026-03-10 | 400 | No | 2 | 4 | NC-E/I
1437923 |  | Open - Ready to Schedule | Preventive maintenance | 0400-110KVAC-XFMR-UNIT1-XFMR1 | 110KVAC TRANSFORMER RECTIFIER UNIT 1 XFMR 1 | YEARLY TRANSFORMER INSPECTION (D) |  | 2026-01-21 19:59 | 2026-03-10 | 400 | No | 1 | 2 | NC-E/I
1437924 |  | Open - Ready to Schedule | Preventive maintenance | 0400-110KVAC-XFMR-UNIT2 | 110KVAC TRANSFORMER RECTIFIER UNIT 2 | Yearly Rectifier Inspection |  | 2026-01-21 19:59 | 2026-02-07 | 400 | No | 2 | 4 | NC-E/I
1437926 |  | Open - Ready to Schedule | Preventive maintenance | 0400-110KVAC-XFMR-UNIT2-XFMR1 | 110KVAC TRANSFORMER RECTIFIER UNIT 2 XFMR 1 | YEARLY TRANSFORMER INSPECTION (D) |  | 2026-01-21 19:59 | 2026-03-03 | 400 | No | 1 | 2 | NC-E/I
1437844 |  | Open - Ready to Schedule | Preventive maintenance | 0200-PSV-2150 | 0200-PSV-2150 DEMIN WATER HEAT EXCHANGER EA-201 | ANNUAL CERTIFICATION OF PSVs | SWORLEY2 | 2026-01-21 19:59 | 2026-03-13 | 800 | No | 2 | 2 | NC-MECHANIC
1442158 |  | Open - Ready to Schedule | Preventive maintenance | 200 | SOLVENT EXTRACTION, AREA 200 | AREA 0200 QUARTERLY OIL SAMPLE ANALYSIS [R] |  | 2026-02-09 14:04 | 2026-03-23 | 200 | No | 1 | 5 | NC-LUBRICATOR
1442094 |  | Open - Ready to Schedule | Preventive maintenance | 100 | Leaching | Weekly Seal Pot Inspection |  | 2026-02-09 14:04 | 2026-03-23 | 100 | No | 1 | 2 | NC-LUBRICATOR
1442096 |  | Open - Ready to Schedule | Preventive maintenance | 100 | Leaching | Weekly Seal Pot Inspection |  | 2026-02-09 14:04 | 2026-03-30 | 100 | No | 1 | 2 | NC-LUBRICATOR
1442097 |  | Open - Ready to Schedule | Preventive maintenance | 0100-4160VAC-SWGR | AREA 0100 ELECTRICAL ROOM 4160VAC SWITCHGEAR | ANNUAL 4160V SWITCHGEAR INSPECTION | E/I EXECUTION | 2026-02-09 14:04 | 2026-04-07 | 100 | No | 2 | 5 | NC-CONT-ELEC
1442101 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-101-B | CL-101-B L/N Clarifier Thickener | CLARIFIER LUBRICATION [R] | SWORLEY2 | 2026-02-09 14:04 | 2026-03-27 | 100 | No | 1 | 1 | NC-LUBRICATOR
1442104 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-151-C | 0100-CL-151-C NEUTRAL LEACHING THICKENER | CL-151-C CLARIFIER LUBRICATION [R] | SWORLEY2 | 2026-02-09 14:04 | 2026-03-24 | 100 | No | 1 | 1 | NC-LUBRICATOR | CRITICAL
1442105 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-181 | 0100-CL-181 WOX WASHING THICKENER | CLARIFIER LUBRICATION [R] | TMILLS2 | 2026-02-09 14:04 | 2026-03-27 | 100 | No | 1 | 1 | NC-LUBRICATOR
1442107 |  | Open - Ready to Schedule | Preventive maintenance | 0100-EER-AREA 100 | Electrical Room Area 100 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | E/I EXECUTION | 2026-02-09 14:04 | 2026-03-27 | 100 | No | 1 | 1 | NC-E/I
1442100 |  | Open - Ready to Schedule | Preventive maintenance | 0100-CL-101-A | CL-101-A L/N Clarifier Thickener | CLARIFIER LUBRICATION [R] | MECH EXE CREW | 2026-02-09 14:04 | 2026-03-27 | 100 | No | 1 | 1 | NC-LUBRICATOR | CRITICAL
1436384 |  | Open - Ready to Schedule | Preventive maintenance | 300 | RAFFINATE BLEED TREATMENT THROUGH DISCHARGE, AREA 300 | 300 Area Grease Caddy PM - Bleed 3 |  | 2026-01-12 13:58 | 2026-04-13 | 300 | No | 2 | 4 | NC-LUBRICATOR
1434914 |  | Open - Ready to Schedule | Preventive maintenance | 0100-GA-110-B-PUMP | GA-110B WOX FEED PREPARATION SUMP PUMP (650 GPM @ 61' TDH, 20 HP) | CLEANING OF GA-110-B PUMP | UPPER PM CREW | 2026-01-02 10:13 | 2026-02-02 | 100 | No | 2 | 4 | NC-MECHANIC
1434915 |  | Open - Ready to Schedule | Preventive maintenance | 0100-GA-110-A-PUMP | GA-110A WOX FEED PREPARATION SUMP PUMP (650 GPM @ 61' TDH, 20 HP) | CLEANING OF GA-110-A PUMP | UPPER PM CREW | 2026-01-02 10:14 | 2026-02-02 | 100 | No | 2 | 4 | NC-MECHANIC
1436326 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-E | WOX SILO BIN E VENT (1039 FT2 FILTER AREA, 0) | BAGHOUSE CLEAN AND INSPECT [D] |  | 2026-01-11 17:28 | 2026-04-12 | 700 | No | 2 | 2 | NC-MECHANIC EXE | EHS
1434992 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-D | WOX SILO BIN D VENT (1039 FT2 FILTER AREA, 0) | BAGHOUSE CLEAN AND INSPECT [D] | TMILLS2 | 2026-01-04 18:21 | 2026-04-05 | 700 | No | 2 | 2 | NC-MECHANIC EXE | EHS
1434993 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-B | WOX SILO BIN B VENT (1039 FT2 FILTER AREA, 0) | BAGHOUSE CLEAN AND INSPECT [D] | TMILLS2 | 2026-01-04 18:26 | 2026-04-05 | 700 | No | 2 | 2 | NC-MECHANIC EXE | EHS
1447371 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | STANCO DUST COLLECTOR MAINTENANCE [R] | SWORLEY2 | 2026-03-08 16:54 | 2026-04-05 | 700 | No | 1 | 0.5 | NC-PM DAY | EHS
1447569 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0800-VLV-OUTFALL | River basin outfall Valve | River Basin Valve Checks | SALLEN2 | 2026-03-11 15:12 | 2026-04-13 | 800 | No | 1 | 0.68 | NC-LUBRICATOR | EHS
1447303 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | MONTHLY AREA 0700 VIBRATION ROUTE PM |  | 2026-03-06 14:10 | 2026-04-27 | 700 | No | 1 | 4 | NC-LUBRICATOR
1449332 |  | Open - Ready to Schedule | Preventive maintenance | M-1600-001-005 | FIRE EXTINGUISHERS | Admin Building Fire Extinguisher PM | SWORLEY2 | 2026-03-18 14:43 | 2026-04-10 | 200 | No | 1 | 2 | NC-LUBRICATOR
1449233 |  | Open - Ready to Schedule | Preventive maintenance | 1600-RESPIRATOR-WASHER | Respirator Washer located in the Lab sample room | Monthly Respirator Washer PM | TWOMACK | 2026-03-18 14:43 | 2026-04-05 | 800 | Yes | 1 | 2 | NC-SAFETY/EMT
1449159 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-B-ENGINE | GA-812B FIRE WATER DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-06 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449156 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-A-ENGINE | GA-812A FIRE WATER DIESEL PUMP FP-1/FP-B DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-13 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449153 |  | Open - Ready to Schedule | Preventive maintenance | 0800-DCS | 0800-Distributed Control System | Distributed Control System Electrical Maintenance |  | 2026-03-18 14:43 | 2026-04-04 | 200 | No | 1 | 0 | NC-CONT-ELEC
1449154 |  | Open - Ready to Schedule | Preventive maintenance | 0800-EER-AREA 800 | Electrical Room Area 800 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 800 | No | 1 | 1 | NC-E/I
1449155 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-A-ENGINE | GA-812A FIRE WATER DIESEL PUMP FP-1/FP-B DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-06 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449157 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-A-ENGINE | GA-812A FIRE WATER DIESEL PUMP FP-1/FP-B DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-20 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449158 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-A-ENGINE | GA-812A FIRE WATER DIESEL PUMP FP-1/FP-B DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-27 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449160 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-B-ENGINE | GA-812B FIRE WATER DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-13 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449161 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-B-ENGINE | GA-812B FIRE WATER DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-20 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449165 |  | Open - Ready to Schedule | Preventive maintenance | 0900-FD-900-1-FILTER | 900 BUILDING ZINC-B-GONE FILTER UNIT - WEST | MONTHLY ZINC-B-GONE INSPECTION PM [D] |  | 2026-03-18 14:43 | 2026-04-05 | 800 | No | 1 | 2 | NC-LUBRICATOR | EHS
1449162 |  | Open - Ready to Schedule | Preventive maintenance | 0800-GA-812-B-ENGINE | GA-812B FIRE WATER DIESEL ENGINE | WEEKLY FIRE SYSTEM MAINTENANCE | SALLEN2 | 2026-03-18 14:43 | 2026-04-27 | 800 | No | 1 | 2 | NC-LUBRICATOR
1449163 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0900-BH-901 | BH-901 -BAGHOUSE | BAGHOUSE CHECK [D] | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-15 | 900 | No | 1 | 1 | NC-MECHANIC EXE | EHS
1449164 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0900-BH-901 | BH-901 -BAGHOUSE | MONTHLY BAGHOUSE LUBRICATION |  | 2026-03-18 14:43 | 2026-04-05 | 900 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1449166 |  | Open - Ready to Schedule | Preventive maintenance | 0900-FD-900-2-FILTER | 900 BUILDING ZINC-B-GONE FILTER UNIT - EAST | MONTHLY ZINC-B-GONE INSPECTION PM [D] |  | 2026-03-18 14:43 | 2026-04-05 | 800 | No | 1 | 2 | NC-LUBRICATOR | EHS
1449177 |  | Open - Ready to Schedule | Preventive maintenance | 1100-RES-1000 | AREA 1100 EQUIPMENT | Monthly Chain Hoist/Chain Fall Inspection |  | 2026-03-18 14:43 | 2026-04-06 | 1100 | No | 1 | 1 | NC-PM DAY
1449193 |  | Open - Ready to Schedule | Preventive maintenance | 1400-ME-233 | 1400-ME-233 Godwin HL150m 6" 3126 sb pump at basin | GREASE CADDY LUBRICATION PM (Bi -weekly) | SMCKINNEY | 2026-03-18 14:43 | 2026-04-05 | 800 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1449194 |  | Open - Ready to Schedule | Preventive maintenance | 1400-ME-233 | 1400-ME-233 Godwin HL150m 6" 3126 sb pump at basin | GREASE CADDY LUBRICATION PM (Bi -weekly) | SMCKINNEY | 2026-03-18 14:43 | 2026-04-19 | 800 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1449195 |  | Open - Ready to Schedule | Preventive maintenance | 1400-ME-233 | 1400-ME-233 Godwin HL150m 6" 3126 sb pump at basin | LUBRICATION PM (WEEKLY) | SMCKINNEY | 2026-03-18 14:43 | 2026-04-05 | 800 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1449196 |  | Open - Ready to Schedule | Preventive maintenance | 1400-ME-233 | 1400-ME-233 Godwin HL150m 6" 3126 sb pump at basin | LUBRICATION PM (WEEKLY) | SMCKINNEY | 2026-03-18 14:43 | 2026-04-12 | 800 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1449197 |  | Open - Ready to Schedule | Preventive maintenance | 1400-ME-233 | 1400-ME-233 Godwin HL150m 6" 3126 sb pump at basin | LUBRICATION PM (WEEKLY) | SMCKINNEY | 2026-03-18 14:43 | 2026-04-19 | 800 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1449198 |  | Open - Ready to Schedule | Preventive maintenance | 1400-ME-233 | 1400-ME-233 Godwin HL150m 6" 3126 sb pump at basin | LUBRICATION PM (WEEKLY) | SMCKINNEY | 2026-03-18 14:43 | 2026-04-26 | 800 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1447292 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501-C-MODULE | MELTING FURNACE BAGHOUSE DUST COLLECTOR, MODULE #1 | Monthly Visual Baghouse Inspection (A.12.a.ii.C) [D] |  | 2026-03-06 12:40 | 2026-03-29 | 500 | No | 1 | 0.8 | NC-PM DAY | EHS
1449071 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449073 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1449069 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | BAGHOUSE CHECK [D] | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-15 | 700 | No | 1 | 1 | NC-MECHANIC EXE | EHS
1449070 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449072 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-702 | BH-702 Lime Silo Dust Collector | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449074 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-703 | BH-703 -CALCIUM HYDROXIDE STORAGE BIN VENT (DUST COLLECTOR) | Monthly Silo Filter Vent PM [D] | TMILLS2 | 2026-03-18 14:43 | 2026-04-26 | 300 | No | 1 | 1 | NC-MECHANIC EXE | EHS
1449075 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0700-BH-721 | BH-721 - ROCKWOOD WAELZ OXIDE STORAGE BIN VENT | Silo Filter Cartridge Inspection [R/D] | TMILLS2 | 2026-03-18 14:43 | 2026-04-05 | 600 | No | 1 | 1 | NC-PM DAY | EHS
1449076 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-721 | BH-721 - ROCKWOOD WAELZ OXIDE STORAGE BIN VENT | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | TMILLS2 | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449077 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-721 | BH-721 - ROCKWOOD WAELZ OXIDE STORAGE BIN VENT | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | TMILLS2 | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449078 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-721 | BH-721 - ROCKWOOD WAELZ OXIDE STORAGE BIN VENT | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | TMILLS2 | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449144 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PX-702 | 0700-PX-702 MILK OF LIMESTONE PREPARATION PACKAGE | ROLLER CHAIN MOTOR SPROCKET LUBE [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-06 | 700 | No | 1 | 1.66 | NC-LUBRICATOR
1449150 |  | Open - Ready to Schedule | Preventive maintenance | 800 | LAND, UTILITIES, ROADS, PARKING LOTS, FENCES, STORMWATER SYSTEMS, AREA 800 | Fire Pump Meter PM | SALLEN2 | 2026-03-18 14:43 | 2026-04-17 | 800 | No | 1 | 0.5 | NC-LUBRICATOR
1449079 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-721 | BH-721 - ROCKWOOD WAELZ OXIDE STORAGE BIN VENT | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] | TMILLS2 | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1449095 |  | Open - Ready to Schedule | Preventive maintenance | 0700-FD-700-1-FILTER | WOX UNLOADING ZINC-B-GONE FILTER UNIT - WEST | MONTHLY ZINC-B-GONE INSPECTION PM [D] |  | 2026-03-18 14:43 | 2026-04-05 | 800 | No | 1 | 2 | NC-LUBRICATOR | EHS
1449096 |  | Open - Ready to Schedule | Preventive maintenance | 0700-FD-700-2-FILTER | WOX UNLOADING ZINC-B-GONE FILTER UNIT - EAST | MONTHLY ZINC-B-GONE INSPECTION PM [D] |  | 2026-03-18 14:43 | 2026-04-05 | 800 | No | 1 | 2 | NC-LUBRICATOR | EHS
1449097 |  | Open - Ready to Schedule | Preventive maintenance | 0700-FF-725-BIN | FF-725 -SODIUM SULFIDE CONVEYOR | Sodium sulfate screw conveyor motor and gear box |  | 2026-03-18 14:43 | 2026-04-16 | 100 | No | 1 | 0.5 | NC-MECHANIC EXE
1449098 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-A | GB-700-A WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-20 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449101 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-B | GB-700-B WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-20 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449104 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-C | GB-700-C WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-20 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449107 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-D | GB-700-D WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-20 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449110 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-E | GB-700-E WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-23 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449113 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-F | GB-700-F WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-23 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449116 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-G | GB-700-G WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-23 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449119 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GB-700-H | GB-700-H WOX BLOWER | BI MONTHLY BLOWER OIL CHANGE [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-23 | 700 | No | 2 | 1 | NC-LUBRICATOR
1449123 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GK-700-0-CTRL | GK-700 WOX SILO BUILDING DUST COLLECTOR DISCHARGE ROTARY VALVE (1 HP) | Monthly Rotary Valve Operability Check and Inspection [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-PM DAY | EHS
1449124 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GK-702-VALVE | GK-702 -LIMESTONE ROTARY VALVE | Monthly Rotary Valve Operability Check and Inspection [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-PM DAY | EHS
1449125 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GK-702-VALVE | GK-702 -LIMESTONE ROTARY VALVE | MONTHLY ROTARY VALVE LUBRICATION PM [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 0.5 | NC-LUBRICATOR
1449126 |  | Open - Ready to Schedule | Preventive maintenance | 0700-GK-721-B-VALVE | GK-721-B -ROCKWOOD WAELZ OXIDE ROTARY VALVE | Monthly Rotary Valve Operability Check and Inspection [R] | TMILLS2 | 2026-03-18 14:43 | 2026-04-05 | 600 | No | 1 | 1 | NC-PM DAY | EHS
1449131 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-700-A-CONVEYOR | WOX SILO BIN A SCREW FEEDER (14" DIAMETER, 1006 CFH, 40 HP) | Screw Conveyor Quarterly PM | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 4 | NC-MECHANIC EXE
1449132 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-700-B-CONVEYOR | WOX SILO BIN B SCREW FEEDER (14" DIAMETER, 1006 CFH, 40 HP) | Screw Conveyor Quarterly PM | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 4 | NC-MECHANIC EXE
1449133 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-700-C-CONVEYOR | WOX SILO BIN C SCREW FEEDER (14" DIAMETER, 1006 CFH, 40 HP) | Screw Conveyor Quarterly PM | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 4 | NC-MECHANIC EXE
1449137 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-701-0-CONVEYOR | WOX WEIGH FEEDER BELT CONVEYOR (28 STPH, 2 HP) | CONVEYOR INSPECTION [D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-28 | 700 | No | 1 | 1 | NC-MECHANIC EXE
1449134 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-700-D-CONVEYOR | WOX SILO BIN D SCREW FEEDER (14" DIAMETER, 1006 CFH, 40 HP) | Screw Conveyor Quarterly PM | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 4 | NC-MECHANIC EXE
1449135 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-700-E-CONVEYOR | WOX SILO BIN E SCREW FEEDER (14" DIAMETER, 1006 CFH, 40 HP) | Screw Conveyor Quarterly PM | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 4 | NC-MECHANIC EXE
1449136 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-700-F-CONVEYOR | WOX SILO BIN F SCREW FEEDER (14" DIAMETER, 1006 CFH, 40 HP) | Screw Conveyor Quarterly PM | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 4 | NC-MECHANIC EXE
1449138 |  | Open - Ready to Schedule | Preventive maintenance | 0700-PC-701-0-CONVEYOR | WOX WEIGH FEEDER BELT CONVEYOR (28 STPH, 2 HP) | Monthly Weigh Belt Feeder Lubrication [D] | TMILLS2 | 2026-03-18 14:43 | 2026-04-06 | 700 | No | 2 | 2 | NC-LUBRICATOR
1449006 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-502 | Fromm Banding Machine | Weekly sealer mechanism cleaning | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-29 | 500 | No | 1 | 2.5 | NC-PM DAY
1449007 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-503-A | CATHODE CHARGING LANE #1 | QUARTERLY FURNACE CHARGING SYSTEM MAINTENANCE |  | 2026-03-18 14:43 | 2026-04-13 | 500 | No | 4 | 8 | NC-MECHANIC EXE
1449004 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-502 | Fromm Banding Machine | Weekly sealer mechanism cleaning | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-15 | 500 | No | 1 | 2.5 | NC-PM DAY
1449005 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-502 | Fromm Banding Machine | Weekly sealer mechanism cleaning | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-22 | 500 | No | 1 | 2.5 | NC-PM DAY
1449009 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-503-B | CATHODE CHARGING LANE #2 | QUARTERLY FURNACE CHARGING SYSTEM MAINTENANCE |  | 2026-03-18 14:43 | 2026-04-20 | 500 | No | 4 | 8 | NC-MECHANIC EXE
1449016 |  | Open - Ready to Schedule | Preventive maintenance | 0600-AT-6041-A | DC-612A: Ambient Air CO2 Detection | SEMI-ANNUAL CARBON DIOXIDE GAS DETECTOR CALIBRATION [R/D] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-13 | 600 | No | 1 | 0.5 | NC-E/I
1449018 |  | Open - Ready to Schedule | Preventive maintenance | 0600-PC-651-A-CONVEYOR | LEAD CAKE SCREW CONVEYOR-A | Screw Conveyor Quarterly PM | TMILLS2 | 2026-03-18 14:43 | 2026-04-13 | 600 | No | 1 | 4 | NC-MECHANIC EXE
1449019 |  | Open - Ready to Schedule | Preventive maintenance | 0600-PC-651-B-CONVEYOR | 0600-PC-651-B-LEAD CAKE SCREW CONVEYOR | Screw Conveyor Quarterly PM | TMILLS2 | 2026-03-18 14:43 | 2026-04-13 | 600 | No | 1 | 4 | NC-MECHANIC EXE
1449020 |  | Open - Ready to Schedule | Preventive maintenance | 0600-PX-613-A | 0600-PX-613-A LEAD PRECIPITATION PRESS FILTER PACKAGE | FILTER PRESS QUARTERLY [D4] | TMILLS2 | 2026-03-18 14:43 | 2026-04-27 | 600 | No | 2 | 4 | NC-MECHANIC EXE | CRITICAL
1449021 |  | Open - Ready to Schedule | Preventive maintenance | 0600-PX-613-A | 0600-PX-613-A LEAD PRECIPITATION PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:43 | 2026-04-21 | 600 | No | 1 | 1 | NC-LUBRICATOR
1449024 |  | Open - Ready to Schedule | Preventive maintenance | 0600-PX-613-B | 0600-PX-613-B LEAD PRECIPITATION PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:43 | 2026-04-21 | 600 | No | 1 | 1 | NC-LUBRICATOR
1449028 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | Weekly WOX (8) Blower Filter Replacements |  | 2026-03-18 14:43 | 2026-04-06 | 700 | No | 1 | 2 | NC-PM DAY
1449029 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | Weekly WOX (8) Blower Filter Replacements |  | 2026-03-18 14:43 | 2026-04-13 | 700 | No | 1 | 2 | NC-PM DAY
1449030 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | Weekly WOX (8) Blower Filter Replacements |  | 2026-03-18 14:43 | 2026-04-20 | 700 | No | 1 | 2 | NC-PM DAY
1449031 |  | Open - Ready to Schedule | Preventive maintenance | 700 | WOX UNLOADING, SLURRYING AREA 700 | Weekly WOX (8) Blower Filter Replacements |  | 2026-03-18 14:43 | 2026-04-27 | 700 | No | 1 | 2 | NC-PM DAY
1449032 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-A-CTRL | BH-701-A BROKEN BAG DETECTOR AT-7200A | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1449036 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-E-CTRL | FB-700E CONTROL AT-7200E | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1449035 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-D-CTRL | BH-701-D BROKEN BAG DETECTOR AT-7200D | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1449033 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-B-CTRL | BH-701-B BROKEN BAG DETECTOR AT-7200B | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1449034 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-C-CTRL | BH-701-C BROKEN BAG DETECTOR AT-7200C | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1449037 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-F-CTRL | BH-701-F BROKEN BAG DETECTOR AT-7200F | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] | SWORLEY2 | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1449038 |  | Open - Ready to Schedule | Preventive maintenance | 0700-AT-7200-G-CTRL | BH-701-G LIMESTONE SILO BROKEN BAG DETECTOR AT-7200G | MONTHLY CLEANING AND INSPECTION OF DUST MONITOR [R] |  | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 0.5 | NC-E/I | EHS
1449040 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-A | WOX SILO BIN A VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449041 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-A | WOX SILO BIN A VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449045 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-B | WOX SILO BIN B VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449042 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-A | WOX SILO BIN A VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449043 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-A | WOX SILO BIN A VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1449044 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-B | WOX SILO BIN B VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449046 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-B | WOX SILO BIN B VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449047 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-B | WOX SILO BIN B VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1449048 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-C | WOX SILO BIN C VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449049 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-C | WOX SILO BIN C VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449050 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-C | WOX SILO BIN C VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449054 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-D | WOX SILO BIN D VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449051 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-C | WOX SILO BIN C VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1449052 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-D | WOX SILO BIN D VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449053 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-D | WOX SILO BIN D VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449055 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-D | WOX SILO BIN D VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1449056 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-E | WOX SILO BIN E VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449057 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-E | WOX SILO BIN E VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449058 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-E | WOX SILO BIN E VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449059 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-E | WOX SILO BIN E VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1449063 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-F | WOX SILO BIN F VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-12 | 700 | No | 1 | 1 | NC-E/I | EHS
1449061 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-F | WOX SILO BIN F VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-05 | 700 | No | 1 | 1 | NC-E/I | EHS
1449065 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-F | WOX SILO BIN F VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-19 | 700 | No | 1 | 1 | NC-E/I | EHS
1449067 |  | Open - Ready to Schedule | Preventive maintenance | 0700-BH-701-F | WOX SILO BIN F VENT (1039 FT2 FILTER AREA, 0) | WEEKLY TIMING CHECK OF SOLENOIDS FOR BH-701/702-A-F [R] |  | 2026-03-18 14:43 | 2026-04-26 | 700 | No | 1 | 1 | NC-E/I | EHS
1448922 |  | Open - Ready to Schedule | Preventive maintenance | 0400-PA-401-CRANE | KUNZ CRANE #1 | BIANNUAL KUNZ CRANE CHECKS [R&D] |  | 2026-03-18 14:43 | 2026-04-06 | 400 | No | 4 | 8 | NC-E/I
1448921 |  | Open - Ready to Schedule | Preventive maintenance | 0400-NCW-1065 | NON-CONTACT COOLING WATER SYSTEM | Ajax non- contact cooling water strainer cleanÂ |  | 2026-03-18 14:43 | 2026-04-24 | 800 | No | 1 | 2 | NC-LUBRICATOR
1448919 |  | Open - Ready to Schedule | Preventive maintenance | 0400-GC-404-0-GEARBOX | GV-404 GEAR REDUCER | Hansen Gearbox Oil Change |  | 2026-03-18 14:43 | 2026-04-13 | 400 | No | 2 | 2 | NC-LUBRICATOR
1448920 |  | Open - Ready to Schedule | Preventive maintenance | 0400-GC-405-0-GEARBOX | GV-405 GEAR REDUCER | Hansen Gearbox Oil Change |  | 2026-03-18 14:43 | 2026-04-13 | 400 | No | 2 | 2 | NC-LUBRICATOR
1448923 |  | Open - Ready to Schedule | Preventive maintenance | 0400-PA-401-CRANE | KUNZ CRANE #1 | ENERGY CHAIN INSPECTION |  | 2026-03-18 14:43 | 2026-04-03 | 400 | No | 1 | 1 | NC-E/I
1448928 |  | Open - Ready to Schedule | Preventive maintenance | 0400-PA-402-CRANE | KUNZ CRANE #2 | ENERGY CHAIN INSPECTION |  | 2026-03-18 14:43 | 2026-04-10 | 400 | No | 1 | 1 | NC-E/I
1449000 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-501 | PX-501 HERZOG METALS ANALYZER | PX-501 Quarterly Lubrication PM |  | 2026-03-18 14:43 | 2026-04-08 | 500 | No | 1 | 1 | NC-MECHANIC EXE
1449001 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-501 | PX-501 HERZOG METALS ANALYZER | PX-501 MONTHLY PM |  | 2026-03-18 14:43 | 2026-04-20 | 500 | No | 1 | 0.75 | NC-MECHANIC EXE
1449002 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-502 | Fromm Banding Machine | Weekly sealer mechanism cleaning | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-01 | 500 | No | 1 | 2.5 | NC-PM DAY
1449003 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PX-502 | Fromm Banding Machine | Weekly sealer mechanism cleaning | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-08 | 500 | No | 1 | 2.5 | NC-PM DAY
1448933 |  | Open - Ready to Schedule | Preventive maintenance | 0400-PA-403-CRANE | PA-403 -AUXILIARY CRANE #1 | ENERGY CHAIN INSPECTION | MECH EXE CREW | 2026-03-18 14:43 | 2026-04-17 | 400 | No | 1 | 1 | NC-E/I
1448934 |  | Open - Ready to Schedule | Preventive maintenance | 0400-PA-404-CRANE | PA-404 -AUXILIARY CRANE #2 | ENERGY CHAIN INSPECTION |  | 2026-03-18 14:43 | 2026-04-24 | 400 | No | 1 | 1 | NC-E/I
1448950 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | SLAB LINE PM (D) |  | 2026-03-18 14:43 | 2026-04-18 | 500 | No | 2 | 3.5 | NC-MECHANIC EXE
1448951 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-06 | 500 | No | 1 | 2 | NC-PM DAY
1448952 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-13 | 500 | No | 1 | 2 | NC-PM DAY
1448953 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-20 | 500 | No | 1 | 2 | NC-PM DAY
1448954 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-501 | CA-501 -SLAB CASTING MACHINE LINE #1 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-27 | 500 | No | 1 | 2 | NC-PM DAY
1448955 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-502 | CA-502 -SLAB CASTING MACHINE LINE #2 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-06 | 500 | No | 1 | 2 | NC-PM DAY
1448956 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-502 | CA-502 -SLAB CASTING MACHINE LINE #2 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-13 | 500 | No | 1 | 2 | NC-PM DAY
1448957 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-502 | CA-502 -SLAB CASTING MACHINE LINE #2 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-20 | 500 | No | 1 | 2 | NC-PM DAY
1448958 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-502 | CA-502 -SLAB CASTING MACHINE LINE #2 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-27 | 500 | No | 1 | 2 | NC-PM DAY
1448962 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-503 | CA-503 -SLAB CASTING MACHINE LINE #3 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-27 | 500 | No | 1 | 2 | NC-PM DAY
1448960 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-503 | CA-503 -SLAB CASTING MACHINE LINE #3 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-13 | 500 | No | 1 | 2 | NC-PM DAY
1448959 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-503 | CA-503 -SLAB CASTING MACHINE LINE #3 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-06 | 500 | No | 1 | 2 | NC-PM DAY
1448961 |  | Open - Ready to Schedule | Preventive maintenance | 0500-CA-503 | CA-503 -SLAB CASTING MACHINE LINE #3 | WEEKLY SLAB LINE CHAIN LUBRICATION |  | 2026-03-18 14:43 | 2026-04-20 | 500 | No | 1 | 2 | NC-PM DAY
1448974 |  | Open - Ready to Schedule | Preventive maintenance | 0500-EER-AREA 500 | Electrical Room Area 500 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TPEACOCK2 | 2026-03-18 14:43 | 2026-04-27 | 500 | No | 1 | 1 | NC-E/I
1448975 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | MONTHLY BAGHOUSE LUBRICATION |  | 2026-03-18 14:43 | 2026-04-05 | 500 | No | 1 | 0.5 | NC-LUBRICATOR | EHS
1448976 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | WEEKLY AREA 500 BAGHOUSE DUST COLLECTOR MAINTENANCE | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-05 | 500 | No | 1 | 2.5 | NC-PM DAY | EHS
1448980 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | WEEKLY AREA 500 BAGHOUSE DUST COLLECTOR MAINTENANCE | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-19 | 500 | No | 1 | 2.5 | NC-PM DAY | EHS
1448977 |  | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | DAILY BAGHOUSE INSPECTION | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-05 | 500 | No | 1 | 5.25 | NC-PM DAY | EHS
1448978 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | WEEKLY AREA 500 BAGHOUSE DUST COLLECTOR MAINTENANCE | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-12 | 500 | No | 1 | 2.5 | NC-PM DAY | EHS
1448979 |  | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | DAILY BAGHOUSE INSPECTION | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-12 | 500 | No | 1 | 5.25 | NC-PM DAY | EHS
1448981 |  | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | DAILY BAGHOUSE INSPECTION | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-19 | 500 | No | 1 | 5.25 | NC-PM DAY | EHS
1448982 | 1-Emergency/Break-in | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | WEEKLY AREA 500 BAGHOUSE DUST COLLECTOR MAINTENANCE | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-26 | 500 | No | 1 | 2.5 | NC-PM DAY | EHS
1448983 |  | Open - Ready to Schedule | Preventive maintenance | 0500-FC-501 | MELTING FURNACE BAGHOUSE DUST COLLECTOR | DAILY BAGHOUSE INSPECTION | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-26 | 500 | No | 1 | 5.25 | NC-PM DAY | EHS
1448984 |  | Open - Ready to Schedule | Preventive maintenance | 0500-FD-502-0-FILTER | SLAB CASTING COOLING WATER FILTER | Semi-annual Cooling Water Strainer Cleaning |  | 2026-03-18 14:43 | 2026-04-20 | 500 | No | 1 | 1 | NC-LUBRICATOR
1448985 |  | Open - Ready to Schedule | Preventive maintenance | 0500-GE-501 | GE-501 500 EMERGENCY GENERATOR | Annual emergency generator load test | TPEACOCK2 | 2026-03-18 14:43 | 2026-04-01 | 500 | No | 1 | 1 | NC-CONT-ELEC
1448986 |  | Open - Ready to Schedule | Preventive maintenance | 0500-GE-501 | GE-501 500 EMERGENCY GENERATOR | Emergency Generator Monthly Maintenance-M/E | TPEACOCK2 | 2026-03-18 14:43 | 2026-04-05 | 500 | No | 1 | 1.5 | NC-MECHANIC EXE | EHS
1448991 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PC-503 | Slab Casting Transfer Cart/Walking Beam Conveyor | Walking Beam and Transfer cart Maintenance [D] |  | 2026-03-18 14:43 | 2026-04-06 | 500 | No | 1 | 0.5 | NC-PM NIGHT
1448992 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PC-503 | Slab Casting Transfer Cart/Walking Beam Conveyor | Walking Beam and Transfer cart Maintenance [D] |  | 2026-03-18 14:43 | 2026-04-13 | 500 | No | 1 | 0.5 | NC-PM NIGHT
1448993 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PC-503 | Slab Casting Transfer Cart/Walking Beam Conveyor | Walking Beam and Transfer cart Maintenance [D] |  | 2026-03-18 14:43 | 2026-04-20 | 500 | No | 1 | 0.5 | NC-PM NIGHT
1448994 |  | Open - Ready to Schedule | Preventive maintenance | 0500-PC-503 | Slab Casting Transfer Cart/Walking Beam Conveyor | Walking Beam and Transfer cart Maintenance [D] |  | 2026-03-18 14:43 | 2026-04-27 | 500 | No | 1 | 0.5 | NC-PM NIGHT
1448854 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-302-B | PX-302B CEMENTATION SOLUTION PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:43 | 2026-04-30 | 300 | No | 1 | 1 | NC-LUBRICATOR
1448861 |  | Open - Ready to Schedule | Preventive maintenance | 0300-PX-303-A | 0300-PX-303-A LIQUID EFFLUENT PRESS FILTER PACKAGE | MONTHLY FILTER PRESS LUBRICATION [D1] | TMILLS2 | 2026-03-18 14:43 | 2026-04-01 | 300 | No | 1 | 1 | NC-LUBRICATOR
1448873 |  | Open - Ready to Schedule | Preventive maintenance | 400 | ELECTROWINNING AREA 400 | AREA 0400 QUARTERLY OIL SAMPLE ANALYSIS |  | 2026-03-18 14:43 | 2026-04-10 | 400 | No | 1 | 1.5 | NC-LUBRICATOR
1448880 |  | Open - Ready to Schedule | Preventive maintenance | 0400-110KVAC-XFMR-UNIT1-MCB1 | 110KVAC TRANSFORMER RECTIFIER UNIT 1 MAIN CIRCUIT BREAKER | Monthly 100KV Breakers |  | 2026-03-18 14:43 | 2026-04-06 | 400 | No | 1 | 1 | NC-E/I
1448881 |  | Open - Ready to Schedule | Preventive maintenance | 0400-110KVAC-XFMR-UNIT2-MCB1 | 110KVAC TRANSFORMER RECTIFIER UNIT 2 MAIN CIRCUIT BREAKER | Monthly 100KV Breakers |  | 2026-03-18 14:43 | 2026-04-20 | 400 | No | 1 | 1 | NC-E/I
1448884 | 2-Urgent/Scheduled | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-HPU | ROW#1 MACHINE HYDRAULIC UNIT | CSM 1 HYDRAULIC CLAMP CHECK |  | 2026-03-18 14:43 | 2026-04-28 | 400 | No | 1 | 3 | NC-PM NIGHT
1448885 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | MONTHLY CSM BEARING GREASING [D] |  | 2026-03-18 14:43 | 2026-04-30 | 400 | No | 1 | 1 | NC-PM NIGHT
1448883 | 2-Urgent/Scheduled | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-HPU | ROW#1 MACHINE HYDRAULIC UNIT | CSM 1 HYDRAULIC CLAMP CHECK |  | 2026-03-18 14:43 | 2026-04-14 | 400 | No | 1 | 3 | NC-PM NIGHT
1448886 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | BIWEEKLY CSM INLET OUTLET MECHANICAL CHECK |  | 2026-03-18 14:43 | 2026-04-02 | 400 | No | 1 | 2 | NC-PM NIGHT
1448887 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | BIWEEKLY CSM INLET OUTLET MECHANICAL CHECK |  | 2026-03-18 14:43 | 2026-04-16 | 400 | No | 1 | 2 | NC-PM NIGHT
1448888 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-0-MACHINE | CA-401 ROW #1 STRIPPING MACHINE | BIWEEKLY CSM INLET OUTLET MECHANICAL CHECK |  | 2026-03-18 14:43 | 2026-04-30 | 400 | No | 1 | 2 | NC-PM NIGHT
1448889 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-CATHBRUSH | CA-401 Stripping machine Cathode Brush System | CSM BRUSHING ELEVATOR PM |  | 2026-03-18 14:43 | 2026-04-14 | 400 | No | 2 | 4 | NC-PM NIGHT
1448890 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-CATHBRUSH | CA-401 Stripping machine Cathode Brush System | CSM BRUSHING ELEVATOR PM |  | 2026-03-18 14:43 | 2026-04-28 | 400 | No | 2 | 4 | NC-PM NIGHT
1448894 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-STACKER | CA-401 Stripping Machine Stacker | CSM STACKER AND ROLLER TABLE PM |  | 2026-03-18 14:43 | 2026-04-27 | 400 | No | 2 | 4 | NC-PM NIGHT
1448891 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-HKNIFE | CA-401 Stripping Machine Horizontal Knife | Horizontal Knife Replacement [D] | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-03 | 400 | No | 2 | 2 | NC-PM NIGHT
1448892 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-HKNIFE | CA-401 Stripping Machine Horizontal Knife | Horizontal Knife Replacement [D] | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-17 | 400 | No | 2 | 2 | NC-PM NIGHT
1448893 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-STACKER | CA-401 Stripping Machine Stacker | CSM STACKER AND ROLLER TABLE PM |  | 2026-03-18 14:43 | 2026-04-13 | 400 | No | 2 | 4 | NC-PM NIGHT
1448895 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-TRANSCART | CA-401 Stripping machine Transfer Cart | CSM 1 BIWEEKLY TRANSFER CART GREASING |  | 2026-03-18 14:43 | 2026-04-02 | 400 | No | 1 | 1 | NC-PM NIGHT
1448896 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-TRANSCART | CA-401 Stripping machine Transfer Cart | CSM 1 BIWEEKLY TRANSFER CART GREASING |  | 2026-03-18 14:43 | 2026-04-16 | 400 | No | 1 | 1 | NC-PM NIGHT
1448897 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-401-TRANSCART | CA-401 Stripping machine Transfer Cart | CSM 1 BIWEEKLY TRANSFER CART GREASING |  | 2026-03-18 14:43 | 2026-04-30 | 400 | No | 1 | 1 | NC-PM NIGHT
1448898 | 3-First Opportunity | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-HPU | ROW#2 MACHINE HYDRAULIC UNIT | CSM 2 HYDRAULIC CLAMP CHECK |  | 2026-03-18 14:43 | 2026-04-07 | 400 | No | 1 | 3 | NC-MECHANIC EXE
1448899 | 3-First Opportunity | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-HPU | ROW#2 MACHINE HYDRAULIC UNIT | CSM 2 HYDRAULIC CLAMP CHECK |  | 2026-03-18 14:43 | 2026-04-21 | 400 | No | 1 | 3 | NC-MECHANIC EXE
1448903 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-CATHBRUSH | CA-402 Stripping Machine Cathode Brush System | CSM BRUSHING ELEVATOR PM |  | 2026-03-18 14:43 | 2026-04-08 | 400 | No | 2 | 4 | NC-PM NIGHT
1448900 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | MONTHLY CSM BEARING GREASING [D] |  | 2026-03-18 14:43 | 2026-04-30 | 400 | No | 1 | 1 | NC-PM NIGHT
1448901 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | BIWEEKLY CSM INLET OUTLET MECHANICAL CHECK |  | 2026-03-18 14:43 | 2026-04-09 | 400 | No | 1 | 2 | NC-PM NIGHT
1448902 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-0-MACHINE | CA-402 ROW#2 STRIPPING MACHINE | BIWEEKLY CSM INLET OUTLET MECHANICAL CHECK |  | 2026-03-18 14:43 | 2026-04-23 | 400 | No | 1 | 2 | NC-PM NIGHT
1448904 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-CATHBRUSH | CA-402 Stripping Machine Cathode Brush System | CSM BRUSHING ELEVATOR PM |  | 2026-03-18 14:43 | 2026-04-22 | 400 | No | 2 | 4 | NC-PM NIGHT
1448905 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-HKNIFE | CA-402 Stripping Machine Horizontal Knife | Horizontal Knife Replacement [D] | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-10 | 400 | No | 2 | 2 | NC-PM NIGHT
1448906 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-HKNIFE | CA-402 Stripping Machine Horizontal Knife | Horizontal Knife Replacement [D] | LOWER PM CREW | 2026-03-18 14:43 | 2026-04-24 | 400 | No | 2 | 2 | NC-PM NIGHT
1448907 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-STACKER | CA-402 Stripping Machine Stacker | CSM STACKER AND ROLLER TABLE PM |  | 2026-03-18 14:43 | 2026-04-06 | 400 | No | 2 | 4 | NC-PM NIGHT
1448908 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-STACKER | CA-402 Stripping Machine Stacker | CSM STACKER AND ROLLER TABLE PM |  | 2026-03-18 14:43 | 2026-04-20 | 400 | No | 2 | 4 | NC-PM NIGHT
1448909 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-TRANSCART | CA-402 Stripping Machine Transfer Cart | CSM 2 BIWEEKLY TRANSFER CART GREASING |  | 2026-03-18 14:43 | 2026-04-09 | 400 | No | 1 | 1 | NC-MECHANIC EXE
1448910 |  | Open - Ready to Schedule | Preventive maintenance | 0400-CA-402-TRANSCART | CA-402 Stripping Machine Transfer Cart | CSM 2 BIWEEKLY TRANSFER CART GREASING |  | 2026-03-18 14:43 | 2026-04-23 | 400 | No | 1 | 1 | NC-MECHANIC EXE
1448913 |  | Open - Ready to Schedule | Preventive maintenance | 0400-EER-AREA 400 | Electrical Room Area 400 | UNINTERRUPTIBLE POWER SOURCE ELECTRICAL MAINTENANCE [R/D] | TPEACOCK2 | 2026-03-18 14:43 | 2026-04-03 | 400 | No | 1 | 1 | NC-E/I
1448915 |  | Open - Ready to Schedule | Preventive maintenance | 0400-GB-401-0-PUMP | VACUUM PUMP | QUARTERLY LUBRICATION OF VACUUM SYSTEM PUMP AND MOTOR [R] |  | 2026-03-18 14:43 | 2026-04-06 | 400 | No | 1 | 1 | NC-LUBRICATOR
1448916 |  | Open - Ready to Schedule | Preventive maintenance | 0400-GC-401-0-FAN | GC-401 FAN | Hansen Gearbox Oil Change |  | 2026-03-18 14:43 | 2026-04-13 | 400 | No | 2 | 2 | NC-LUBRICATOR
1448917 |  | Open - Ready to Schedule | Preventive maintenance | 0400-GC-402-0-GEARBOX | GV-402 GEAR REDUCER | Hansen Gearbox Oil Change |  | 2026-03-18 14:43 | 2026-04-13 | 400 | No | 2 | 2 | NC-LUBRICATOR
1448918 |  | Open - Ready to Schedule | Preventive maintenance | 0400-GC-403-0-FAN | GV-403 FAN | Hansen Gearbox Oil Change |  | 2026-03-18 14:43 | 2026-04-13 | 400 | No | 2 | 2 | NC-LUBRICATOR